## Non-Proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: LAGOS STATE SPORTS COMMISSION
BUDGET YEAR: 2021
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER
1 | Travel and Transport within lagos | LSSC/NP/NM/001/21 | 1,920,000.00 | Plan | 160000 | 160000 | 160000 | 160000 | 160000 | 160000 | 160000 | 160000 | 160000 | 160000 | 160000 | 160000
Actual
2 | payment for dstv, phone cards and internet subscriptions | LSSC/NP/NM/002/21 | 5,280,000.00 | Plan | 440000 | 440000 | 440000 | 440000 | 440000 | 440000 | 440000 | 440000 | 440000 | 440000 | 440000 | 440000
Actual
3 | servicing of MTB and Staff Forums | LSSC/NP/NM/003/21 | 2640000 | Plan | 342400 | 342400 | 342400 | 342400 | 342400 | 342400 | 342400 | 342400 | 342400 | 342400 | 342400 | 342400
Actual
4 | Personel Insurance of 500 State Athletes | LSSC/NP/NM/004/21 | 1,000,000.00 | Plan | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000
Actual
5 | Promotion Exercise and PMBs | LSSC/NP/NM/005/21 | 6,000,000.00 | Plan
Actual
6 | monthly allowances to cleaners,security,groundsmen,garders and Adhoc staffs | LSSC/NP/NM/006/21 | 18,000,000.00 | Plan
Actual
7 | Interactive session with sports editors and correspondence | LSSC/NP/NM/007/21 | 1,200,000.00 | Plan
Actual
8 | Sponsorship for organising and celebration of international and national united nation's movement for disables | LSSC/NP/NM/008/21 | 4,000,000.00 | Plan
Actual
9 | Collection & analysis Data, preparation Annual Budget by the Planning unit | LSSC/NP/NM/009/21 | 270,000.00 | Plan
Actual
10 | monthly running cost for SSA to Gov on Sports and Facility | LSSC/NP/NM/010/21 | 2,400,000.00 | Plan | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000
Actual
11 | Donations at official functions | LSSC/NP/NM/011/21 | 2,000,000.00 | Plan
Actual
12 | Miscellaneous for unforseen sporting activities | LSSC/NP/NM/012/21 | 50500000 | Plan
Actual
13 | Grants for 43 sports Association Secretariat's annual running cost and Donations at functions | LSSC/NP/NM/013/21 | 7000000 | Plan
Actual
14 | sitting Allowance for 12 Board Members | LSSC/NP/NM/014/21 | 19000000 | Plan
Actual
15 | Sponsoring Hosting of Sports Events | LSSC/NP/NM/015/21 | 30000000 | Plan
Actual
16 | Participation in an organized Sponsored sports events | LSSC/NP/NM/016/21 | 60000000 | Plan
Actual
17 | Attending Sponsored international sports events and Lagos state summer camp | LSSC/NP/NM/017/21 | 71500000 | Plan
Actual
18 | Hosting of Sponsored International Table Tennis competition | LSSC/NP/NM/018/21 | 17500000 | Plan
Actual
19 | Hosting of sponsored International Squash Competition | LSSC/NP/NM/019/21 | 17500000 | Plan
Actual
20 | Hosting of Sponsored International Taekwando Competition | LSSC/NP/NM/020/21 | 13000000 | Plan
Actual
21 | Hosting of Sponsored International Badminton Competition | LSSC/NP/NM/021/21 | 20000000 | Plan
Actual
22 | support and sponsorship for State Physically Challenged Games | LSSC/NP/NM/022/21 | 100000000 | Plan
Actual
23 | sponsorship for Marathon and other Races | LSSC/NP/NM/023/21 | 560000000 | Plan
Actual
24 | Sponsorship National Youth Sports Festival | LSSC/NP/NM/024/21 | 150000000 | Plan
Actual
25 | monthly meeting of committee member of sports development department and quarterly Zonal meeting | LSSC/NP/NM/025/21 | 2000000 | Plan
Actual
26 | Instant Awards to Athelets | LSSC/NP/NM/026/21 | 5000000 | Plan
Actual
27 | Sponsorship of Lagos State secondary school Table Tennis Championship | LSSC/NP/NM/027/21 | 6200000 | Plan
Actual
28 | Sponsorship ofLagos State secondary school Handball copmpetition | LSSC/NP/NM/028/21 | 6000000 | Plan
Actual
29 | sponsorship Lagos State secondary school Combat sports competition | LSSC/NP/NM/029/21 | 6100000 | Plan
Actual
30 | sponsorship for Lagos State secondary school Cycling competition | LSSC/NP/NM/030/21 | 5200000 | Plan
Actual
31 | sponsorship for Lagos State secondary school relay | LSSC/NP/NM/031/21 | 5000000 | Plan
Actual
32 | sponsorship for Lagos State Secondary school Deaf games competition | LSSC/NP/NM/032/21 | 6000000 | Plan
Actual
33 | Sponsorship for Lagos State secondary school Swimmin competition | LSSC/NP/NM/033/21 | 5500000 | Plan
Actual
34 | sponsorship for Lagos State secondary school Racket games fiesta | LSSC/NP/NM/034/21 | 5028000 | Plan
Actual
35 | sponsorship for Lagos State Summer Camp (4Zone) | LSSC/NP/NM/035/21 | 100000000 | Plan
Actual
36 | sponsorship for Lagos State Principal Games (Principal Cup) | LSSC/NP/NM/036/21 | 35000000 | Plan
Actual
37 | sponsorship for Organisation of Association sports across 20 LGs and 37 LCDAs | LSSC/NP/NM/037/21 | 2000000000 | Plan
Actual
38 | sponsorship for Lagos State International | LSSC/NP/NM/038/21 | 13000000 | Plan
Actual
39 | sitting Allowance and Training of Board Members of sports commisssion | LSSC/NP/NM/039/21 | 38000000 | Plan
Actual
40 | sponsorhip of Eko Basketball league | LSSC/NP/NM/040/21 | 9000000 | Plan
Actual
41 | sponsorhip of Delegates to Y2021 Olympic Games | LSSC/NP/NM/041/21 | 35000000 | Plan
Actual
42 | sponsorship of Lagos State Ayo Olopon Open Challenge | LSSC/NP/NM/042/21 | 4300000 | Plan
Actual
43 | sponsorship for Ashoju Oba Table Tennis | LSSC/NP/NM/043/21 | 7000000 | Plan
Actual
44 | sponsorhsip for Southwest Judo Championship | LSSC/NP/NM/044/21 | 7000000 | Plan
Actual
45 | sponsorship of Rugby independence day international 7s | LSSC/NP/NM/045/21 | 7000000 | Plan
Actual
46 | sponsorship for Gymnastic southwest Artistic and Trampoline | LSSC/NP/NM/046/21 | 9000000 | Plan
Actual
47 | sponsorship of Community sports project (Sports coonect) | LSSC/NP/NM/048/21 | 10000000 | Plan
Actual
48 | sponsorship of Samaritan feet,youth clininc and volleyball Tournament | LSSC/NP/NM/048/21 | 9000000 | Plan
Actual
49 | sponsorship of Lagos Open Para Powerlifting Challenge | LSSC/NP/NM/049/21 | 15000000 | Plan
Actual
50 | 42 Sports Association Athletes Training grants | LSSC/NP/NM/050/21 | 216000000 | Plan
Actual
51 | Monthly allowance for Honourary coaches | LSSC/NP/NM/051/21 | 86400000 | Plan | 7200000 | 7200000 | 7200000 | 7200000 | 7200000 | 7200000 | 7200000 | 7200000 | 7200000 | 7200000 | 7200000 | 7200000
Actual
52 | Helpers Allowance | LSSC/NP/NM/052/21 | 9000000 | Plan | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000
Actual
53 | Lagos State football supporters club subvention | LSSC/NP/NM/053/21 | 1500000 | Plan
Actual
54 | Internal procurement Audit Expenses | LSSC/NP/NM/054/21 | 250000 | Plan
Actual

## trg conf wsh
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: LAGOS STATE SPORTS COMMISSION
BUDGET YEAR: 2021
S/N | Description of Training/Workshop/ Conference | Package Number | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | Local workshop for Executive Chairman and Director General | LSSC/S-WTC/SS/001/21 | Development and Capacity Building | 2 |  | Plan | Lagos | 400000 | 200000 | 100000 | 700000
Actual
2 | PSSDC training for officers | LSSC/S-WTC/SS/002/21 | Development and Capacity Building | 10 |  | Plan | Lagos | 860000 | 500000 | 750000 | 2110000
Actual
3 | Conferences and seminars for CIPM,NIM,ICAN,NBA & NPMCN | LSSC/S-WTC/SS/003/21 | Development and Capacity Building | 42 |  | Plan | Lagos | 15600000 | 5000000 | 7000000 | 22600000
Actual
4 | in-House Training of Sports Officers | LSSC/S-WTC/SS/004/21 | Development and Capacity Building | 120 |  | Plan | Lagos | 14000000 | 2000000 | 2000000 | 18000000
Actual
5 | MTSS & PMR training and conferences for Planners | LSSC/S-WTC/SS/005/21 | Development and Capacity Building | 18 |  | Plan | Abuja | 1500000 | 1000000 | 2000000 | 3500000
Actual
6 | CIPSM AND NIPR conferences and seminars | LSSC/S-WTC/SS/006/21 | Development and Capacity Building | 4 |  | Plan | Abuja | 700000 | 250000 | 400000 | 1150000
Actual
7 | Internal Training for Coaches (staff & Contract) | LSSC/S-WTC/SS/007/21 | Development and Capacity Building | 120 |  | Plan |  | 10000000 | 2500000 | 2500000 | 15000000
Actual
8 | Training for facilities managers | LSSC/S-WTC/SS/008/21 | Development and Capacity Building | 13 |  | Plan |  | 2500000 | 100000 | 50000 | 4000000
Actual
9 | [5 empty] | Plan
Actual
10 | [5 empty] | Plan
Actual
11 | [5 empty] | Plan
Actual

## non-cons
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY: LA GOS STATE SPORTS COMMISSION
BUDGET YEAR: 2021
Contract Description | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
| Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
Servicing of 10 Buses | LSSC/S-F/NS/001/21 | NA | 10 | 3120000 | <10,000,000.00 | NS | Plan | POST | POST | 10th Feb,2020 | 24th feb,2020 | 2nd Mar,2020 | 9th Mar.2020 | 16th Mar.2020 | 23rd Mar,2020 | 30th Mar,2020 | Plan | 27th Aprl,2020 | 29th Aprl,2020 | NA | 27th May,2020 | 10th June,2020 | 24th June,2020 | 8th July,2021
[7 empty] | Actual | [9 empty] | Actual
Teslim Balogun Stadium Facility Maintenance | LSSC/S-F/NS/002/21 | NA |  | 8307692.35 | <50,000,000.00 | NS | Plan | POST | PRIOR | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 16th Mar.2021 | 23rd Mar,2021 | 30th Mar,2021 | Plan | 27th Aprl,2021 | 29th Aprl,2021 | NA | 27th May,2021 | 10th June,2021 | 24th June,2021 | 8th July,2021
[7 empty] | Actual | [9 empty] | Actual
Agege Stadium Facility Maintenance | LSSC/S-F/NS/003/21 | NA |  | 8307692.35 | <10,000,000.00 | NS | Plan | POST | POST | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 16th Mar.2021 | 23rd Mar,2021 | 30th Mar,2021 | Plan | 27th Aprl,2021 | 29th Aprl,2021 | NA | 27th May,2021 | 10th June,2021 | 24th June,2021 | 8th July,2021
[7 empty] | Actual | [9 empty] | Actual
Rowe-Park Stadium Facility maintenance | LSSC/S-F/NS/004/21 | NA |  | 8307692.35 | <10,000,000.00 | NS | Plan | POST | POST | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 16th Mar.2021 | 23rd Mar,2021 | 30th Mar,2021 | Plan | 27th Aprl,2021 | 29th Aprl,2021 | NA | 27th May,2021 | 10th June,2021 | 24th June,2021 | 8th July,2021
[7 empty] | Actual | [9 empty] | Actual
Araromi Stadium facility maintenance | LSSC/S-F/NS/005/21 | NA |  | 8307692.35 | <10,000,000.00 | NS | Plan | POST | POST | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 16th Mar.2021 | 23rd Mar,2021 | 30th Mar,2021 | Plan | 27th Aprl,2021 | 29th Aprl,2021 | NA | 27th May,2021 | 10th June,2021 | 24th June,2021 | 8th July,2021
[7 empty] | Actual | [9 empty] | Actual
Amuto Stadium facility maitenance | LSSC/S-F/NS/006/21 | NA |  | 8307692.35 | <10,000,000.00 | NS | Plan | POST | POST | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 16th Mar.2021 | 23rd Mar,2021 | 30th Mar,2021 | Plan | 27th Aprl,2021 | 29th Aprl,2021 | NA | 27th May,2021 | 10th June,2021 | 24th June,2021 | 8th July,2021
[7 empty] | Actual | [9 empty] | Actual
Ijede Stadium Faiclity maitenance | LSSC/S-F/NS/007/21 | NA |  | 8307692.35 | <10,000,000.00 | NS | Plan | POST | POST | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 16th Mar.2021 | 23rd Mar,2021 | 30th Mar,2021 | Plan | 27th Aprl,2021 | 29th Aprl,2021 | NA | 27th May,2021 | 10th June,2021 | 24th June,2021 | 8th July,2021
[7 empty] | Actual | [9 empty] | Actual
Isheri Stadium Facility maintenance | LSSC/S-F/NS/008/21 | NA |  | 8307692.35 | <10,000,000.00 | NS | Plan | POST | POST | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 16th Mar.2021 | 23rd Mar,2021 | 30th Mar,2021 | Plan | 27th Aprl,2021 | 29th Aprl,2021 | NA | 27th May,2021 | 10th June,2021 | 24th June,2021 | 8th July,2021
[7 empty] | Actual | [9 empty] | Actual
Badagry Stadium Facility maitenance | LSSC/S-F/NS/009/21 | NA |  | 8307692.35 | <10,000,000.00 | NS | Plan | POST | POST | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 16th Mar.2021 | 23rd Mar,2021 | 30th Mar,2021 | Plan | 27th Aprl,2021 | 29th Aprl,2021 | NA | 27th May,2021 | 10th June,2021 | 24th June,2021 | 8th July,2021
[7 empty] | Actual | [9 empty] | Actual
Epe Stadium facility maintenance | LSSC/S-F/NS/010/21 | NA |  | 8307692.35 | <10,000,000.00 | NS | Plan | POST | POST | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 16th Mar.2021 | 23rd Mar,2021 | 30th Mar,2021 | Plan | 27th Aprl,2021 | 29th Aprl,2021 | NA | 27th May,2021 | 10th June,2021 | 24th June,2021 | 8th July,2021
[7 empty] | Actual | [9 empty] | Actual
Jalisco Stadium facility maintenance | LSSC/S-F/NS/011/21 | NA |  | 8307692.35 | <10,000,000.00 | NS | Plan | POST | POST | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 16th Mar.2021 | 23rd Mar,2021 | 30th Mar,2021 | Plan | 27th Aprl,2021 | 29th Aprl,2021 | NA | 27th May,2021 | 10th June,2021 | 24th June,2021 | 8th July,2021
[7 empty] | Actual | [9 empty] | Actual
Sari-Iganmu Stadium facility maintenance | LSSC/S-F/NS/012/21 | NA |  | 8307692.35 | <10,000,000.00 | NS | Plan | POST | POST | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 16th Mar.2021 | 23rd Mar,2021 | 30th Mar,2021 | Plan | 27th Aprl,2021 | 29th Aprl,2021 | NA | 27th May,2021 | 10th June,2021 | 24th June,2021 | 8th July,2021
[7 empty] | Actual | [9 empty] | Actual
Elegbeta Stadium facility maintenance | LSSC/S-F/NS/013/21 | NA |  | 8307692.35 | <10,000,000.00 | NS | Plan | POST | POST | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 16th Mar.2021 | 23rd Mar,2021 | 30th Mar,2021 | Plan | 27th Aprl,2021 | 29th Aprl,2021 | NA | 27th May,2021 | 10th June,2021 | 24th June,2021 | 8th July,2021
[7 empty] | Actual | [9 empty] | Actual
Ajele Campus-Mini Stadium facility maintenance | LSSC/S-F/NS/014/21 | NA |  | 8307692.35 | <10,000,000.00 | NS | Plan | POST | POST | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 16th Mar.2021 | 23rd Mar,2021 | 30th Mar,2021 | Plan | 27th Aprl,2021 | 29th Aprl,2021 | NA | 27th May,2021 | 10th June,2021 | 24th June,2021 | 8th July,2021
[7 empty] | Actual | [9 empty] | Actual
Retreat for 12 Board members | LSSC/S-NC/NS/001/21 | NA | 12 | 20000000 | <50,000,000.00 | NS | Plan | POST | POST | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 16th Mar.2021 | 23rd Mar,2021 | 30th Mar,2021 | Plan | 27th Aprl,2021 | 29th Aprl,2021 | NA | 27th May,2021 | 10th June,2021 | 24th June,2021 | 8th July,2021
[7 empty] | Actual | [9 empty] | Actual
Numbering and engraving of Fixed Assests | LSSC/S-NC/NS/002/21 | NA |  | 412000 | <10,000,000.00 | NS | Plan | POST | POST | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 16th Mar.2021 | 23rd Mar,2021 | 30th Mar,2021 | Plan | 27th Aprl,2021 | 29th Aprl,2021 | NA | 27th May,2021 | 10th June,2021 | 24th June,2021 | 8th July,2021
[7 empty] | Actual | [9 empty] | Actual
Catering for 42 Association scouting and zonal participationin competition | LSSC/S-NC/NS/003/21 | NA | 42 | 500000 | <10,000,000.00 | NS | Plan | POST | POST | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 16th Mar.2021 | 23rd Mar,2021 | 30th Mar,2021 | Plan | 27th Aprl,2021 | 29th Aprl,2021 | NA | 27th May,2021 | 10th June,2021 | 24th June,2021 | 8th July,2021
[7 empty] | Actual | [9 empty] | Actual
Catering for Athletes at National festival and International competitions | LSSC/S-NC/NS/004/21 | NA |  | 4000000 | <10,000,000.00 | NS | Plan | POST | POST | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 16th Mar.2021 | 23rd Mar,2021 | 30th Mar,2021 | Plan | 27th Aprl,2021 | 29th Aprl,2021 | NA | 27th May,2021 | 10th June,2021 | 24th June,2021 | 8th July,2021
[7 empty] | Actual | [9 empty] | Actual

## consultancy
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/ AGENCY: LAGOS STATE SPORTS COMMISSION
BUDGET YEAR: 2021
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[5 empty] | 0 |  | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
1 | Publication of Commission Annual Reports | LSSC/S-C/QCBS/001/21 | QCBS | Lump sum | 500000 | POST | Plan | 20th Jan,2021 | 3rd feb,2021 | 10th Feb,2021 | 24th Feb, 2021 | 2nd March,2021 | 16th March,2021 | 6th April,2021 | 13th April,2021 | 20th April,2021 | 27th April,2021 | 4th May,2021 | 11th May,2021 | 25th May,2021 | 26th May,2021 | NA | 2nd June,2021 | 16th June,2021 | 30th June,2021 | 7th July,2021 | 14th June,2021 | NA
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual

## goods
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: LAGOS STATE SPORTS COMMISSION
BUDGET YEAR: 2021
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Procurement of Locks and Electrical items | LSSC/G/NS/001/21 | NA | various | 1200000 | <10M | NS | POST Qualification | POST | Plan | 20th Jan,2021 | 3rd feb,2021 | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 6th Aprl,2021 | 8th Aprl,2021 | NA | 15th Aprl,2021 | 22nd Aprl,2021 | 6th May,2021 | 20th May,2021 | 3rd June,2021
Actual
2 | Purchase of 15 units of (15R/196)Tyres for Buses | LSSC/G/NS/002/21 | NA | 15 | 2016000 | <10M | NS | POST Qualification | POST | Plan | 20th Jan,2021 | 3rd feb,2021 | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 6th Aprl,2021 | 8th Aprl,2021 | NA | 15th Aprl,2021 | 22nd Aprl,2021 | 6th May,2021 | 20th May,2021 | 3rd June,2021
Actual
3 | procurement of Stationeries | LSSC/G/NS/003/21 | NA | various | 11680000 | <10M | NS | POST Qualification | POST | Plan | 20th Jan,2021 | 3rd feb,2021 | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 6th Aprl,2021 | 8th Aprl,2021 | NA | 15th Aprl,2021 | 22nd Aprl,2021 | 6th May,2021 | 20th May,2021 | 3rd June,2021
Actual
4 | Procurement of Information & Comuunication Consumables | LSSC/G/NS/004/21 | NA | various | 3300000 | <10,000,000.00 | NS | POST | POST | Plan | 20th Jan,2021 | 3rd feb,2021 | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 6th Aprl,2021 | 8th Aprl,2021 | NA | 15th Aprl,2021 | 22nd Aprl,2021 | 6th May,2021 | 20th May,2021 | 3rd June,2021
Actual
5 | Uniforms and Protective outfit for Security Personel | LSSC/G/NS/005/21 | NA | various | 1500000 | <10,000,000.00 | NS | POST | POST | Plan | 20th Jan,2021 | 3rd feb,2021 | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 6th Aprl,2021 | 8th Aprl,2021 | NA | 15th Aprl,2021 | 22nd Aprl,2021 | 6th May,2021 | 20th May,2021 | 3rd June,2021
Actual
6 | Audit Consumables and equipments | LSSC/G/NS/006/21 | NA | various | 590000 | <10,000,000.00 | NS | POST | POST | Plan | 20th Jan,2021 | 3rd feb,2021 | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 6th Aprl,2021 | 8th Aprl,2021 | NA | 15th Aprl,2021 | 22nd Aprl,2021 | 6th May,2021 | 20th May,2021 | 3rd June,2021
Actual
8 | Medical Consumables | LSSC/G/NS/008/21 | NA | various | 10500000 | <50,000,000.00 | NS | PRE | PRIOR | Plan | 20th Jan,2021 | 3rd feb,2021 | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 6th Aprl,2021 | 8th Aprl,2021 | NA | 15th Aprl,2021 | 22nd Aprl,2021 | 6th May,2021 | 20th May,2021 | 3rd June,2021
Actual
9 | procurement of gifts for Sendforth Party for retired Staffs | LSSC/G/NS/009/21 | NA | various | 1500000 | <50,000,000.00 | NS | POST | POST | Plan | 20th Jan,2021 | 3rd feb,2021 | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 6th Aprl,2021 | 8th Aprl,2021 | NA | 15th Aprl,2021 | 22nd Aprl,2021 | 6th May,2021 | 20th May,2021 | 3rd June,2021
Actual
10 | purchase of Jeseys and boots for HOS CUP | LSSC/G/NS/010/21 | NA | various | 3000000 | <50,000,000.00 | NS | POST | POST | Plan | 20th Jan,2021 | 3rd feb,2021 | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 6th Aprl,2021 | 8th Aprl,2021 | NA | 15th Aprl,2021 | 22nd Aprl,2021 | 6th May,2021 | 20th May,2021 | 3rd June,2021
Actual
11 | Procuring specialised stationeries for Qauterly stadia inspection and Annual Auditing | LSSC/G/NS/011/21 | NA |  | 540000 | <50,000,000.00 | NS | POST | POST | Plan | 20th Jan,2021 | 3rd feb,2021 | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 6th Aprl,2021 | 8th Aprl,2021 | NA | 15th Aprl,2021 | 22nd Aprl,2021 | 6th May,2021 | 20th May,2021 | 3rd June,2021
Actual
12 | Publicity & Press coverage | LSSC/G/NS/012/21 | NA |  | 2200000 | <10M | NS | POST | POST | Plan | 20th Jan,2021 | 3rd feb,2021 | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 6th Aprl,2021 | 8th Aprl,2021 | NA | 15th Aprl,2021 | 22nd Aprl,2021 | 6th May,2021 | 20th May,2021 | 3rd June,2021
Actual
13 | Production of chronicles boards | LSSC/G/NS/013/21 | NA | various | 400000 | <10M | NS | POST | POST | Plan | 20th Jan,2021 | 3rd feb,2021 | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 6th Aprl,2021 | 8th Aprl,2021 | NA | 15th Aprl,2021 | 22nd Aprl,2021 | 6th May,2021 | 20th May,2021 | 3rd June,2021
Actual
14 | Production of books | LSSC/G/NS/014/21 | NA | Various | 500000 | <10M | NS | POST | POST | Plan | 20th Jan,2021 | 3rd feb,2021 | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 6th Aprl,2021 | 8th Aprl,2021 | NA | 15th Aprl,2021 | 22nd Aprl,2021 | 6th May,2021 | 20th May,2021 | 3rd June,2021
Actual
15 | Consumables sport Equipment specialized | LSSC/G/NS/015/21 | NA | Various | 5500000 | >1M | ICB | PRE | PRIOR | Plan | 20th Jan,2021 | 3rd feb,2021 | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 6th Aprl,2021 | 8th Aprl,2021 | NA | 15th Aprl,2021 | 22nd Aprl,2021 | 6th May,2021 | 20th May,2021 | 3rd June,2021
Actual
16 | FuelIing of Motor Vehicles | LSSC/G-F/NS/001/21 | NA | 40 | 6480000 | <10M | NS | POST | POST | Plan | 20th Jan,2021 | 3rd feb,2021 | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 6th Aprl,2021 | 8th Aprl,2021 | NA | 15th Aprl,2021 | 22nd Aprl,2021 | 6th May,2021 | 20th May,2021 | 3rd June,2021
Actual
17 | Office furniture,sports facility tools and sports equipment | LSSC/G/1CB/001/21 | NA | various | 1122458983 | >1B | ICB | PRE | PRIOR | Plan | 20th Jan,2021 | 3rd feb,2021 | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 6th Aprl,2021 | 8th Aprl,2021 | NA | 15th Aprl,2021 | 22nd Aprl,2021 | 6th May,2021 | 20th May,2021 | 3rd June,2021
Actual

## works
PROCUREMENT PLAN FOR WORKS
MINISTRY: LAGOS STATE SPORTS COMMISSION
BUDGET YEAR: 2021
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
1 | [10 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual