## Non-Proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
LAGOS STATE PUBLIC PROCUREMENT AGENCY
BUDGET YEAR: 2021
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TOTAL
1 | Travel and Transport | PPA/NP/NM/001/21 | 2829999.99 | Plan | 235833.33 | 235833.33 | 235833.33 | 235833.33 | 235833.33 | 235833.33 | 235833.33 | 235833.33 | 235833.33 | 235833.35 | 235833.33 | 235833.33 | 2,829,999,99
Actual
2 | General Utilities Services, GOTV, DSTV etc | PPA/NP/NM/002/21 | 3500000
[5 empty] | 291666.67 |  | 291666.67 | 291666.67 | 291666.57 | 291666.67 | 291666.67 | 291,666/67 | 291666.67 | 291666.57 | 291666.67 | 291666.67 | 3500000
3 | Special Duties Expenses | PPA/NP/NM/003/21 | 15000000
[5 empty] | 1250000 |  | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 15000000
[5 empty] | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 15000000
4 | Miscelleaneous Expenses | PPA/NP/NM/004/21 | 1500000
[5 empty] | 125000 |  | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 1500000
5 | Board Expenses | PPA/NP/NM/005/21
|  |  | 15000000 |  | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1259000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 15000000
6 | Meeting Expenses | PPA/NP/NM/006/21 | 4013992
[5 empty] | 334499.33 | 334499.33 | 334499.33 | 334499.33 | 334499.33 | 334499.33 | 334499.33 | 334.499.33 | 334499.33 | 334499.33 | 344499.33 | 344499.33 | 4013992
7 | Application of Converter | PPA/NP/NM/007/21 | 260000
[5 empty] | 21666.67 | 21666.67 | 21666.67 | 21666.67 | 21666.67 | 21666.67 | 21666.67 | 21666.67 | 21666.67 | 21666.67 | 21666.67 | 21666.67 | 21666.67
8 | PPA Website Hosting and Yearly renewal | PPA/NP/NM/008/21 | 919000
[5 empty] | 76, 583.33 |  | 76, 583.33 | 76, 583.33 | 76, 583.33 | 76, 583.33 | 21666.67 | 21666.67 | 21666.67 | 21666.67 | 21666.67 | 21666.67 | 21666.67
9 | Swift Modem Subscription | PPA/NP/NM/009/21 | 1200000 |  |  | 76, 583.33
[5 empty] | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 1200000
10 | Adobe Fireworks Professionals subcriptions | PPA/NP/NM/010/21 | 250000
[5 empty] | 20833.33 | 20833.33 | 20833.33 | 20833.33 | 20833.33 | 20833.33 | 20833.33 | 20833.33 | 20833.33 | 20833.33 | 20833.33 | 20833.33 | 20833.33
11 | Staff Welfare | PPA/NP/NM/011/21 | 3500000
[5 empty] | 291666.67 |  | 291666.67 | 291666.67 | 291666.67 | 291666.67 | 291666.67 | 291666.67 | 291666.67 | 291666.67 | 291666.67 | 291666.67 | 3500000
15 | Salary of Support Staff & Intens | PPA/NP/NM/012/21 | 5040000 |  |  | 291666.67
[5 empty] | 420000 |  | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000
16 | Coutsey Visit to PPA from Others State | PPA/NP/NM/013/21 | 4500000 |  |  | 420000
[5 empty] | 375000 |  | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000
17 | TOTAL |  | 59573158.67 |  |  | 375000
59573158.67

## trg conf wsh
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: Ministry of the Environment and Water Resources, Office of Environmetal Services | LAGOS STATE PUBLIC PROCUREMENT AGENCY | [6 empty] | Z
BUDGET YEAR: 2021
| Description of Training/Workshop/ Conference | Package Number | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | Training and Workshop for newly employed & conversion Staff | PPA/S-WTC/SS/001/21 |  | 25 | 5Days | Plan |  |  |  |  | 1680000
[6 empty] | Actual | Lagos
2 | Special Workshop Training for Professional Cadres | PPA/S-WTC/SS/002/21 |  | 30 | 5days | Plan |  |  |  |  | 7200000
[6 empty] | Actual | Lagos |  |  |  | 3000000
3 | Advance Management Training for Management Staff | PPA/SWTC/SS/03 |  |  |  | Plan
Actual
4 | COWLSO Conferences | PPA/S-WTC/SS/003/21 |  | 20 | 3Days | Plan
[6 empty] | Actual | Abuja |  |  |  | 1800000
5 | To Organisevin-house Training base on identify programs | PPA/S-WTC/SS/004/21 |  |  |  | Plan |  |  |  |  | 3800000
[6 empty] | Actual | Lagos
6 | Payment of course fee &other allowance for staff on training within &outside Lagos | PPA/S-WTC/SS/005/21 |  |  |  | Plan |  |  |  |  | 520000
[6 empty] | Actual | Lagos &Other
7 | Professional Conference & Seminars for GM and two others Senior Management Staff for International Training | PPA/S-WTC/SS/007/21 |  | 3 | 5Days | Plan | Abuja |  |  |  | 9000000
Actual
8 | Professional Course for GM amd Other Sixteen Management Staff for Local Trainning, CIPSMN,ICAN, ANAN, CIPM etc | PPA/S-WTC/SS/008/21 |  | 17 |  | Plan | UK |  |  |  | 7200000
Actual
9 | Training a few (five) 5 Officers Pooled Procurement Cadre Statewide(GL13 &above) | PPA/S-WTC/SS/009/21 |  | 7 |  | Plan | Lagos |  |  |  | 2000000
Actual
10 | International Trainning for Board members. | PPA/S- WTC/SS/010/21
11 | International Trainning for Principal Officers.
| TOTAL |  |  | 3 |  | Plan
[6 empty] | Actual |  |  |  |  | 36200000
17
18
19
20
21

## non-cons
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY: LAGOS STATE PUBLIC PROCUREMENT AGENCY
BUDGET YEAR : 2021
LAGOS STATE PUBLIC PROCUREMENT AGENCY.
Contract Description | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
| Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
Mtce of office Building | PPA/S-NC-F/NS/001/20 |  | Various | 1500000 | <10M | NS | Plan | Pre | Post | 1O-Feb-2021 | NA | 17-Feb-'20 | 19-Feb-'21 | 21-Feb-'21 | 24-Feb-'21 | NA | Plan | 01-Mar-'21 | NA | 0 | 4-Mar-'21 | NA | 18-Mar-'21 | 19-Mar-'21
[7 empty] | Actual | [9 empty] | Actual
Mtce & Repairs of Motor Vehicles | PPA/S-NC-F/NS/002/21 |  | 13 | 7250000 | <10M | NS | Plan | Pre | Post | 13-Feb-'21 | NA | 17-Feb-'21 | 19-Feb-'21 | 21-Feb-'21 | 24-Feb-'21 | NA | Plan | 01- Mar'21 | NA | 0 | 4-Mar-'21 | NA | 18-Mar-'21 | 19-Mar-'21
[7 empty] | Actual | [9 empty] | Actual
Mtce and Repairs of Plant and Equipment | PPA/S-NC-F/NS/003/21 |  | Various | 1800000 | <10M | NS | Plan | Pre | Post | 13-Feb-'21 | NA | 17-Feb-'21 | 19-Feb-'21 | 21-Feb-'21 | 24-Feb-'21 | NA | Plan | 01- Mar'21 | NA | 0 | 4-Mar-'21 | NA | 18-Mar-'21 | 19-Mar-'21
[7 empty] | Actual | [9 empty] | Actual
Janitorial Services | PPA/S-NC-F/NS/004/21 |  |  | 2500000 | various | NS | <10M | NS | Plan | Pre | Post | 13-Feb-'21 | NA | 17-Feb-'21 | 19-Feb-'21 | 21-Feb-'21 | 24-Feb-'20 | NA | Plan | 0 | NA |  | 4-Mar-'21 | NA
[9 empty] | Actual | [9 empty] | Actual
Servicing and Maintenance of Printers and Photocopiers | PPA/S-NC-F/NS/005/21 |  | 30 | 430000 | <10M | NS | Plan | Pre | Post | 12-Feb-'21 | NA | 17-Feb-'21 | 18-Feb-'21 | 22-Feb-'21 | 24-Feb-'21 | NA | Plan | 01-03-'21 | NA | 0 | 4-Mar-'21 | NA | 18-Mar-'21 | 19-Mar-'21
[7 empty] | Actual | [9 empty] | Actual
ICT Maintenance/ Repairs, Laptops, PCs, etc | PPA/S-NC-F/NS/006/21 |  | Various | 600000 | <10M | NS | Plan | Pre | Post | 17-Mar-''21 | NA | 20-Mar-''21 | 25-Mar-''21 | 27-Mar-''21 | 30-Mar-''21 | NA | Plan | 2-Apr-''21 | NA | 0 | 6-Mar-''21 | NA | 10-Apr-''21 | 2021-04-13
[7 empty] | Actual | [9 empty] | Actual
Servicing and replacement of PR Equipment | PPA/S-NC-F/NS/007/21 |  | Various | 690000 | <10M | NS | Plan | Pre | Post | 20-Apr-''21 | NA | 23-Apr-''21 | 28-Apr-''21 | 30-Apr-''21 | 4-May-''21 | NA | Plan | 7-May-''21 | NA | 0 | 12-May-''21 | NA | 26-May-''21 | 29-May-''21
[7 empty] | Actual | [9 empty] | Actual
TOTAL |  |  |  | 14770000 |  |  | Plan | Pre | Post
[7 empty] | Actual | [9 empty] | Actual

## consultancy
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/ AGENCY: LAGOS STATE PUBLIC PROCUREMENT AGENCY
BUDGET YEAR: 2021
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[5 empty] | 0 |  | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
1 | Yearly Procurement Plan Clinic for Procuremet Officers | PPA/S-C/SSS/001/21 | SSS | LS | 8000000 | POST | Plan | 13-Jan-''21 | 20 Jan 21 | 27-1-21 | NA | NA | 17 Jan--''21 | 21-Jan-''21 | 24-Jan-''21 | 27-Jan-''21 | NA | 29 Jan 21 | NA | 12-Mar-''21 | NA | 0 | 2-Feb-2021 | 05 -Feb- 21 | NA | N/A | 8-Feb''21 | 8,000,000.00
Actual
2 | Year 2021 Annual Retreat | PPA/S-C/SSS/002/21 | SSS | LS | 15000000 | Prior | Plan | 10-Feb-''21 | 17-2-21 | 24-2-21 | NA | NA | 17-Feb-''21 | 24-Feb-''21 | 28-Feb-''20 | 4-Mar-''21 | NA | 9-Mar-''21 | NA | 12-Mar-''21 | NA | 0 | 19-Mar-''20 | 24-Mar-''21 | NA | 31-Mar-''20 | 7-Apr-''21
Actual
3 | Capacity Building for Procurement Cadre (Statewide) | PPA/S-C/SSS/003/21 | SSS | LS | 15000000 | Prior | Plan | 17-Mar-''21 | 31-3-21 | 05-04-21 | NA | NA | 20-Mar-''21 | 25-Mar-''21 | 3-Apr-''21 | 8-Apr-''21 | NA | 13-Apr-''21 | NA | 17-Apr-''21 | NA | 0 | 24-Apr-''21 | 29-Apr-''21 | NA | 8-May-''21 | 14-May-''21
Actual
4 | Media Appearance on print & Electronic Media and sponsorship of Futures Articles, Ministerial Press Briefing | PPA/S-C/SSS/004/21 | SSS | LS | 2500000 | POST | Plan | 17-Mar-''21 | 24-3-21 | NA | NA | NA | 20-Mar-''21 | 25-Mar-''21 | 3-Apr-''21 | 8-Apr-''21 | NA | 13-Apr-''21 | NA | 17-Apr-''20 | NA | 0 | 24-Apr-''20 | 29-Apr-''20 | NA | 8-May-''20 | 14-May-''20
Actual
5 | Annual State Procurement Summit | PPA/S-C/SSS/005/21 | SSS | LS | 3,500,000.00 | Prior | 20000000 | POST | Plan | 13-Apr-''21 | NA | NA | NA | NA | 16-Apr-''21 | 23-Apr-''21 | 4-May-''20 | 8-May-''20 | NA | 14-May-''20 | NA | 20-May-''21 | NA | 20000000 | 27-May-''20 | 3-June-''21 | NA | 10-Jun-''21
Actual
6 | Advocacy on Procurement Process | PPA/S-C/SSS/006/21 | SSS | LS | 10000000 | Prior | Plan | 13-Apr-''21 | 1900-01-19 | NA | NA | NA | 16-Apr-''21 | 23-Apr-''21 | 4-May-''21 | 8-May-''21 | NA | 14-May-''21 | NA | 20-May-''21 | NA | 0 | 27-May-''21 | 3-June-''21 | NA | 10-Jun-''21 | 17-Jun-''21
Actual
7 | Maintenance &Support for e- Procurement System | PPA/S-C/SSS/007/21 | SSS | LS | 40000000 | Prior | Plan | 3-Jun-''21 | 2021-06-10 | NA | NA | NA | 8-Jun-''21 | 17-June-''21 | 24-June-''21 | 3-July-''21 | NA | 10-July-''21 | NA | 16-July-''21 | NA | 0 | 24-July-''20 | 30-July-''21 | NA | 7-Aug-''20 | 14-Aug-''21
Actual
8 | Production of Annual Report Journal (Publicity) | PPA/S-C/SSS/008/21 | SSS | LS | 3,310,000.00 | POST | Plan | 3-Jun-''21 | NA | NA | NA | NA | 8-Jun-''21 | 17-June-''21 | 24-June-''21 | 3-July-''21 | NA | 10-July-''21 | NA | 16-July-''21 | NA | 0 | 24-July-''21 | 30-July-''21 | NA | 7-Aug-''20 | 14-Aug-''21
Actual
9 | Engagement of Business Community on Procurement process | PPA/S-C/SSS/009/21 | SSS | LS | 3500000 | POST | Plan | 3-June -''21 | 2021-06-10 |  |  | NA | 8-Jun-''21 | 17-June-''21 | 24-June-''21 | 3-July-''21 | NA | 10-July-''21 | NA | 16-July-''21 | NA | 0 | 24-July-''21 | 30-July-''21 | NA | 7-Aug-''21 | 14-Aug-''21
Actual
10 | Change Management on e-Procurement | PPA/S-C/SSS/010/21 | SSS | LS | 78939034 | Prior | Plan | 2021-01-25 | 2021-02-01 | 2021-02-15 | 2021-02-22 | NA | 16-Apr-''21 | 23-Apr-''21 | 4-May-''21 | 8-May-''21 | NA | 14-May-''21 | NA | 20-May-''21 | NA | 0 | 27-May-''21 | 3-June-''21 | NA | 10-Jun-''21 | 17-Jun-''21
Actual
11 | Branding of Agency | PPA/S-C/SSS/011/21 | SSS | LS | 640000 | POST | Plan | 5-Mar-''21 | NA | NA | NA | NA | 12=Mar-''21 | 19-Mar''21 | 19-Mar-''21 | 24-Mar-''21 | NA | 27-Mar-''21 | NA | 7-Apr-''21 | NA | 0 | 10-Apr-''21 | 16-Apr-''21 | NA | 23-Apr-''21 | 14-May-''21
Actual
12 | Integration and set-up of Environment for Ninety-Seven (97) MDAs on the e- Procurement Platform. | PPA/S-C-F/SSS/012/21 | SSS | LS | 727500000 | Prior |  | 05-Jan- '21 | 2021-01-05 | 2021-01-13 | 2021-01-20 |  | 2021-02-02 | 2-09-n21 | 2021-02-23 | 2021-02-26 | NA | 2021-03-05 | NA | 12=03-21 |  | 0 | 2021-03-19 | 2021-03-26 |  | 2021-03-30 | 2021-11-03
| TOTAL |  |  |  | 901079034

## goods
PROCUREMENT PLAN FOR GOODS.
| MINISTRY/AGENCY: Ministry of the Environment and Water Resources, Office of Environmental Services | STRY AGENT: LAGOS STATE PUBLIC PROCUREMENT AGENCY.
BUDGET YEAR: 2021
S/N | CONTRACT IDENTIFICATION | [9 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description |  | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[12 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Procurement of Stationeries |  | PPA/G-F/NS/001/21 |  | Various | 3000000 | <10M | NS | PRE | Post | Plan | 11-Jun-21 | 14-Jun-20 | 18-Jun-''21 | 21-Jun-''21 | 25-Jun-''21 | NA | 29-Jun-''21 | NA | 0.00 | 3-July-21 | 9-July-''21 | NA | 8-July-''20 | 9-July-''21
Actual
2 | Procurement of Inspection of Tools for Review and Monitoring. |  | PPA/G-F/NS/002/21 |  |  | 10000000 | <10M | NS | PRE | Post | Plan | 2021-02-21 | NA | 2021-02-25 | 2021-02-28 | 2021-03-03 | NA | 2021-03-06 | NA | 0 | 2021-03-10 | 2021-03-13 | NA | 2021-03-20 | 2021-03-23
Actual
3 | Procurement of Journals and Professional textbooks |  | PPA/G-F/NS/003/21 |  | Various | 170000 | <10M | NS | PRE | Post | Plan | 2021-02-21 | NA | 2021-02-25 | 2021-02-28 | 2021-03-03 | NA | 2021-03-06 | NA | 0 | 2020-03-10 | 2021-03-13 | NA | 2021-03-20 | 2021-03-23
Actual
4 | Procurement of Uniform and Protectives outfits |  | PPA/G-F/NS/004/21 |  | Various | 400000 | <10M | NS | PRE | Post | Plan | 2021-02-21 | NA | 2021-02-25 | 2021-02-28 | 2021-03-03 | NA | 2021-03-06 | NA | 0 | 2021-03-10 | 2021-03-13 | NA | 2021-03-20 | 2021-03-23
Actual
5 | Procurement of ICT Equipment |  | PPA/G-F/NS/005/21 |  | Various | 10000000 | <10M | NS | PRE | Post | Plan | 2021-03-10 | NA | 2021-03-12 | 2020-03-18 | 2021-03-23 | NA | 2021-03-27 | NA | 0 | 2021-03-31 | 3-Apr-'21 | NA | 10-Apr-''21 | 13-Apr-''21
Actual
6 | Procurement of Audit Tools |  | PPA/G-F/NS/006/21 |  | Various | 1500000 | <10M | NS | PRE | Post |  | 2-Apr-''21 | NA | 7-Apr-''21 | 10-Apr-''21 | 17-Apr-''21 | NA | 23-Apr-''21 | NA | 0 | 28-Apr-''21 | 30-Apr''21 | NA | 7-May-''21 | 8-May-''21
7 | Procurement of Planning tools and Instrument |  | PPA/G-F/NS/007/21 |  | Various | 1500000 | <10M | NS | PRE | Post | Plan | 2-Apr-''21 | NA | 7-Apr-''21 | 10-Apr-''21 | 17-Apr-''21 | NA | 23-Apr-''21 | NA | 0 | 28-Apr-''21 | 30-Apr''21 | NA | 7-May-''21 | 8-May-''21
Actual
8 | Procurement of Newspapers |  | PPA/G-F/NS/008/21 |  | Various | 650000 | <10M | NS | PRE | Post | Plan | 2-Apr-''21 | NA | 7-Apr-''21 | 10-Apr-''21 | 17-Apr-''21 | NA | 23-Apr-''21 | NA | 0 | 28-Apr-''21 | 30-Apr''21 | NA | 7-May-''21 | 8-May-''21
Actual
9 | Replacement and Servicing of PR Equipment |  | PPA/G-F/NS/009/21 |  | various | 690000 | <10M | NS |  |  |  | 2-Apr-''21 | NA | 7-Apr-''21 | 10-Apr-''21 | 17-Apr-''21 | NA | 23-Apr-''21 | NA | 0 | 28-Apr-''21 | 30-Apr''21 | NA | 7-May-''21 | 8-May-''21
10 | Procurement for Equipment for Onboarding of 97 MDAs and PPA |  | PPA/G-F/NS/010/21 |  | various | 102, 937,500.00 | >100M | NS |  | Pre | Plan | 2-Apr-''21 | NA | 7-Apr-''21 | 10-Apr-''21 | 17-Apr-''21 | NA | 23-Apr-''21 | NA | 0 | 28-Apr-''21 | 30-Apr''21 | NA | 7-May-''21 | 8-May-''21
Actual
11 | Procurement of Motor Vehicle Fuel |  | PPA/G-F/NS/011/21 |  | various | 10500000 | ≥10M | NS | PRE |  | Plan | 11-Jun-21 | NA | 18-Jun-''21 | 21-Jun-''21 | 25-Jun-''21 | NA | 29-Jun-''21 | NA | 0.00 | 3-July-21 | 9-July-''21 | NA | 8-July-''21 | 9-July-''21
Actual
12 | Procurement of Diesel for Generator |  | PPA/G-F/NS/012/21 |  | various | 2496974 | <10M | NS | PRE | Post | Plan | 13-May-''21 | NA | 15-May''21 | 20-May-''21 | 22-May-''21 | NA | 28-May-''21 | NA | 0 | 2-Jun-''21 | 5-Jun-''21 | NA | 12-Jun-''21 | 16-Jun-''21
Actual
13 | Procurement of Legal Tools & Documents |  | PPA/G-F/NS/013/21 |  | Various | 1500000 | <10M | NS | PRE | Post | Plan | 11-Jun-21 | 14-Jun-21 | 18-Jun-''21 | 21-Jun-''21 | 25-Jun-''21 | NA | 29-Jun-''21 | NA | 0.00 | 3-July-21 | 9-July-''21 | NA | 8-July-''21 | 9-July-''21
Actual
14 | TOTAL |  |  |  |  | 141844474 | [13 empty] | 0
184251448

## works
PROCUREMENT PLAN FOR WORKS
MINISTRY: LAGOS STATE PUBLIC PROCUREMENT AGENCY
BUDGET YEAR: 2020
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[9 empty] | Plan |  | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
Actual
1 | Remodelling of General Manager office | PPA/W/NS/001/21
2 | Remodelling of procurement Dept. Office | PPA/W/NS/002/21
3 | Development Power Back-up Sysyem (Inverter) | PPA/W/NS/003/21 |  | 3500000 | <50M | NS | LS | POST | Plan | Post | 14-May-''21 | NA | 19-May-''21 | 22-May''21 | 26-May-''21 | NA | 1-Jun-''21 | NA | 0 | 4-Jun-''21 | 11-Jun-''21 | 17-Jun-''21 | 1-Aug-''21 | 6-Aug-''21
Actual
| TOTAL |  |  | 3500000