## Non-Proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: LAGOS STATE CONSUMER PROTECTION AGENCY
BUDGET YEAR: Y2021
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TOTAL
1 | Servicing of court summons, Execution & matters relating to consumer court. | LASCOPA/NP/NM/001/21 | 1,516,000 | Plan | 126400 | 126400 | 126400 | 126400 | 126400 | 126400 | 126400 | 126400 | 126400 | 126400 | 126000 | 126000 | 1516000
Actual
2 | Payment for DSTV subscriptions for GM,Board Secretary,Admin Office & 5 Other Offices. | LASCOPA/NP/NM/002/21 | 2,710,000 | Plan | 225835 | 225835 | 225835 | 225835 | 225835 | 225835 | 225835 | 225835 | 225835 | 225835 | 225835 | 225835 | 2,710,000
Actual
3 | Payment of allowance for 5 volunters @35,000X 5 | LASCOPA/NP/NM/003/21 | 2100000 | Plan | 175000 | 175000 | 175000 | 175000 | 175000 | 175000 | 175000 | 175000 | 175000 | 175000 | 175000 | 175000 | 2100000
Actual
4 | Payment of 1 corp member @ 10,000 | LASCOPA/NP/NM/004/21 | 120,000 | Plan | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 120000
Actual
5 | Unforeseen Expenses for miscellaneous | LASCOPA/NP/NM/005/21 | 1,244,000 | Plan | 103000 | 103000 | 103000 | 103000 | 103000 | 103000 | 103000 | 103000 | 103000 | 103000 | 103000 | 111000 | 1244000
Actual
6 | Telephone Expenses for Complaint & Mediation Dept. | LASCOPA/NP/NM/006/21 | 2,000,000 | Plan | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 250000 | 250000 | 2000000
Actual
7 | Survelance | LASCOPA/NP/NM/007/21 | 1,200,000 | Plan | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 120000
Actual
8 | Hononourarium for 4 mopol officers @ 20,000 | LASCOPA/NP/NM/008/21 | 3,840,000 | Plan | 320000 | 320000 | 320000 | 320000 | 320000 | 320000 | 320000 | 320000 | 320000 | 320000 | 320000 | 320000 | 3840000
Actual
9 | General Investigation Expenses | LASCOPA/NP/NM/009/21 | 2,500,000 | Plan | 208000 | 208000 | 208000 | 208000 | 208000 | 208000 | 208000 | 208000 | 208000 | 208000 | 208000 | 212000 | 2500000
Actual
10 | Publicity & Press Coverage | LASCOPA/NP/NM/010/21 | 10000000 | Plan | 500000 | 500000 | 500000 | 500000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 10000000
Actual
11 | Hazards allowance for 35 staff @ 10,000 | LASCOPA/NP/NM/011/21 | 4200000 | Plan | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 4200000
Actual
12 | Stakeholders forum on food safety | LASCOPA/NP/NM/012/21 | 7000000 | Plan | 582000 | 582000 | 582000 | 582000 | 582000 | 582000 | 582000 | 582000 | 582000 | 582000 | 582000 | 598000 | 7000000
Actual
13 | Staff Welfare | LASCOPA/NP/NM/013/21 | 10600000 | Plan | 300000 | 300000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 10600000
Actual
14 | Seminars with stakeholders on products and consumers right | LASCOPA/NP/NM/014/21 | 10000000 | Plan | 625000 | 625000 | 625000 | 625000 | 625000 | 625000 | 625000 | 625000 | 625000 | 625000 | 625000 | 625000 | 10000000
15 | Mega Rally in all 5 Ibile Division`s of Lagos State |  |  | Actual
|  | LASCOPA/NP/NM/015/21 | 18000000 | Plan | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 18000000
Actual
16 | Planning Research & Statistics Expenses | LASCOPA/NP/NM/016/21 | 1542626 | Plan | 128000 | 128000 | 128000 | 128000 | 128000 | 128000 | 128000 | 128000 | 128000 | 128000 | 128000 | 134626 | 1542626
Actual
17 | Audit Unit Expenses | LASCOPA/NP/NM/017/21 | 1500000 | Plan | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 1500000
Actual
18 | Procurement Unit Expenses | LASCOPA/NP/NM/018/21 | 1000000 | Plan | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 100000 | 100000 | 1000000
Actual
19 | Institution of legal litigation | LASCOPA/NP/NM/019/21 | 1200000 | Plan | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 1200000
Actual
20 | Research & Development | LASCOPA/NP/NM/020/21
| Routine Laboratory Analysis | LASCOPA/NP/NM/020/21-1 | 2500000 | Plan | 208000 | 208000 | 208000 | 208000 | 208000 | 208000 | 208000 | 208000 | 208000 | 208000 | 208000 | 212000 | 2500000
| Capacity Building | LASCOPA/NP/NM/020/21-2 | 2500000 | Plan | 208000 | 208000 | 208000 | 208000 | 208000 | 208000 | 208000 | 208000 | 208000 | 208000 | 208000 | 212000 | 2500000
| Collection of Fruits | LASCOPA/NP/NM/020/21-3 | 3500000 | Plan | 250000 | 250000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 3500000
| Stakeholders Seminars | LASCOPA/NP/NM/020/21-4 | 3750000 | Plan | 312500 | 312500 | 312500 | 312500 | 312500 | 312500 | 312500 | 312500 | 312500 | 312500 | 312500 | 312500 | 3750000
| Biannual Product Return Policy | LASCOPA/NP/NM/020/21-5 | 4700000 | Plan | 350000 | 350000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 4700000
21 | Servicing of stakeholders, board meetings & general meetings | LASCOPA/NP/NM/021/21 | 2000000 | Plan | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 200000 | 200000 | 200000 | 200000 | 2000000
Actual
22 | Board members allowance | LASCOPA/NP/NM/022/21 | 3250000 | Plan | [12 empty] | 3250000
Actual
23 | Consumer Education | LASCOPA/NP/NM/023/21 |  | Plan
Actual
| Enlightenment at grassroot level | LASCOPA/NP/NM/023/21-1 | 3220000 | Plan | 265000 | 265000 | 265000 | 265000 | 265000 | 265000 | 265000 | 265000 | 265000 | 265000 | 265000 | 305000 | 32220000
| School Advocacy | LASCOPA/NP/NM/023/21-2 | 3600000 | Plan | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 3600000
| Public Enlightment on LGA`s / LCDA`S | LASCOPA/NP/NM/023/21-3 | 5600000 | Plan | 460000 | 460000 | 460000 | 460000 | 460000 | 460000 | 460000 | 460000 | 460000 | 460000 | 460000 | 540000 | 5600000
| Parley with stakeholders | LASCOPA/NP/NM/023/21-4 | 3000000 | Plan | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 3000000
24 | World Consumer Day | LASCOPA/NP/NM/024/21 | 1000000 | Plan | MARCH: 1000000 | 1000000
Actual
25 | Unforeseen incidence for motor vehicle | LASCOPA/NP/NM/025/21 | 550000 | Plan | 25000 | 25000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 550000
Actual
26 | Travel allowance for dispatch o f mails | LASCOPA/NP/NM/026/21 | 3240000 | Plan | 285000 | 285000 | 285000 | 285000 | 285000 | 285000 | 285000 | 285000 | 285000 | 285000 | 285000 | 285000 | 3240000
|  |  | 109552626 | Actual
27 | Rent Expenses | LASCOPA/NP/NM/027/21 | 24000000 | Plan | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 24000000
Actual
|  | TOTAL | 122432626

## trg conf wsh
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: LAGOS STATE CONSUMER PROTECTION AGENCY
BUDGET YEAR: Y2021
S/N | Description of Training/Workshop/ Conference | Package Number | Objective of Training/Workshop/Conference | No. of Participants | Duration (days) | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | Government Legal Adviser Course | LASCOPA/S-WTC/SS/001/21 |  | 1 | 1 | Plan | Abuja | 120000 | 65000 | 192000 | 377000
Actual
2 | Alternative Dispute Resolution | LASCOPA/S-WTC/SS/002/21 |  | 3 | 6 | Plan | Badagry | 450000 | 90000 | 1083000 | 1623000
Actual
3 | Team Building & Synergy for Peak Performance | LASCOPA/S-WTC/SS/003/21 |  | 1 | 5 | Plan | Ibadan | 70000 | 15000 | 180500 | 265000
Actual
4 | Preparation of Research Report | LASCOPA/S-WTC/SS/004/21 |  | 5 | 5 | Plan | Badagry | 375000 | 75000 | 902500 | 1352500
Actual
5 | Team Building & Synergy for Peak Performance | LASCOPA/S-WTC/SS/005/21 |  | 2 | 5 | Plan | Enugu | 180000 | 18000 | 427000 | 625000
Actual
6 | Preparation of Research Report | LASCOPA/S-WTC/SS/006/21 |  | 1 | 2 | Plan | Badagry | 75000 | 12000 | 121000 | 208000
Actual
7 | Mandatory Continuing Professional Development Programme (CIPSMN) | LASCOPA/S-WTC/SS/007/21 |  | 1 | 5 | Plan | Abeokuta | 50000 | 12000 | 121000 | 183000
Actual
8 | Global Norms & The Stability of Cyberspace MCPD | LASCOPA/S-WTC/SS/008/21 |  | 1 | 4 | Plan | Lagos | 80000 | 5000 | 10000 | 95000
Actual
9 | Chartered Institute of Mediator | LASCOPA/S-WTC/SS/009/21 |  | 10 | 2 | Plan | Lagos | 2500000 | 335000 | 726000
[6 empty] | Actual |  |  |  |  | 3561000
10 | Store Management & Inventory Control (CIPSMN) | LASCOPA/S-WTC/SS/010/21 |  | 1 | 4 | Plan | P/Harcourt | 70000 | 65000 | 30000
[6 empty] | Actual |  |  |  |  | 165000
11 | Alternative Dispute Resolution | LASCOPA/S-WTC/SS/011/21 |  | 16 | 5 | Plan | Badagry | 1200000 | 96000 | 2032000
[6 empty] | Actual |  |  |  |  | 3328000
12 | Conflict Management & Arbitration | LASCOPA/S-WTC/SS/012/21 |  | 2 | 2 | Plan | Lagos | 400000 | 30000 | 15000
[6 empty] | Actual |  |  |  |  | 450000
13 | Effective Budgeting & Budget Control In Private Public Sector | LASCOPA/S-WTC/SS/013/21 |  | 2 | 4 | Plan | Lagos | 65000 | 6000 | 2500
[6 empty] | Actual |  |  |  |  | 73500
14 | Alternative Dispute Resolution | LASCOPA/S-WTC/SS/014/21 |  | 6 | 4 | Plan | Badagry | 675000 | 90000 | 289500
15 | Effective Internal Auditor (Tools & Techniques for the Modern Auditor |  |  |  |  | Actual |  |  |  |  | 1054500
|  | LASCOPA/S-WTC/SS/015/21 |  | 1 | 4 | Plan | Lagos | 122000 | 10000 | 15000
16 | Consulting Skills for HR Practitioners | LASCOPA/S-WTC/SS/016/21 |  |  |  | Actual |  |  |  |  | 147000
|  |  |  | 2 | 2 | Plan | Lagos | 160000 | 6000 | 5000
17 | Mandatory Continuing Professional Development Programme | LASCOPA/S-WTC/SS/017/21 |  | 2 | 2 | Plan | Abeokuta | 100000 | 20000 | 181500 | 171000
Actual
18 | Negociation & Influencial Skill (ASCON) |  |  | 10 | 5 | Plan | Badagry | 750000 | 100000 | 907500 | 301500
|  | LASCOPA/S-WTC/SS/018/21 |  |  |  | Actual |  |  |  |  | 1757500
19 | Efficiency E-Performance Improvement | LASCOPA/S-WTC/SS/019/21 |  | 2 | 5 | Plan | Ibadan | 140000 | 121000 | 15000
Actual
20 | Negociation & Influencial Skill (ASCON) | LASCOPA/S-WTC/SS/020/21 |  | 12 | 5 | Plan | Badagry | 900000 | 90000 | 717000 | 276000
Actual
21 | Environmental Management | LASCOPA/S-WTC/SS/021/21 |  | 8 | 4 | Plan | Badagry | 1200000 | 120000 | 968000 | 1716000
Actual
22 | Financial Accounting & Reporting- A Strategy for Service Delivery. | LASCOPA/S-WTC/SS/022/21 |  | 8 | 4 | Plan | Abeokuta | 520000 | 60000 | 484000 | 2288000
Actual
23 | Data Processing & Analysing Using SPPSS | LASCOPA/S-WTC/SS/023/21 |  | 4 | 5 | Plan | Badagry | 400000 | 30000 | 242000 | 1064000
Actual
24 | Negociation & Influencial Skill (ASCON) | LASCOPA/S-WTC/SS/024/21 |  | 8 | 5 | Plan | Badagry | 600000 | 24000 | 440000 | 672000
Actual
25 | Advanced Management Clerical Skills (Best Practice) | LASCOPA/S-WTC/SS/025/21 |  | 2 | 4 | Plan | Ibadan | 130000 | 15000 | 121000 | 1064000
Actual
26 | NBA 2021 Conference | LASCOPA/S-WTC/SS/026/21 |  | 4 | 3 | Plan | Abuja | 600000 | 260000 | 1256000 | 266000
Actual
27 | Journalist Conference | LASCOPA/S-WTC/SS/027/21 |  | 4 | 2 | Plan | Abuja | 240000 | 260000 | 768000 | 2116000
Actual
28 | CIPM Conference | LASCOPA/S-WTC/SS/028/21 |  | 2 | 4 | Plan | Abuja | 150000 | 128000 | 288000 | 1268000
Actual
29 | ANAN Conference | LASCOPA/S-WTC/SS/029/21 |  | 2 | 3 | Plan | Abuja | 90000 | 128000 | 357000 | 566000
Actual
30 | Mandatory Proficiency Programme In Supply Chain | LASCOPA/S-WTC/SS/030/21 |  | 2 | 2 | Plan | Abuja | 120000 | 130000 | 486000 | 575000
Actual
31 | Computer Professional Reg. Concil of Nigeria | LASCOPA/S-WTC/SS/031/21 |  | 2 | 3 | Plan | Imo | 140000 | 128000 | 218000 | 736000
Actual
32 | Seminars on Speech Writing | LASCOPA/S-WTC/SS/032/21 |  | 1 | 2 | Plan | Badagry | 75000 | 12000 | 144000 | 486000
Actual
33 | Nigerian Statistical Association Conference | LASCOPA/S-WTC/SS/033/21 |  | 1 | 2 | Plan | Abuja | 60000 | 61000 | 142250 | 231000
Actual
34 | ICAN Conference | LASCOPA/S-WTC/SS/034/21 |  | 1 | 2 | Plan | Abuja | 110000 | 61000 | 142250 | 263500
Actual
35 | CIPM Conference | LASCOPA/S-WTC/SS/035/21 |  | 2 | 2 | Plan | Abuja | 150000 | 122000 | 193000 | 313500
[6 empty] | Actual |  |  |  |  | 465000
30000000

## non-cons
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY:
Y2021
LAGOS STATE CONSUMER PROTECTION AGENCY
Contract Description | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
| Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
Maintainance of Office building | LASCOPA/S-NC/NCB/001/21 | 1 |  | 2000000 |  | QCBS | Plan | Post | Post | 2021-02-08 | N/A | 2021-02-08 | 15/03/21 | 2021-04-01 | 2021-04-08 | 2021-04-22 | Plan | May/6/21 | 05/07/21 | 2000000 | 2021-06-06 | 18/06/21 | 2021-07-02
[7 empty] | Actual | [9 empty] | Actual
Replacement of damage window blind |  | 2 |  | 1000000 |  | QCBS | Plan | Post | Post | 2021-02-08 | N/A | 2021-02-08 | 15/03/21 | 2021-04-01 | 2021-04-08 | 2021-04-22 | Plan | May/6/21 | 05/07/21 | 1260000 | 2021-06-06 | 18/06/21 | 2021-07-02
|  |  |  | 1260000 |  |  | Actual | [12 empty] | 1000000
Partitioning of PRS, Procurement, Legal & ICT Unit |  | 3 |  | 1260000 |  | QCBS | Plan | Post | Post | 2021-02-08 | N/A | 2021-02-08 | 15/03/21 | 2021-04-01 | 2021-04-08 | 2021-04-22 | Plan | 13/05/21 | 14/05/21 |  | 2021-06-11 | 25/06/21 | 2021-07-09
Actual
Motor Vehicle repairs & maintainance | LASCOPA/S-NC/NCB/002/21 |  |  | 1200000 |  | QCBS | Plan | Post | Post | 2021-03-05 | N/A | 2021-03-12 | 26/03/21 | 2021-04-02 | 2021-04-09 | 23/04/21 | Plan | May/6/21 | 05/07/21 | 1200000 | 2021-06-06 | 18/06/21 | 2021-07-02
Retreat & Summit | LASCOPA/S-NC/NCB/003/21 |  |  | 13000000 |  | QCBS | Actual | Pre | Prior | 13/07/21 | 20/07/21 | 27/07/21 | 2021-08-10 | 24/08/21 | 31/08/21 | 2021-09-07 | Actual | 2021-05-10 | 2021-07-10 | 13000000 | 2021-11-11 | 25/11/21 | 2021-09-12
| TOTAL |  |  | 18460000

## consultancy
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/ AGENCY:
BUDGET YEAR:
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[5 empty] | 0 |  | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
1 | Maintainance of Office Building | LASCOPA/S-C-F/QCBS/001/21-1 | QCBS | Time- based | 2000000 | Prior Review | Plan | 08-02-21 | N/A | 08-03-21 | 15-03-21 | N/A | 22-03-21 | 26-04-21 | 03-05-21 | 17-03-21 | 24-05-21 | 24-05-21 | N/A | 28-06-21 | 29-06-21 | 2000000 | 05-07-21 | 12-07-21 | 26-07-21 | 02-08-21 | 10-08-21
Actual
| Replacement of damage window blind | LASCOPA/S-C-F/QCBS/001/21-2 | QCBS | Time- based | 1100000 | Prior Review | Plan | 08-02-21 | N/A | 08-03-21 | 15-03-21 | N/A | 22-03-21 | 26-04-21 | 03-05-21 | 17-03-21 | 24-05-21 | 24-05-21 | N/A | 28-06-21 | 29-06-21 | 1000000 | 05-07-21 | 12-07-21 | 26-07-21 | 02-08-21 | 10-08-21
Actual
| Partitioning of PRS, Procurement, Legal & ICT Office | LASCOPA/S-C-F/QCBS/001/21-3 | QCBS | Time- based | 1260000 | Prior Review | Plan | 08-02-21 | N/A | 08-03-21 | 15-03-21 | N/A | 22-03-21 | 26-04-21 | 03-05-21 | 17-03-21 | 24-05-21 | 24-05-21 | N/A | 28-06-21 | 29-06-21 | 1260000 | 05-07-21 | 12-07-21 | 26-07-21 | 02-08-21 | 10-08-21
Actual
2 | Motor vehicle repairs & Maintenance | LASCOPA/S-C-F/QCBS/002/21 | QCBS | Time- based | 1200000 | Prior Review | Plan | 15-02-21 | N/A | 22-02-21 | 22-03-21 | N/A | 29-03-21 | 2021-12-03 | 19-04-21 | 2021-03-05 | 2021-10-05 | 17-05-21 | N/A | 14-06-21 | 16-06-21 | 1200000 | 23-06-21 | 2021-06-07 | 27-07-21 | 2021-03-08 | 2021-10-08
Actual
3 | Retreat and summit | LASCOPA/S-C-F/QCBS/003/21 | QCBS | Time- based | 13000000 | Prior Review | Plan | 30-03-21 | 30-04-21 | 2021-07-05 | 21-05-21 | 28-05-21 | 2021-04-06 | 24-06-21 | 30-06-21 | 2021-12-07 | 19-07-21 | 28-07-21 | 2021-02-08 | 23-08-21 | 25-08-21 | 13000000 | 31-08-21 | 14-09-21 | 28-09-21 | 2021-05-10 | 19-10-21
Actual
4 | Rent Expenses | LASCOPA/S-C-F/SS/004/21 | SS | Lump sum | 24000000 | Prior | Plan | 2021-04-01 | 2021-04-01 | 2021-04-01 | 2021-04-01 | 2021-04-01 | 2021-04-01 | 2021-11-01 | 18-01-21 | 19-01-21 | 22-01-21 | 25-01-21 | 29-01-21 | 2021-03-02 | 24-02-21 | 24000000 | 26-02-21 | 2021-08-03 | 22-03-21 | 25-01-21 | 30-03-21
Actual
5 | Subscription of Internet | LASCOPA/S-C-F/SS/005/21 | SS | Lump sum | 1440000 | Prior | Plan | 2021-04-01 | N/A | 2021-11-01 | 25-01-2021 | N/A | 2021-08-02 | 2021-01-03 | 15-03-2021 | 20-03-2021 | 2021-05-04 | 19-04-2021 | 26-04-2021 | 17-05-2021 | 19-05-2021 | 1440000 | 25-05-2021 | 2021-08-06 | 22-06-2021 | 29-06-2021 | 2021-06-07
Actual
6 | Implementation / Settling of Electronic / Digital Filling System | LASCOPA/S-C-F/SS/006/21 | SS | Time- based | 7000000 | Prior | Plan | 2021-08-03 | 22-03-2021 | 29-03-2021 | 2021-12-04 | N/A | 26-04-2021 | 17-05-2021 | 24-05-2021 | 2021-07-06 | 14-06-2021 | 21-06-2021 | N/A | 19-07-2021 | 21-07-2021 | 7000000 | 26-07-2021 | 2021-09-08 | 23-08-2021 | 2021-09-09 | 16-09-2021
|  |  |  | TOTAL | 51000000

## goods
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: LAGOS STATE CONSUMER PROTECTION AGENCY
BUDGET YEAR: Y2021
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Purchase of fuel for 2 official vehicles and 10 management staff | LASCOPA/G/NS/001/21 | 1 |  | 3870000 | <10,000,000 | National shopping | Post | Post | Plan | 2021-04-02 | NA | 18/2/21 | 25/3/21 | 2021-01-04 | NA | 15/4/21 | 19/4/21 |  | 26/4/21 | 2021-06-05 | 20/4/21
2 | Procurement of Stationery | LASCOPA/G/NS/002/21 | 1 |  | 6000000 | <10,000,000 | National shopping | Post | Post | Plan | 26/2/21 | N/A | 2021-11-03 | 25/3/21 | 2021-01-04 | N/A | 21/4/21 | 22/4/21 |  | 29/4/21 | 2021-06-05 | 13/5/21
Actual
3 | Procurement of Management Information System Equipments | LASCOPA/G/NS/003/21 | 1 |  | 1560000 | <10,000,000 | National shopping | Post | Post | Plan | 2021-02-19 | N/A | 2021-03-04 | 18/3/21 | 2021-04-01 | N/A | 2021-04-15 | 16/4/21 |  | 23/4/21 | 30/4/21 | 14/5/21
Actual
4 | Procurement of consumables for Complaint & Mediation Dept. | LASCOPA/G/NS/004/21 | 1 |  | 2440000 | <10,000,000 | National shopping | Post | Post | Plan | 2021-02-26 | N/A | 2021-03-11 | 2021-04-01 | 2021-04-08 | N/A | 2021-04-22 | 23/4/21 |  | 30/4/21 | 2021-05-07 | 2021-05-21
Actual
5 | Procurement of raincoats, boots,nose guard, gloves,customized T-Shirt and jackets for Enforcement & Compliance | LASCOPA/G/NS/005/21 | 1 |  | 1500000 | <10,000,000 | National shopping | Post | Post | Plan | 19/2/21 | N/A | 2021-03-05 | 2021-04-09 | 2021-04-16 | N/A | 2021-05-14 | 2021-05-17 |  | 2021-05-24 | 2021-06-03 | 2021-06-17
Actual
6 | Procurement of uniforms and protectives and other items under special duties expenses | LASCOPA/G/NS/006/21 | 1 |  | 4000000 | <10,000,000 | National shopping | Post | Post | Plan | 2021-03-06 | N/A | 2021-10-06 | 24/6/21 | 2021-01-07 | 2021-08-07 | 29/7/21 | 30/7/21 |  | 2021-06-08 | 13/8/21 | 20/8/21
Actual
7 | Procurement of laptops under Special Duties Expenses | LASCOPA/G/NS/007/21 | 1 |  | 3000000 | <10,000,000 | National shopping | Post | Post | Plan | 2021-03-06 | N/A | 2021-10-06 | 24/6/21 | 2021-01-07 | 2021-08-07 | 29/7/21 | 30/7/21 |  | 2021-06-08 | 13/8/21 | 20/8/21
Actual
8 | Procurement of computer consumables and accessories for ICT Unit | LASCOPA/G/NS/008/21 | 1 |  | 1000000 | <10,000,000 | National shopping | Post | Post | Plan | 2021-04-06 | N/A | 2021-06-11 | 24/6/21 | 2021-01-07 | 2021-08-07 | 29/7/21 | 30/7/21 |  | 2021-06-08 | 13/8/21 | 20/8/21
Actual
9 | Procurement of legal books | LASCOPA/G/NS/009/21 | 1 |  | 800000 | <10,000,000 | National shopping | Post | Post | Plan | 2021-05-02 | N/A | 2021-02-12 | 26/2/21 | 2021-03-05 | N/A | 2021-03-12 | 2021-03-15 |  | 2021-03-19 | 2021-03-26 | 2021-04-02
Actual
10 | Procurement of 2 motor bikes, registration and other accessories,accessories for 3 utility vehicle | LASCOPA/G/NS/010/21 | 1 |  | 3450000 | <10,000,000 | National shopping | Post | Post | Plan | 2021-03-02 | N/A | 17/2/21 | 18/3/21 | 25/3/21 | N/A | 13/4/21 | 2021-04-15 |  | 2021-04-22 | 2021-04-29 | 20/5/21
Actual
11 | Procurement of Office Fittings / Equipment | LASCOPA/G/NS/011/21 | 1 |  | 4490000 | <10,000,000 | National shopping | Post | Post | Plan | 2021-02-19 | N/A | 2021-03-04 | 2021-04-08 | 2021-04-15 | N/A | 2021-04-29 | 2021-05-17 |  | 2021-05-25 | 2021-06-01 | 2021-06-15
Actual
12 | Setting up of Offices in 10 LGA | LASCOPA/G/NS/012/21 | 1 |  | 24050000 | >10,000,000 | National shopping | Post | Post | Plan | 2021-08-10 | 18/8/21 | 2021-09-01 | 22/9/21 | 2021-09-29 | 2021-10-06 | 2021-10-21 | 28/10/21 |  | 2021-11-04 | 2021-11-11 | 2021-11-25
Actual
|  |  | TOTAL |  | 56160000
112320000

## works
PROCUREMENT PLAN FOR WORKS
MINISTRY:
BUDGET YEAR:
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual