## Non-Proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: LAGOS STATE INDEPENDENT ELECTORAL COMMISSION
BUDGET YEAR: 2021
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TOTAL
1 | Travel and Transport | LASIEC/NP/NM/001/21 | 27819339 | Plan | 2318278.25 | 2318278.25 | 2318278.25 | 2318278.25 | 2318278.25 | 2318278.25 | 2318278.25 | 2318278.25 | 2318278.25 | 2318278.25 | 2318278.25 | 2318278.25 | 27819339
Actual
2 | Payment for Utility Services (Payment of Electricity Bills, Waste Disposal, Recharge Cards, Water rates, Subsription for DSTV,CUG, Internet Connectivity | LASIEC/NP/NM/002/21 | 19094395 | Plan | 1591199.58 | 1591199.58 | 1591199.58 | 1591199.58 | 1591199.58 | 1591199.58 | 1591199.58 | 1591199.58 | 1591199.58 | 1591199.58 | 1591199.6 | 1591199.6 | 19094395
Actual
3 | Statutory Commission Meetings | LASIEC/NP/NM/003/21 | 1440000 | Plan |  | 240000 |  | 240000 |  | 240000 |  | 240000 |  | 240000 |  | 240000 | 1440000
Actual
4 | Management Meetings | LASIEC/NP/NM/004/21 | 1440000 | Plan |  | 240000 |  | 240000 |  | 240000 |  | 240000 |  | 240000 |  | 240000 | 1440000
Actual
5 | Personnel Management Board Meetings | LASIEC/NP/NM/005/21 | 900000 | Plan |  | 150000 |  | 150000 |  | 150000 |  | 150000 |  | 150000 |  | 150000 | 900000
Actual
6 | Senatorial District Meeting with Stakeholders | LASIEC/NP/NM/006/21 | 1840740 | Plan |  | 306790 |  | 306790 |  | 306790 |  | 306790 |  | 306790 |  | 306790 | 1840740
Actual
7 | Attendance of Commission Members at Forum of State Independent Electoral Commission National Delegates Conference | LASIEC/NP/NM/007/21 | 2053778 | Plan |  | 342296 |  | 342296 |  | 342296 |  | 342296 |  | 342296 |  | 342298 | 2053778
Actual
8 | Operation and Logistic Meetings with Electoral Officers | LASIEC/NP/NM/008/21 | 1440000 | Plan |  | 240000 |  | 240000 |  | 240000 |  | 240000 |  | 240000 |  | 240000 | 1440000
Actual
9 | Attendance at South West SIEC's Meetings by Chairman | LASIEC/NP/NM/009/21 | 600000 | Plan |  | 100000 |  | 100000 |  | 100000 |  | 100000 |  | 100000 |  | 100000 | 600000
Actual
10 | Payment of Annual Dues of FOSIECON. | LASIEC/NP/NM/010/21 | 120000 | Plan |  | 20000 |  | 20000 |  | 20000 |  | 20000 |  | 20000 |  | 20000 | 120000
Actual
11 | Press Conference by the Chairman | LASIEC/NP/NM/011/21 | 1000000 | Plan |  |  | 250000 |  |  | 250000 |  |  | 250000 |  |  | 250000 | 1000000
Actual
12 | Payment by Commission on turnover , Value Added Tax, Police escort and other Charges Monthly | LASIEC/NP/NM/012/21 | 960000 | Plan | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 960000
Actual
13 | Welfare expenses | LASIEC/NP/NM/013/21 | 8645007 | Plan |  |  | 2161251.7 |  |  | 2161251.7 |  |  | 2161251.7 |  |  | 2161251.7 | 8645006.8
Actual
14 | Litigation and Attendance of Court Proceedings | LASIEC/NP/NM/014/21 | 1933435 | Plan | [5 empty] | 966717.5 | [5 empty] | 966717.5 | 1933435
Actual
15 | Elections Monitoring and observation | LASIEC/NP/NM/015/21 | 11102308 | Plan |  |  | 2775577 |  |  | 2775577 |  |  | 2775577 |  |  | 2775577 | 11102308
Actual
16 | Organisation of a Political Stakeholders meetings for Political Parties, NOA, INEC officials etc. | LASIEC/NP/NM/016/21 | 1115538.75 | Plan |  |  | 278884.68 |  |  | 278884.68 |  |  | 278884.68 |  |  | 278884.68 | 1115538.72
Actual
17 | Organisation of Security Stakeholders Meetings for Police, DSS,NCDC,Neighbourwood Watch, Man O War, Boys Scout, KAI, LASTMA etc. | LASIEC/NP/NM/017/21 | 1115538.75 | Plan |  |  | 278884.68 |  |  | 278884.68 |  |  | 278884.68 |  |  | 278884.68 | 1115538.72
Actual
18 | Organisation of Grassroot Stakeholders Meetings at Lagos East and Central Senatorial district. | LASIEC/NP/NM/018/21 | 1115538.75 | Plan |  |  | 278884.68 |  |  | 278884.68 |  |  | 278884.68 |  |  | 278884.68 | 1115538.72
Actual
19 | Organisation of Grassroot Stakeholders Meetings at Lagos West Senatorial District. | LASIEC/NP/NM/019/21 | 1115538.75 | Plan |  |  | 278884.68 |  |  | 278884.68 |  |  | 278884.68 |  |  | 278884.68 | 1115538.72
Actual
20 | Organisation of Civic Populace Stakeholders Meetings. | LASIEC/NP/NM/020/21 | 1115538.75 | Plan |  |  | 278884.68 |  |  | 278884.68 |  |  | 278884.68 |  |  | 278884.68 | 1115538.72
Actual
21 | Organisation of Media/NGOs/CBOS Stakeholders Meetings. | LASIEC/NP/NM/021/21 | 1115538.75 | Plan |  |  | 278884.68 |  |  | 278884.68 |  |  | 278884.68 |  |  | 278884.68 | 1115538.72
Actual
22 | Sensitisation of Poll Guides on Newly Delinated Wards. | LASIEC/NP/NM/022/21 | 1115538.75 | Plan |  |  | 278884.68 |  |  | 278884.68 |  |  | 278884.68 |  |  | 278884.68 | 1115538.72
Actual
23 | Organisation of Gender Sensitisation Activities. | LASIEC/NP/NM/023/21 | 1115538.75 | Plan |  |  | 278884.68 |  |  | 278884.68 |  |  | 278884.68 |  |  | 278884.68 | 1115538.72
Actual
24 | Transport allowance for market survey | LASIEC/NP/NM/024/21 | 120000 | Plan |  |  | 30000 |  |  | 30000 |  |  | 30000 |  |  | 30000 | 120000
Actual
26 | Monitoring and Evaluation of Projects and Elections | LASIEC/NP/NM/026/21 | 600000 | Plan |  |  | 150000 |  |  | 150000 |  |  | 150000 |  |  | 150000 | 600000
Actual
30 | Holding Minsterial Tenders Board Meetings | LASIEC/NP/NM/030/21 | 378294 | Plan |  |  | 94573.5 |  |  | 94573.5 |  |  | 94573.5 |  |  | 94573.5 | 378294
Actual
31 | Audit Exercise for Staff | LASIEC/NP/NM/031/21 | 300000 | Plan |  | 50000 |  | 50000 |  | 50000 |  | 50000 |  | 50000 |  | 50000 | 300000
Actual
32 | Personnel Cost (Non Oracle Staff) | LASIEC/NP/NM/032/21 | 20747060 | Plan | 6846530 | 6846530 | 7054000 | [9 empty] | 20747060
Actual
33 | Election Projects | LASIEC/NP/NM/033/21 | 1126219208 | Plan | 371652339 | 371652339 | 382914530 | [9 empty] | 1126219208
Actual
34 | Miscellaneous | LASIEC/NP/NM/034/21 | 7867129 | Plan | 655594.08 | 655594.08 | 655594.08 | 655594.08 | 655594.08 | 655594.08 | 655594.08 | 655594.08 | 655594.08 | 655594.08 | 655594.08 | 655594.08 | 7867128.96
Actual
| Total |  | 1245545003 | Plan | [12 empty] | 1245545002.52
Actual

## non-cons
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY: LAGOS STATE INDEPENDENT ELCTORAL COMMISSION
BUDGET YEAR: 2021
Contract Description | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
| Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
Maintenance of Office Equipment | LASIEC/S-NC-F/LCS/001/21 |  | Several | 8365887 | <10Million | LCS | Plan | Pre | Post | 2021-02-08 | 2021-02-16 | 2021-02-22 | 2021-03-05 | 2021-03-22 | 2021-04-06 | 2021-04-13 | Plan | 2021-04-20 | 2021-05-07 | 8365887 | 2021-05-11 | 2021-06-09 | 2021-06-28 | 2021-06-30
Actual
Maintenance of office Building | LASIEC/S-NC-F/LCS/002/21 |  | Several | 1942612 | <10Million | LCS | Plan | Pre | Post | 2021-02-08 | 2021-02-16 | 2021-02-22 | 2021-03-05 | 2021-03-22 | 2021-04-06 | 2021-04-13 | Plan | 2021-04-20 | 2021-05-07 | 1942612 | 2021-05-11 | 2021-06-09 | 2021-06-28 | 2021-06-30
Actual
Maintenance of Motor Vehicles | LASIEC/S-NC-F/LCS/003/21 |  | Several | 11724501.97 | <50Million | LCS | Plan | Pre | Prior | 2021-02-08 | 2021-02-16 | 2021-02-22 | 2021-03-05 | 2021-03-22 | 2021-04-06 | 2021-04-13 | Plan | 2021-04-20 | 2021-05-07 | 11724501.97 | 2021-05-11 | 2021-06-09 | 2021-06-28 | 2021-06-30
Actual
Maintenance of Two Heavy Duty Generating Sets (250KVA) | LASIEC/S-NC-F/LCS/004/21 |  | Several | 1223748 | <10Million | LCS | Plan | Pre | Post | 2021-02-08 | 2021-02-16 | 2021-02-22 | 2021-03-05 | 2021-03-22 | 2021-04-06 | 2021-04-13 | Plan | 2021-04-20 | 2021-05-07 | 1223748 | 2021-05-11 | 2021-06-09 | 2021-06-28 | 2021-06-30
[7 empty] | Actual | [9 empty] | Actual
Advertisement for invitation to Bid | LASIEC/S-NC-F/LCS/005/21 |  | Several | 1400000 | <10Million | LCS | Plan | Pre | Post | 2021-02-08 | 2021-02-16 | 2021-02-22 | 2021-03-05 | 2021-03-22 | 2021-04-06 | 2021-04-13 | Plan | 2021-04-20 | 2021-05-07 | 1400000 | 2021-05-11 | 2021-06-09 | 2021-06-28 | 2021-06-30
[7 empty] | Actual | [9 empty] | Actual
Engagement of Event Planner for Retreat for the Commission Members, Staff and Election Stakeholder | LASIEC/S-NC/LCS/001/21 |  | Several | 17012860 | <50Million | LCS | Plan | Pre | Prior | 2021-02-08 | 2021-02-16 | 2021-02-22 | 2021-03-05 | 2021-03-22 | 2021-04-06 | 2021-04-13 | Plan | 2021-04-20 | 2021-05-07 | 17012860 | 2021-05-11 | 2021-06-09 | 2021-06-28 | 2021-06-30
Actual
Total |  |  |  | 41669608.97 |  |  | Plan | [9 empty] | Actual |  |  | 41669608.97
[7 empty] | Actual | [9 empty] | Plan

## consultancy
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/ AGENCY: LAGOS STATE INDEPENDENT ELECTORAL COMMISSION
BUDGET YEAR: 2021
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[8 empty] | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
1 | Engagement of Private security Firm. | LASIEC/S-C/FBS/001/21 | CQS | Lump sum | 2023968 | Post | Plan | 2/02/2021 | 8/2/2021 | 16/02/2021 | 23/02/2021 | 8/03/2021 | 16/03/2021 | 25/03/2021 | 19/04/2021 | 28/04/2021 | 11/05/2021 | 17/05/2021 | 24/05/2021 | 02/06/2021 | 17/06/2021 | 2023968 | 21/07/2021 | 28/06/2021 | 12/07/2021 | 26/07/2021 | 04/08/2021
Actual
3 | Engagement of Financial Audit Firm. | LASIEC/S-C/LCS/001/21 | LCS | Lump sum | 1000000 | Post | Plan | 2/02/2021 | 8/2/2021 | 16/02/2021 | 23/02/2021 | 8/03/2021 | 16/03/2021 | 25/03/2021 | 19/04/2021 | 28/04/2021 | 11/05/2021 | 17/05/2021 | 24/05/2021 | 02/06/2021 | 17/06/2021 | 1000000 | 21/07/2021 | 28/06/2021 | 12/07/2021 | 26/07/2021 | 04/08/2021
Actual
| Total |  |  |  | 3023968 |  | Plan | [14 empty] | 3023968
Actual

## goods
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: LAGOS STATE INDEPENDENT ELECTORAL COMMISSION
BUDGET YEAR: 2021
S/N | CONTRACT IDENTIFICATION |  |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description |  | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[12 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Procurerment of Energy Saving Bulb |  | LASIEC/G-F/NS/001/21 |  | Several | 1250000 | <10Million | NS | Post | Post | Plan | 2021-01-04 | 2021-01-15 | 2021-01-22 | 2021-01-29 | 2021-02-12 | 2021-02-19 | 2021-02-26 | 2021-03-12 | 1250000 | 2021-03-16 | 2021-03-23 | 2021-03-30 | 2021-04-06 | 2021-04-15
Actual
2 | Procurerment of Toiletries and Liquid car wash |  | LASIEC/G-F/NS/002/21 |  | Several | 5755500 | <10Million | NS | Post | Post | Plan | 2021-01-04 | 2021-01-15 | 2021-01-22 | 2021-01-29 | 2021-02-12 | 2021-02-19 | 2021-02-26 | 2021-03-12 | 5755500 | 2021-03-16 | 2021-03-23 | 2021-03-30 | 2021-04-06 | 2021-04-15
Actual
3 | Procurement of tyres, Fire Extinguishers and Motor Vehicle accessories. |  | LASIEC/G/NS/003/21 |  | Several | 4739435 | <10Million | NS | Post | Post | Plan | 2021-01-04 | 2021-01-15 | 2021-01-22 | 2021-01-29 | 2021-02-12 | 2021-02-19 | 2021-02-26 | 2021-03-12 | 4739435 | 2021-03-16 | 2021-03-23 | 2021-03-30 | 2021-04-06 | 2021-04-15
Actual
4 | Procurement of 7 national Newspaper Daily |  | LASIEC/G-F/NS/004/21 |  | Several | 337500 | <10Million | NS | Post | Post | Plan | 2021-01-04 | 2021-01-15 | 2021-01-22 | 2021-01-29 | 2021-02-12 | 2021-02-19 | 2021-02-26 | 2021-03-12 | 337500 | 2021-03-16 | 2021-03-23 | 2021-03-30 | 2021-04-06 | 2021-04-15
Actual
5 | Procurement of Motor Vehicle Fuel (PMS) |  | LASIEC/G-F/NS/005/21 |  | Several | 25179314 | <50Million | NS | Post | Prior | Plan | 2021-01-04 | 2021-01-15 | 2021-01-22 | 2021-01-29 | 2021-02-12 | 2021-02-19 | 2021-02-26 | 2021-03-12 | 25179314 | 2021-03-16 | 2021-03-23 | 2021-03-30 | 2021-04-06 | 2021-04-15
Actual
6 | Procurement of Stationeries for General Use; Preparation of Bidding Documents, PMR, Annual Budget, Revenue and Expenditure returns and MTSS. |  | LASIEC/G-F/NS/006/21 |  | Several | 14311465 | <50Million | NS | Post | Prior | Plan | 2021-01-04 | 2021-01-15 | 2021-01-22 | 2021-01-29 | 2021-02-12 | 2021-02-19 | 2021-02-26 | 2021-03-12 | 14341465 | 2021-03-16 | 2021-03-23 | 2021-03-30 | 2021-04-06 | 2021-04-15
Actual
7 | Procurement of Diesel for 2 heavy duty generator sets |  | LASIEC/G-F/NS/007/21 |  | Several | 25288162 | <50Million | NS | Post | Prior | Plan | 2021-01-04 | 2021-01-15 | 2021-01-22 | 2021-01-29 | 2021-02-12 | 2021-02-19 | 2021-02-26 | 2021-03-12 | 25288162 | 2021-03-16 | 2021-03-23 | 2021-03-30 | 2021-04-06 | 2021-04-15
Actual
8 | Procurement of Uniforms and protectives for Drivers, Securities and Cleaners. |  | LASIEC/G/NS/008/2021 |  | Several | 402443 | <10Million | NS | Post | Post | Plan | 2021-02-01 | 2021-02-15 | 2021-02-22 | 29/02/2021 | 2021-03-12 | 2021-03-19 | 2021-03-26 | 2021-04-12 | 402443 | 2021-04-16 | 2021-04-23 | 2021-04-30 | 2021-05-14 | 2021-05-12
Actual
9 | Procurement of Souvenir (Branded Mugs, Key Holders, Ballpoint pen, Table Note pad and Flasks) and DVD Player |  | LASIEC/G/NS/009/2021 |  | Several | 240398 | <10Million | NS | Post | Post | Plan | 2021-01-04 | 2021-01-15 | 2021-01-22 | 2021-01-29 | 2021-02-12 | 2021-02-19 | 2021-02-26 | 2021-03-12 | 240398 | 2021-03-16 | 2021-03-23 | 2021-03-30 | 2021-04-06 | 2021-04-15
Actual
10 | Procurement of Operational Vehicle for Elections and Logistics |  | LASIEC/G/NS/010/21 |  | 2 | 45540491 | <50Million | NS | Post | Prior | Plan | [8 empty] | 45540491
Actual
11 | Procurement of Law Books of Lagos State and Federation on Election Process and Management |  | LASIEC/G/DC/001/21 |  | Several | 543554 | <10Million | DC | Post | Post |  | 2021-01-04 | 2021-01-15 | 2021-01-22 | 2021-01-29 | 2021-02-12 | 2021-02-19 | 2021-02-26 | 2021-03-12 | 543554 | 2021-03-16 | 2021-03-23 | 2021-03-30 | 2021-04-06 | 2021-04-15
12 | Procurement of Ballot Boxes |  | LASIEC/G/DC/002/21 |  | Several | 135000000 | <500Million | DC | Post | Prior | Plan | 2021-01-04 | 2021-01-15 | 2021-01-22 | 2021-01-29 | 2021-02-12 | 2021-02-19 | 2021-02-26 | 2021-03-12 | 135000000 | 2021-03-16 | 2021-03-23 | 2021-03-30 | 2021-04-06 | 2021-04-15
Actual
13 | Procurement of ICT Equipments |  | LASIEC/G/NCB/001/21 |  | Several | 57851000 | <100Million | NCB | Pre | Prior | Plan | 2021-01-04 | 2021-01-15 | 2021-01-22 | 2021-01-29 | 2021-02-12 | 2021-02-19 | 2021-02-26 | 2021-03-12 | 57851000 | 2021-03-16 | 2021-03-23 | 2021-03-30 | 2021-04-06 | 2021-04-15
Actual
| Total |  |  |  |  | 316439262 |  |  |  |  | Plan | [8 empty] | 316469262
Actual
|  | TEMPLATES | AMOUNT
|  | GOODS | 316439262
|  | WORKS | 170000000
|  | CONSULTRANCY | 3023968
|  | NON-CONSULTANCY | 41699609
|  | NON-PROCUREMENT | 1245545003
|  | TRG CONF WASH | 20918990
1797626832

## works
PROCUREMENT PLAN FOR WORKS:
MINISTRY: LAGOS STATE INDEPENDENT ELECTORAL COMMISSION
BUDGET YEAR: 2021
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Construction of Store/Warehouse at Lagos State East Senatorial District | LASIEC/W/NS/001/21 |  | 50000000 | <100Million | NS | Lump Sum | Prior | Plan | Post | 2021-06-29 | 2021-07-13 | 2021-07-20 | 2021-07-27 | 2021-08-10 | 2021-08-17 | 2021-08-24 | 2021-09-07 | 50000000 | 2021-09-09 | 2021-09-16 | 2021-09-30
Actual
2 | Construction of Store/Warehouse at Lagos State West Senatorial District | LASIEC/W/NS/002/21 |  | 50000000 | <100Million | NS | Lump Sum | Prior | Plan | Post | 2021-06-29 | 2021-07-13 | 2021-07-20 | 2021-07-27 | 2021-08-10 | 2021-08-17 | 2021-08-24 | 2021-09-07 | 50000000 | 2021-09-09 | 2021-09-16 | 2021-09-30
Actual
3 | Construction of Store/Warehouse at Lagos State Central Senatorial District | LASIEC/W/NS/003/21 |  | 50000000 | <100Million | NS | Lump Sum | Prior | Plan | Post | 2021-06-29 | 2021-07-13 | 2021-07-20 | 2021-07-27 | 2021-08-10 | 2021-08-17 | 2021-08-24 | 2021-09-07 | 50000000 | 2021-09-09 | 2021-09-16 | 2021-09-30
Actual
4 | Renovation of offices at the Headquater/Zonal offices. | LASIEC/W/NS/004/21 |  | 20000000 | <50Million | NS | Lump Sum | Prior | Plan | Post | 2021-02-01 | 2021-02-15 | 2021-02-22 | 29/02/2021 | 2021-03-12 | 2021-03-19 | 2021-03-26 | 2021-04-12 | 20000000 | 2021-04-16 | 2021-04-23 | 2021-04-30 | 2021-05-28 | 2021-06-04
Actual
|  |  |  | 170000000 |  |  |  |  | Plan | [9 empty] | 170000000
Actual

## trg conf wash
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: LAGOS STATE INDEPENDENT ELECTORAL COMMISSION
BUDGET YEAR: 2021
S/N | Description of Training/Workshop/ Conference | Package Number | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | International Bar Association | LASIEC/S-WTC/SS/001/21 |  | 1 | 7 days | Plan | Oversea | 940000 | 2000000 | 3707830 | 6647830
Actual
2 | Nigeria Statistical Association (NSA) | LASIEC/S-WTC/SS/001/21 |  | 1 | 5 days | Actual | Abuja | 60000 | 62000 | 248000 | 370000
Actual
3 | Computer Professional Registration of Nigeria (CPN) | LASIEC/S-WTC/SS/002/21 |  | 1 | 5 days | Plan | Abuja | 120000 | 124000 | 373000 | 617000
Actual
4 | Nigeria Bar Association (NBA) | LASIEC/S-WTC/SS/003/20 |  | 3 | 5 days | Plan | Abuja | 200000 | 124000 | 496000 | 820000
Actual
5 | Chatered Institute of Personnel Management (CIPM) | LASIEC/S-WTC/SS/004/21 |  | 8 | 5 days | Plan | Abuja | 480000 | 496000 | 1984000 | 2960000
Actual
6 | Master Class on Navigating Public Sector Challenges in a Complex World for Permanent Secretary | LASIEC/S-WTC/SS/004/21 |  | 1 | 7 days | Plan | Oversea | 700000 | 2000000 | 3176160 | 5876160
Actual
7 | Institute of Chatered Accountant of Nigeria (ICAN) | LASIEC/S-WTC/SS/008/20 |  | 2 | 5 days | Plan | Abuja | 200000 | 124000 | 435500 | 759500
Actual
8 | Nigeria Institute of Public Relation (NIPR) | LASIEC/S-WTC/SS/009/21 |  | 2 | 5days | Plan | Abuja | 120000 | 124000 | 373500 | 617500
Actual
9 | Chatered Institute of Purchasing and Supply Management of Nigeria (CIPSMN) | LASIEC/S-WTC/SS/010/21 |  | 3 | 5 days | Plan | Abuja | 180000 | 186000 | 561000 | 927000
Actual
10 | Management Trainig & Workshop by Lagos State Public Service Staff Development Center for Senior Officer | LASIEC/S-WTC/SS/015/21 |  | 45 | 3 Days | Plan | PSSDC | 765000 | 90000 | 135000 | 990000
Actual
11 | Management Trainig & Workshop by Lagos State Public Service Staff Development Center for Junior Officer | LASIEC/S-WTC/SS/017/21 |  | 20 | 3 Days | Plan | Lagos | 300000 | 14000 | 20000 | 334000
Actual
| Total |  |  |  |  | Plan |  | 4065000 | 5344000 | 11509990 | 20918990
Actual