## goods
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: LAGOS STATE PLANNING ENVIRONMENT MONITORING AUTHORITY
BUDGET YEAR: 2021
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Provision for Planning Research and Statisitcs | LASPEMA/NS/001/21 |  |  | 250000 | <50 | NS | POST | PRIOR | Plan | 2021-02-02 | 2021-02-23 | 2021-03-02 | 2021-03-09 | 2021-03-30 | 2021-04-06 | 2021-05-04 | 2021-05-06 |  | 2021-05-13 | 2021-05-20 | 2021-06-03
Actual
2 | Procurement for Operational Vehicles and other Accessiries | LASPEMA/NS/002/21 |  |  | 18500000 | <50 | NS | PRE | POST | Plan | 2021-01-01 | 2021-01-22 | 2021-01-29 | 2021-02-19 | 2021-02-26 | 2021-03-05 | 2021-04-05 | 2021-04-07 |  | 2021-04-14 | 2021-04-21 | 2021-05-12
Actual
3 | Procurement of Operational Equipment for Enforcement | LASPEMA/NS/003/21 |  |  | 10,000.000.00 | <50 | NS | PRE | POST | Plan | 2021-02-02 | 2021-02-23 | 2021-03-02 | 2021-03-09 | 2021-03-30 | 2021-04-06 | 2021-05-04 | 2021-05-06 |  | 2021-05-13 | 2021-05-20 | 2021-06-03
Actual
4 | Procurement of Office Furniture and Equipment | LASPEMA/NS/004/21 |  |  | 5198000 | <50 | NS | POST | PRIOR | Plan | 2021-01-01 | 2021-01-22 | 2021-01-29 | 2021-02-19 | 2021-02-26 | 2021-03-05 | 2021-04-05 | 2021-04-07 |  | 2021-04-14 | 2021-04-21 | 2021-05-12
Actual
5 | Procurement of Computer Consumables and Accessiries | LASPEMA/NS/005/21 |  |  | 150000 | <50 | NS | POST | PRIOR | Plan | 2021-02-02 | 2021-02-23 | 2021-03-02 | 2021-03-09 | 2021-03-30 | 2021-04-06 | 2021-05-04 | 2021-05-06 |  | 2021-05-13 | 2021-05-20 | 2021-06-03
Actual
Plan
Actual

## consultancy
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/AGENCY: LAGOS STATE PLANNING ENVIRONMENT MONITORING AUTHORITY
BUDGET YEAR: 2021
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[5 empty] | 0 |  | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
1 | Engagement of external Auditor | LASPEMA/S-C/CQ/001/21 | CQ |  | 2500000 | POST | Plan | 2021-03-01 | 2021-03-22 | 2021-03-29 | 2021-04-12 | 2021-04-19 | 2021-04-26 | 2021-05-17 | 2021-05-24 | 2021-05-31 | 2021-06-07 | 2021-06-14 | 2021-06-21 | 2021-07-19 | 2021-07-21 |  | 2021-07-28 | 2021-08-11 | 2021-09-15 | 2021-09-22 | 2021-09-29
Actual
2 | Provision for Management Retreat | LASPEMA/S-C/CQ/002/21 | CQ |  | 1000000 | POST | Plan | 2021-03-01 | 2021-03-22 | 2021-03-29 | 2021-04-12 | 2021-04-19 | 2021-04-26 | 2021-05-17 | 2021-05-24 | 2021-05-31 | 2021-06-07 | 2021-06-14 | 2021-06-21 | 2021-07-19 | 2021-07-21 |  | 2021-07-28 | 2021-08-11 | 2021-09-15 | 2021-09-22 | 2021-09-29
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual

## non-cons
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY:
BUDGET YEAR: 2021
Contract Description | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
| Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
Provision for Stakeholders meeting with informal (Under Miscellaneous) | LASPEMA/S-NC/CQ/001/21 |  |  | 1920000 | <50 | NS | Plan | PRE | POST | 2021-02-01 | 2021-02-01 | 2021-02-01 | 2021-02-01 | 2021-02-01 | 2021-02-01 | 2021-02-01 | Plan | 2021-02-01 | 2021-02-01 | 2021-02-01 | 2021-02-01 | 2021-02-01 | 2021-02-01 | 2021-02-01
[7 empty] | Actual | [9 empty] | Actual
Procurement of Uniform and protective outfits | LASPEMA/S-NC/NS/002/21 |  |  | 150000 | <50 | NS | Plan | PRE | POST | 2021-02-01 | 2021-02-01 | 2021-02-01 | 2021-02-01 | 2021-02-01 | 2021-02-01 | 2021-02-01 | Plan | 2021-02-01 | 2021-02-01 | 2021-02-01 | 2021-02-01 | 2021-02-01 | 2021-02-01 | 2021-02-01
[7 empty] | Actual | [9 empty] | Actual
Publicity Advocacy and Enlightement | LASPEMA/S-NC/NS/003/21 |  |  | 250000 | <50 | NS | Plan | PRE | POST | 2021-02-01 | 2021-02-01 | 2021-02-01 | 2021-02-01 | 2021-02-01 | 2021-02-01 | 2021-02-01 | Plan | 2021-02-01 | 2021-02-01 | 2021-02-01 | 2021-02-01 | 2021-02-01 | 2021-02-01 | 2021-02-01
[7 empty] | Actual | [9 empty] | Actual
Provision for Printing of materials and enforcement notices | LASPEMA/S-NC/NS/004/21 |  |  | 200000 | <50 | NS | Plan | PRE | POST | [7 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
Provision for World Habitat Day | LASPEMA/S-NC/NS/005/21 |  |  | 1400000 | <50 | NS | Plan | PRE | POST | [7 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual

## Non-Proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: LAGOS STATE PLANNING ENVIRONMENT MONITORING AUTHORITY
BUDGET YEAR: 2021
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TOTAL
1 | Travel and Transport - Local | LASPEMA/NP/NM/001/21 | 720,000.00 | Plan
Actual
2 | Maintenance of Office Building | LASPEMA/NP/NM/002/21 | 600,000.00 | Plan
Actual
3 | Motor Vehicle Repairs & Maintenance | LASPEMA/NP/NM/003/21 | 2160000 | Plan
Actual
4 | Motor Vehicle Fueling | LASPEMA/NP/NM/004/21 | 3,600,000.00 | Plan
Actual
5 | Provision for General Utility Services | LASPEMA/NP/NM/005/21 | 1,800,000.00 | Plan
Actual
6 | Stationery | LASPEMA/NP/NM/006/21 | 900,000.00 | Plan
Actual
7 | Servicing of Management Meeting | LASPEMA/NP/NM/007/21 | 700,000.00 | Plan
Actual
8 | Provision for Staff Welfare, Public Service Week/HOS cup | LASPEMA/NP/NM/008/21 | 1,040,000.00 | Plan
Actual
9 | Provision for Local Training and Worshop | LASPEMA/NP/NM/009/21 | 300,000.00 | Plan
Actual

## trg conf wsh
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: LAGOS STATE PLANNING ENVIRONMENT MONITORING AUTHORITY
BUDGET YEAR: 2021
S/N | Description of Training/Workshop/ Conference | Package Number | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | ANNUAL NSE CONFERENCE | LASPEMA/S-WTC/SS/001/21 |  | 1 |  | Plan |  |  |  |  | 270000
Actual
2 | ANNUAL ICAN CONFERENCE | LASPEMA/S-WTC/SS/002/21 |  | 1 |  | Plan |  |  |  |  | 270000
Actual
3 | ANNUAL ANAN CONFERENCE | LASPEMA/S-WTC/SS/003/21 |  | 1 |  | Plan |  |  |  |  | 270000
Actual
4 | ANNUAL COREN CONFERENCE | LASPEMA/S-WTC/SS/004/21 |  | 2 |  | Plan |  |  |  |  | 500000
Actual
5 | NSA/STATISTICAL WORSHOP/RESEARCH METHODOLOGY | LASPEMA/S-WTC/SS/005/21 |  | 1 |  | Plan |  |  |  |  | 250000
Actual
6 | CIPSMN CONFERENCE | LASPEMA/S-WTC/SS/006/21 |  | 1 |  | Plan |  |  |  |  | 240000
Actual
7 | [5 empty] | Plan
Actual
8 | [5 empty] | Plan
Actual
9 | [5 empty] | Plan
Actual
10 | [5 empty] | Plan
Actual
11 | [5 empty] | Plan
Actual
12 | [5 empty] | Plan
Actual