## Non-Proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: LAGOS STATE REAL ESTATE REGULATORY AUTHORITY (LASRERA)
BUDGET YEAR: 2021
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TOTAL
1 | Payment of Transportation ( Road/Air) allowances for staff | LASRERA/NP/ NM/001/2021 | 6,183,000.00 | Plan | 515250 | 515250 | 515250 | 515250 | 515250 | 515250 | 515250 | 515250 | 515250 | 515250 | 515250 | 515250 | 6183000
|  |  |  | Actual | [12 empty] | 0
2 | Payment of telephone, water and cable bills | LASRERA/NP/NM/002/2021 | 10,705,500.00 | Plan | 892125 | 892125 | 892125 | 892125 | 892125 | 892125 | 892125 | 892125 | 892125 | 892125 | 892125 | 892125 | 10705500
|  |  |  | Actual | [12 empty] | 0
3 | Allowances for different categories of Ad-hoc staff | LASRERA/NP/NM/003/2021 | 41400000 | Plan | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 41400000
|  |  |  | Actual | [12 empty] | 0
4 | Payment of fund for the enforcement/taskforce team for compliance and prosecution | LASRERA/NP/NM/004/2021 | 3,140,000.00 | Plan | 261666.6667 | 261666.6667 | 261666.6667 | 261666.6667 | 261666.6667 | 261666.6667 | 261666.6667 | 261666.6667 | 261666.6667 | 261666.6667 | 261666.6667 | 261666.6667 | 3140000
|  |  |  | Actual | [12 empty] | 0
5 | Allowances for field engineers | LASRERA/NP/NM/005/2021 | 5,000,000.00 | Plan | 416666.6667 | 416666.6667 | 416666.6667 | 416666.6667 | 416666.6667 | 416666.6667 | 416666.6667 | 416666.6667 | 416666.6667 | 416666.6667 | 416666.6667 | 416666.6667 | 5000000
Actual
6 | Staff welfare /Ceremonies | LASRERA/NP/NM/006/2021 | 3,000,000.00 | Plan | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 3000000
Actual
7 |  |  |  | Plan
Actual
8 |  |  |  | Plan
Actual
Total |  |  | 69428500

## trg conf wsh
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: LAGOS STATE REAL ESTATE REGULATORY AUTHORITY
BUDGET YEAR: 2021
S/N | Description of Training/Workshop/ Conference | Package Number | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | Conference and Seminar for different categories of Professional Staff | LASRERA/S-WTC/SS/001/2021 | Capacity development for different categories of professional staff | 25 | 2 | Plan | Lagos/Abuja |  |  |  | 5000000
Actual
2 | Workshop and Trainning for Staff @ PSSDC | LASRERA/S-WTC/SS/002/2021 | Understanding Real Esate | 24 | 2 | Plan | Lagos |  |  |  | 1000000
Actual
3 | Bespoke Trainning for Staff | LASRERA/S-WTC/SS/003/2021 | Administrative Ethics | 24 | 2 | Plan | Lagos |  |  |  | 2000000
Actual
4 | Mandatory Trainning for Professional bodies | LASRERA/S-WTC/SS/004/2021 | Capacity development for different categories of professional staff | 15 | 2 | Plan | Lagos/Abuja |  |  |  | 2500000
Actual
4 | Workshop and Trainning within Lagos | LASRERA/S-WTC/SS/005/2021 | Capacity Building for staff | 24 | 2 | Plan | Lagos |  |  |  | 1500000
Actual
5 | COWLSO | LASRERA/S-WTC/SS/006/2021 | Women empowerment initiatives | 10 | 2 | Plan | Lagos |  |  |  | 2000000
Actual
6 | Capacity Building for Staff | LASRERA/S-WTC/SS/007/2021 | Capacity Building for staff | 24 | 2 | Plan |  |  |  |  | 4000000
[6 empty] | Actual | Lagos
| TOTAL | [9 empty] | 18000000

## non-cons
PROCUREMENT PLAN FOR NON-CONSULTING SERVICES.
MINISTRY/AGENCY: LAGOS STATE REAL ESTATE REGULATORY AUTHORITY
BUDGET YEAR: 2021
S/N | Contract Description | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
|  | Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
1 | Maintenance/Servicing of LASRERA fleet of vehicles | LASRERA/S-NCS/NS/01/2021 |  |  | 2896500 | <10m | NS | Plan | Post | Post | 2021-02-01 | 2021-02-08 | 2021-02-15 | 2021-02-22 | 2021-03-02 |  | 2021-03-09 | Plan |  |  |  | 2021-03-15 | 2021-03-29 | 2021-04-05 | 2021-04-12
[8 empty] | Actual | [9 empty] | Actual
2 | Maintenance/Servicing of office equipment i.e photocopiers, airconditioner etc | LASRERA/S-NCS/NS/02/2021 |  |  | 5007500 | <10m | NS | Plan | Post | Post | 2021-02-01 | 2021-02-08 | 2021-02-15 | 2021-02-22 | 2021-03-02 |  | 2021-03-09 | Plan |  |  |  | 2021-03-15 | 2021-03-29 | 2021-04-05 | 2021-04-12
[8 empty] | Actual | [9 empty] | Actual
3 | [7 empty] | Plan | Post | Post | [7 empty] | Plan
[8 empty] | Actual | [9 empty] | Actual
4 |  |  |  |  | 7904000

## consultancy
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/ AGENCY:LAGOS STATE REAL ESTATE REGULATORY AUTHORITY
BUDGET YEAR: 2021
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[5 empty] | 0 |  | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
1 | Engagement of Consultant for the identification of abandoned building in 20 LGs/LCDAs | LASRERA/S-C/CQ/001/21 | CQ | Lump Sum | 10000000 | Prior | Plan | 2021-02-01 | 2021-02-08 | 2021-02-15 | 2021-02-22 | 2021-03-01 | 2021-03-08 | 2021-03-15 | 2021-03-29 | 2021-04-05 | 2021-04-12 | 2021-04-19 | 2021-04-26 | 2021-05-03 |  |  | 2021-05-10 | 17//05/2021 | 2021-05-24 | 2021-06-07 | 14//06/2021
Actual
2 | Engagement of Consultant to undertake publicity on TV , Radio Stations and Print Media for Advocacy Campaign | LASRERA/S-C/CQ/002/21 | CQ | Lump Sum | 5746000 | Post | Plan | 2021-02-01 | 2021-02-08 | 2021-02-15 | 2021-02-22 | 2021-03-01 | 2021-03-08 | 2021-03-15 | 2021-03-29 | 2021-04-05 | 2021-04-12 | 2021-04-19 | 2021-04-26 | 2021-05-03 |  |  | 2021-05-10 | 17//05/2021 | 2021-05-24 | 2021-06-07 | 14//06/2021
Actual
3 | Engagement of Consultant to organise Sensitisation/workshop for the stakeholders in the Real Estate in the State | LASRERA/S-C/CQ/003/21 | CQ | Lump Sum | 5000000 | Post | Plan | 2021-02-01 | 2021-02-08 | 2021-02-15 | 2021-02-22 | 2021-03-01 | 2021-03-08 | 2021-03-15 | 2021-03-29 | 2021-04-05 | 2021-04-12 | 2021-04-19 | 2021-04-26 | 2021-05-03 |  |  | 2021-05-10 | 17//05/2021 | 2021-05-24 | 2021-06-07 | 14//06/2021
Actual
4 | Engagement of Consultant to organise Conference and Exhibition for the 2nd Edition Market Place for the players in Real estate sector | LASRERA/S-C/CQ/004/21 | CQ | Lump Sum | 80000000 | Prior | Plan | 2021-03-01 | 2021-03-08 | 2021-03-15 | 2021-03-22 | 2021-03-29 | 2021-04-05 | 2021-03-12 | 2021-04-19 | 2021-04-26 | 2021-05-03 | 2021-05-10 | 2021-05-17 | 2021-05-24 |  |  | 2021-06-07 | 2021-06-14 | 2021-06-21 | 2021-06-28 | 2021-07-05
Actual
5 | Engagement of Legal Consultant/technical committee/ committee of enquiries on Real Estate matters | LASRERA/S-C/CQ/005/21 | CQ | Lump Sum | 55000000 | Prior | Plan | 2021-03-01 | 2021-03-08 | 2021-03-15 | 2021-03-22 | 2021-03-29 | 2021-04-05 | 2021-03-12 | 2021-04-19 | 2021-04-26 | 2021-05-03 | 2021-05-10 | 2021-05-17 | 2021-05-24 |  |  | 2021-06-07 | 2021-06-14 | 2021-06-21 | 2021-06-28 | 2021-07-05
Actual
6 | Engagement of consultant to organise a Retreat for Staff of LASRERA | LASRERA/S-C/CQ/006/21 | CQ | Lump Sum | 5000000 | Post | Plan | 2021-03-01 | 2021-03-08 | 2021-03-15 | 2021-03-22 | 2021-03-29 | 2021-04-05 | 2021-03-12 | 2021-04-19 | 2021-04-26 | 2021-05-03 | 2021-05-10 | 2021-05-17 | 2021-05-24 |  |  | 2021-06-07 | 2021-06-14 | 2021-06-21 | 2021-06-28 | 2021-07-05
Actual
Total |  |  |  |  | 160746000

## goods
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: LAGOS STATE REAL ESTATE REGULATORY AUTHORITY
BUDGET YEAR: 2021
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot No | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Procurement of damaged/repair office items such as doors, electrical, plumbing etc | LASRERA/G/NS/001/21 |  |  | 3116500 | <10m | NS | Post | Post | Plan | 2021-02-01 |  | 2021-02-08 | 2021-02-15 | 2021-02-22 |  | 2021-03-01 |  |  | 2021-03-08 | 2021-03-15 | 2021-03-29 | 2021-03-30 | 2021-03-30
Actual
2 | Procurement of fuelling for the Fleet of Vehicles | LASRERA/G-F/NS/001/21 |  |  | 8640000 | <10m | NS | Post | Post | Plan | 2021-02-01 |  | 2021-02-08 | 2021-02-15 | 2021-02-22 |  | 2021-03-01 |  |  | 2021-03-08 | 2021-03-15 | 2021-03-29 | 2021-03-30 | 2021-03-30
Actual
3 | Procurement of stationery | LASRERA/G- F/NS/002/2021 |  |  | 12,600,000,00 | <50m | NS | Post | Post | Plan | 2021-04-05 | 2021-04-12 | 2021-04-19 | 2021-04-26 | 2021-05-10 | 2021-05-17 | 2021-05-24 |  |  | 2021-05-31 | 2021-06-07 | 2021-06-14 | 2021-06-21 | 2021-06-21
Actual
4 | Procurement of computer Accessories/equipmemt | LASRERA/G- F/NS/003/2021 |  |  | 10565000 | <50m | NS | Post | Post | Plan | 2021-04-05 | 2021-04-12 | 2021-04-19 | 2021-04-26 | 2021-05-10 | 2021-05-17 | 2021-05-24 |  |  | 2021-05-31 | 2021-06-07 | 2021-06-14 | 2021-06-21 | 2021-06-21
Actual
5 | Printing/Production of Certificates/Forms and Seals | LASRERA/G/NS/002/2021 |  |  | 6,000,000,00 | <10m | NS | Post | Post | Plan | 2021-04-05 | 2021-04-12 | 2021-04-19 | 2021-04-26 | 2021-05-10 | 2021-05-17 | 2021-05-24 |  |  | 2021-05-31 | 2021-06-07 | 2021-06-14 | 2021-06-21 | 2021-06-21
Actual
6 | Procurement of office consummables to all Depts/Units | LASRERA/G/NS/003/2021 |  |  | 9000000 | <10m | NS | Post | Post | Plan | 2021-05-03 |  | 2021-05-10 | 2021-05-17 | 2021-05-24 |  | 2021-06-07 |  |  | 2021-06-14 | 2021-06-21 | 2021-06-28 | 2021-07-05 | 2021-07-05
Actual
7 | Procurement of 30KVA/27KW Soundproof Generator | LASRERA/G/NS/004/2021 |  |  | 5500000 | <10m | NS | Post | Post | Plan | 2021-05-03 |  | 2021-05-10 | 2021-05-17 | 2021-05-24 |  | 2021-06-07 |  |  | 2021-06-14 | 2021-06-21 | 2021-06-28 | 2021-07-05 | 2021-07-05
Actual
8 | Procurement of Vehicle | LASRERA/G/NS/005/2021 |  |  | 55000000 | <100m | NS | Post | Post | Plan | 2021-06-07 | 2021-06-14 | 2021-06-21 | 2021-06-28 | 2021-07-05 | 2021-07-12 | 2021-07-19 |  |  | 2021-07-26 | 2021-08-02 | 2021-08-09 | 2021-08-16 | 2021-08-16
Actual
9 | [9 empty] | Plan
Actual
10 | [9 empty] | Plan
Actual
11 | [9 empty] | Plan
Actual
12 | [9 empty] | Plan
Actual
13 | [9 empty] | Plan
Actual
Total |  |  |  |  | 91821500

## works
PROCUREMENT PLAN FOR WORKS
MINISTRY: LAGOS STATE REAL ESTATE REGULATORY AUTHORITY
BUDGET YEAR: 2021
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package No | Lot No | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Construction of Prefabricated portacabin office structure across the selected LGAs/LCDAs | LASRERA/W/NCB/001/2020 |  | 108607890 | <500m | NCB | BOQ | Post | Plan | Prior | 2021-04-05 | 2021-04-12 | 2021-04-19 | 2021-04-26 | 2021-05-10 | 2021-05-17 | 2021-05-24 |  |  | 2021-05-31 | 2021-06-07 | 2021-06-14 | 2021-06-21 | 2021-06-21
Actual
2 | Re-Engineering of Existing Housing Estates | LASRERA/W/ICB/001/2020 |  | 950000000 | <1B | ICB | BOQ | Post | Plan | Prior | 2021-04-05 | 2021-04-12 | 2021-04-19 | 2021-04-26 | 2021-05-10 | 2021-05-17 | 2021-05-24 |  |  | 2021-05-31 | 2021-06-07 | 2021-06-14 | 2021-06-21 | 2021-06-21
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual