## Non-Proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: LAGOS STATE UNIVERSITY TEACHING HOSPITAL, (LASUTH), IKEJA.
BUDGET YEAR: 2021
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TOTAL
1 | Professional fee (Honourarium). | LASUTH/NPI/NS/01/21 | 842,660,497.44 | Plan | January | February | March | April | May | June | July | August | September | October | November | December | 842660497.44
Actual
2 | Payment of Rented Accomodation. | LASUTH/NPI/NS/02/21 | 17,500,000 | Plan | January | [11 empty] | 17500000
Actual
3 |  |  |  | Plan
Actual
4 |  |  |  | Plan
Actual
5 |  |  |  | Plan
Actual
6 |  |  |  | Plan
Actual
7 |  |  |  | Plan
Actual
8 |  |  |  | Plan
Actual
9 |  |  |  | Plan
Actual
10 |  |  |  | Plan
Actual

## trg conf wsh
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY:
BUDGET YEAR: |  |  |  | 2021
S/N | Description of Training/Workshop/ Conference | Package Number | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | Health Workers Workshop &Training. | LASUTH/TCW/NS/01/21 | Departmental Trainig | 80 |  | Plan | Lasuth |  |  |  | 2000000
Actual
2 | [5 empty] | Plan
Actual
3 | [5 empty] | Plan
Actual
4 | [5 empty] | Plan
Actual
5 | [5 empty] | Plan
Actual
6 | [5 empty] | Plan
Actual
7 | [5 empty] | Plan
Actual
8 | [5 empty] | Plan
Actual
9 | [5 empty] | Plan
Actual
10 | [5 empty] | Plan
Actual
11 | [5 empty] | Plan
Actual
12 | TOTAL |  |  |  |  | Plan
Actual

## non-cons
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY:
BUDGET YEAR:
Contract Description | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
| Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [8 empty] | 2019-03-26 | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [8 empty] | 2019-03-26 | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [8 empty] | 2019-03-26 | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [8 empty] | 2019-03-26 | Plan
[7 empty] | Actual | [9 empty] | Actual

## consultancy
PROCUREMENT PLAN FOR CONSULTING SERVICES
LASUTH , IKEJA.
BUDJECT YEAR ; 2021
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[5 empty] | 0 |  | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
1 | Attendants Workshop & Training. | LASUTH/CS/NS/01/21 | QBS | LP | 6400000 | Post | Plan | 8th,feb, 21 | 15th,feb,21 | 22nd,feb,21 | 8th,March,21 | 15th,March,21 | 22nd,March,21 | 12th,April,21 | 19th,April,21 | 26th,April,21 | 3rd,May,21 | 10th,May,21 | 17th,May,21 | 24th,May,21 | 26th,May,21 |  | 2nd,June,21 | 16th,June,21 | 30th,june,21 | 7th,July,21 | 14th,July,21
Actual
2 | Training for Resident Doctors.(Yearly Training). | LASUTH/CS/NS/02/21 | QBS | LP | 10575000 | Post | Plan | 15th,feb,21 | 22nd,feb,21 | 1st,March,21 | 15th,March,21 | 22nd,March,21 | 29th,March,21 | 19th,April,21 | 26th,April,21 | 3rdMay,21 | 10th,May,21 | 17th,May,21 | 24th,May,21 | 31st,May,21 | 2nd,June,21 |  | 9th,June,21 | 23rd,June,21 | 7th,June,21 | 14th,June,21 | 21st,June,21
Actual
3 | Workshop for (10) Hospital consultants | LASUTH/CS/NS/03/21 | QBS | LP | 2000000 | Post | Plan | 22nd,feb,21 | 1st,March,21 | 8th,March,21 | 22nd,March,21 | 29th,March,21 | 5th,April,21 | 26th,April,21 | 3rd,May,21 | 10th,May,21 | 17th,May,21 | 24th,May,21 | 31st,May,21 | 7th,June,21 | 9th,June,21 |  | 16th,June,21 | 30th,June,21 | 14th,July,21 | 21st,July,21 | 28th,July,21
Actual
4 | Attendance of Professional Conferences (CIPM, NIM, NITHAD. Etc, for Mdical/ Non Medical. | LASUTH/CS/NS/04/21 | QBS | LP | 8000000 | Post | Plan | 8th,feb, 21 | 15th,feb,21 | 22nd,feb,21 | 8th,March,21 | 15th,March,21 | 22nd,March,21 | 12th,April,21 | 19th,April,21 | 26th,April,21 | 3rd,May,21 | 10th,May,21 | 17th,May,21 | 24th,May,21 | 26th,May,21 |  | 2nd,June,21 | 16th,June,21 | 30th,June,21 | 7th,July,21 | 14th,July,21
Actual
5 | Training and Workshop for other Non Medical officers;Admin, Account, Procurement, Auditor, Budget, PRO, Engineer. | LASUTH/CS/NS/05/21 | QBS | LP | 10400000 | Post | Plan | 15th,feb,21 | 22nd,feb,21 | 1st,March,21 | 15th,March,21 | 22nd,March,21 | 29th,March,21 | 19th,April,21 | 26th,April,21 | 3rdMay,21 | 10th,May,21 | 17th,May,21 | 24th,May,21 | 31st,May,21 | 2nd,June,21 |  | 9th,June,21 | 23rd,June,21 | 7th,June,21 | 14th,June,21 | 21st,June,21
Actual
6 | Internal & External branding of LASUTH. | LASUTH/CS/NS/06/21 | QBS | LP | 25000000 | Post | Plan | 22nd,feb,21 | 1st,March,21 | 8th,March,21 | 22nd,March,21 | 29th,March,21 | 5th,April,21 | 26th,April,21 | 3rd,May,21 | 10th,May,21 | 17th,May,21 | 24th,May,21 | 31st,May,21 | 7th,June,21 | 9th,June,21 |  | 16th,June,21 | 30th,June,21 | 14th,July,21 | 21st,July,21 | 28th,July,21
Actual

## goods
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: LASUTH.
BUDGET YEAR: 2021
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Procurement of Radiation Monitoting, C-ARM, Dlylesis & Diaylazer Machines. | LASUTH/G/NS/01/21 |  | 5 | 308640558.26 | <1B | NCB | Post | Post | Plan | 8th,March,21 | 15th, March,21 | 22nd,March,21 | 5th,April,21 | 12th,Apr,21 | 19th,Apr,21 | 3rd,May,21 | 5th,May,21 |  | 12th,May,21 | 19th,May,21 | 2nd,June,21
Actual
2 | Procurement of Anaesthesia Consumables. | LASUTH/G-F/NS/02/21 |  | 10 | 49500000 | <50M | NS | Post | Post | Plan | 15th,March,21 | 22nd,March,21 | 29th,March,21 | 12th,April,21 | `19th,April,21 | 26th,April,21 | 10th,May,21 | 12th,May,21 |  | 19th,May,21 | 26th,May,21 | 9th,June,21
Actual
3 | Procurement of Daniel Trolley, Hospital bed & Theatre table. | LASUTH/G/NS/03/21 |  | 14 | 28500000 | <50M | NS | Post | Post | Plan | 22nd,March,21 | 29th,March,21 | 5th,April,21 | 19th,April,21 | 26th,April,21 | 3rd,May,21 | 17th,May,21 | 19th,May,21 |  | 26th,May,21 | 2nd,June,21 | 16th,June,21
Actual
4 | Procurement of Auto-clave Machine | LASUTH/G/NS/04/21 |  | 1 | 5175000 | <10M | NS | Post | Post | Plan | 29,March,21 | 5th,April,21 | 12th,April,21 | 26th,April,21 | 3rd,May,21 | 10th,May,21 | 24th,May,21 | 26th,May,21 |  | 2nd,June,21 | 9th,June,21 | 23rd,June,21
Actual
5 | Procurement of Monitors,Glucometer, Defribilator, Arterial blood gas,Paediatric sphg & bed side locker | LASUTH/G/NS/05/21 |  | 3530 | 48776000 | <50M | NS | Post | Post | Plan | 8th,March,21 | 15th,March,21 | 22nd,March,21 | 5th,April,21 | 12th,April,21 | 19th,April,21 | 3rd,May,21 | 5th,May,21 |  | 12th,May,21 | 19th,May,21 | 2nd,June,21
Actual
6 | Procurement of Laundry Trolley(clean linen),Aluminiun wet laundry trolley & Advance pid wet laundry plastic. | LASUTH/G/NS/06/21 |  | 4 | 2794000 | <10M | NS | Post | Post | Plan | 15th,March,21 | 22nd,March,21 | 29th,March,21 | 12th,April,21 | 19th,April,21 | 26th,April,21 | 10th,May,21 | 12th,May,21 |  | 19th,May,21 | 26th,May,21 | 10th,June,21
Actual
7 | Procurement of Operating Microscope,Pachymeter Machine, None -contact Tonometer &Phaco-emulsification Machine. | LASUTH/G/NS/07/21 |  | 4 | 33200000 | <50M | NS | Post | Post | Plan | 22nd,march,21 | 29th,March,21 | 5th,April,21 | 19th,April,21 | 26th,April,21 | 3rd,May,21 | 17th,May,21 | 19th,May,21 |  | 26th,May,21 | 2nd,June,21 | 16th,June,21
Actual
8 | Procurement of Master Name Index equipment.(Multi drawers Master name Index). | LASUTH/G/NS/08/21 |  | 1 | 3000000 | <10M | NS | Post | Post | Plan | 29th,March,21 | 5th,April,21 | 12th,April,21 | 26th,April,21 | 3rd,May,21 | N/A | 24th,May,21 | 26th,May,21 |  | 2nd,June,21 | 9th,June,21 | 23rd,June,21
Actual
9 | Procurement of Prosthetic Lab,Ceramic Lab,Mobile X-ray unit,Hand Instrument,Hand pieces,Auto-clave,Intraoral sensor for periapical, Endomotor rotary hand piece, Surveyor,Duplicating flask, Deeping wax pot, Fret saw, Articulator plain line & Model trimmer. | LASUTH/G/NS/09/21 |  | 27 | 6213500 | <10M | NS | Post | Post | Plan | 8th,March,21 | 15th,March,21 | 22nd,March,21 | 5th,April,21 | 12th,April,21 | 19th,April,21 | 3rd,May,21 | 5th,May,21 |  | 12th,May,21 | 19,May,21 | 2nd,June,21
Actual
10 | Procurement of Spectrophotometer, Elisa Reader, Centrifuge, Water bath,Oven(dry), PH Meter, Serum protein electrophoresis machine & Laboratory refridgerator. | LASUTH/G/NS/10/20 |  | 10 | 11900723.74 | <50M | NS | Post | Post | Plan | 15th,March,21 | 22nd,March,21 | 29th,March,21 | 12th,April,21 | 19th,April,21 | 26th,April,21 | 10th,May,21 | 12th,May,21 |  | 19th,May,21 | 26th,May,21 | 9th,June,21
Actual
11 | Procurement of Short wave Diathermy machine, Diagnostic EMG with Biofeed back, Cervical/Lumbar Tractor machine, Electrical Muscles stimulation & Tilt bed. | LASUTH/G/NS/11/21 |  | 6 | 19000000 | <50M | NS | Post | Post | Plan | 22nd,March,21 | 29th,March,21 | 5th,April,21 | 19th,April,21 | 26th,April,21 | 3rd,May,21 | 17th,May,21 | 19th,May,21 |  | 26th,May,21 | 2nd,June,21 | 16th,June,21
Actual
12 | Procurement of Kichen Equipment. | LASUTH/G/NS/12/21 |  | 1 |  | <10M | NS | Post | Post | Plan | 29th,March,21 | 5th,April,21 | 12th,April,21 | 26th,April,21 | 3rd,May,21 | N/A | 24th,May,21 | 26th,May,21 |  | 2nd,June,21 | 9th,June,221 | 23rd,June,21
[5 empty] | 7334000 |  |  |  |  | Actual
13 | Procurement of Carbondioxide Incubator-thermo Scientific 240L, Automated sperm analyzer, Hot Air oven 254 capacity brand &Urine Analyzer. | LASUTH/G/NS/13/21 |  | 4 | 20108000 | <50M | NS | Post | Post | Plan | 8th,March,21 | 15th,March,21 | 22nd,March,21 | 5th,April,21 | 12th,April,21 | 19th,April,21 | 3rd,May,21 | 5th,May,21 |  | 12th,May,21 | 19th,May,21 | 2nd,June,21
Actual
14 | Procurement of Utility Vehicles,(Toyota Dyna mini truck & Toyota saloon car) | LASUTH/G/NS/14/21 |  | 2 | 36119221 | <50M | NS | Post | Post | Plan | 15th,March,21 | 22nd,March,21 | 29th,March,21 | 12th,April,21 | 19th,April,21 | 26th,April,21 | 10th,May,21 | 12th,May,21 |  | 19th,May,21 | 26th,May,21 | 9th,June,21
Actual
15 | Procurement of Uniform & Protective outfits | LASUTH/G/NS/15/21 |  | 1 | 49226500 | <50M | NS | Post | Post | Plan | 22nd,March,21 | 29th,March,21 | 5th, April,21 | 19th,April,21 | 26th,April,21 | 3rd,May,21 | 17th,May,21 | 19th,May,21 |  | 26th,May,21 | 2nd,June,21 | 16th,June,21
Actual
16 | Procurement of open Heart Surgery Equipment. | LASUTH/G/NS/16/21 |  | 1 | 15000000 | <50M | NS | Post | Post | Plan | 29th,March,21 | 3rd,May,21 | 10th,May,21 | 24th,May,21 | 7th,June,21 | 14th,June,21 | 28th,June,21 | 30th,June,21 |  | 7th,July,21 | 14th,July,21 | 28th,July,21
Actual
17 | Procurement of Generators (A)1000KVA, (B)500KVA 3, © 250KVA. | LASUTH/G/NCB/17/21 |  | 3 | 123919456.26 | <1B | NCB | Post | Post | Plan | 8th,March,21 | 15th,March,21 | 22nd,March,21 | 5th,April,21 | 12th,April,21 | 19th,April,21 | 5th,July,21 | 7th,July,21 |  | 14th,July,21 | 21st,July,21 | 4th,August,21
Actual
18 | Provision of Nurse call system, ( ICT Equipment) in LASUTH. | LASUTH/G/NS/18/21 |  | 1 | 24000000 | <50M | NS | Post | Post | Plan | 15th,March,21 | 22nd,March,21 | 29th,March,21 | 12th,April,21 | 19th,April,21 | 26th,April,21 | 10th,May,21 | 12th,May,21 |  | 19th,May,21 | 26th,May,21 | 9th,June,21
Actual
19 | Hospital intercom system, (Interconnectivity in LASUTH.) | LASUTH/G/NS/19/21 |  | 1 | 20000000 | <50M | NS | Post | Post | Plan | 22nd,March,21 | 29th,March,21 | 5th,April,21 | 19th,April,21 | 26th,April,21 | 3rd,May,21 | 17th,May,21 | 19th,May,21 |  | 26th,May,21 | 2nd,June,21 | 16th,June,21
Actual
20 | Procurement of solar system. | LASUTH/G/NS/20/21 |  | 1 | 20000000 | <50M | NS | Post | Post | Plan | 29th,March,21 | 3rd,May,21 | 10th,May,21 | 24th,May,21 | 7th,June,21 | 14th,June,21 | 28th,June,21 | 30th,June,21 |  | 7th,July,21 | 14th,July,21 | 28th,July,21
Actual
21 | Automation of Lasuth(New). ICT Equipment. | LASUTH/G/NCB/21/21 |  | 1 | 100000000 | <1B | NCB | Post | Post | Plan | 8th,March,21 | 15th,March,21 | 22nd,March,21 | 5th,April,21 | 12th,April,21 | 19th,April,21 | 5th,July,21 | 7th,July,21 |  | 14th,July,21 | 21st,July,21 | 4th,August,21
Actual
[8 empty] | Post | Post | Plan
Actual
[8 empty] | Post | Post | Plan
Actual
[8 empty] | Post | Post | Plan
Actual

## works
PROCUREMENT PLAN FOR WORKS
MINISTRY: LAGOS STATE UNIVERSITY TEACHING HOSPITAL (LASUTH), IKEJA.
BUDGET YEAR: 2021
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Renovation of Old Critical Unit | LASUTH/W/NS/01/21 | 1 | 31250000 | <50M | NS | BOQ | Post | Plan | Post | 1st,feb,21 | 8th,feb,21 | 15th,feb,21 | 1st,March,21 | 8th ,March,21 | 15th,Mar,21 |  |  |  | 22nd,Mar,21 | 29th,March,21 | 12th,April,21
Actual
2 | Construction of Resident Doctors Quarters in LASUTH. | LASUTH/W/NS/02/21 | 1 | 30000000 | <50M | NS | BOQ | Post | Plan | Post | 8th,feb,21 | 15th,feb,21 | 22nd,feb,21 | 8th,March,21 | 15th,March,21 | 22nd,Mar,21 |  |  |  | 29th,Mar,21 | 5th,April,21 | 19th,April,21
Actual
3 | Expansion of Medical & Surgical Emergency unit. | LASUTH/W/NCB/03/21 | 2 | 55000000 | >50M<100M | NCB | BOQ | Post | Plan | Post | 15th,feb,21 | 22nd,feb,21 | 1st, March,21 | 15th,March,21 | 22nd,March,21 | 29th,Mar,21 |  |  |  | 5th,April,21 | 12th,April,21 | 26th,April,21
Actual
4 | Refurbishment of Bola Tinubu Adult | LASUTH/W/NS/05/21 | 1 | 10000000 | <50M | NS | BOQ | Post | Plan | Post | 22nd,feb,21 | 1st,March,21 | 8th,March,21 | 22nd,March,21 | 29th,March,21 | 5th,April,21 |  |  |  | 12th,April,21 | 19th,April,21 | 3rd,May,21
Actual
5 | Extension of Psychiatric Ward/CSSD | LASUTH/W/NS/06/21 | 1 | 15000000 | <50M | NS | BOQ | Post | Plan | Post | 1st,feb,21 | 8th,feb,21 | 15th,feb,21 | 1st,March,21 | 8th,March,21 | 15th,Mar,21 |  |  |  | 22nd,Mar,21 | 29th,March,21 | 12th,April,21
Actual
6 | Construction of Cold Room | LASUTH/W/NS/07/20 | 1 | 7200000 | <10M | NS | BOQ | Post | Plan | Post | 8th,feb,21 | 15th,feb,21 | 22nd,feb,21 | 8th,March,21 | 15th,March,21 | 22nd,Mar,21 |  |  |  | 29th,Mar,21 | 5th,April,21 | 19th,April,21
Actual
7 | Construction of LASUTH Main & Second gates. | LASUTH/W/NS/08/21 | 2 | 31250000 | <50M | NS | BOQ | Post | Plan | Post | 15th,feb,21 | 22nd,feb,21 | 1st,March,21 | 15th,March,21 | 22nd,March,21 | 29th,Mar,21 |  |  |  | 5th,April,21 | 12th,April,21 | 26th,April,21
Actual
8 | Renovation of ENT (Ear,Nose and Throat) Extension. | LASUTH/W/NS/09/21 | 1 | 21250000 | <50M | NS | BOQ | Post | Plan | Post | 22nd,feb,21 | 1st,March,21 | 8th,March,21 | 22nd,March,21 | 29th,March,21 | 5th,April,21 |  |  |  | 12th,April,21 | 19th,April,21 | 3rd,May,21
Actual
9 | Renovation of Old House Officers quarters. | LASUTH/W/NS/10/21 | 1 | 26750000 | <50M | NS | BOQ | Post | Plan | Post | 1st,feb,21 | 8th,feb,21 | 15th,feb,21 | 1st,March,21 | 8th,March,21 | 15th,Mar,21 |  |  |  | 22nd,Mar,21 | 29th,March,21 | 12th,April,21
Actual
| Renovation of Surgical Emergency (New). | LASUTH/W/NS/11/21 | 1 | 30000000 | <50M | NS | BOQ | Post | Plan | Post | 8th,feb,21 | 15th,feb,21 | 22nd,feb,21 | 8th,March,21 | 15th,March,21 | 22nd,Mar,21 |  |  |  | 29th,May,21 | 5th,April,21 | 19th,April,21
10 | [8 empty] | Actual
11 | Renvation of laboratory (New). | LASUTH/W/NS/12/21 | 1 | 25000000 | <50M | NS | BOQ | Post | Plan | Post | 15th,feb, 21 | 22nd,feb,21 | 1st, March,21 | 15th,March,21 | 22nd,March, 21 | 29th,Mar,21 |  |  |  | 5th,April,21 | 12th,April,21 | 26th,April,21
Actual
12 | Renovation of burns and Truama (New) | LASUTH/W/NCB/13/21 | 1 | 135000000 | >100M | NCB | BOQ | Post | Plan | Post | 22nd,feb,21 | 1st,March,21 | 8th,March,21 | 22nd,March,21 | 29th,March,21 | 5th,April,21 |  |  |  | 12th,April,21 | 19th,April,21 | 3rd,May,21
Actual
13 | Renovation of Dental complex(New) | LASUTH/W/NS/14/21 | 1 | 20246000 | <50M | NS | BOQ | Post | Plan | Post | 1st,feb,21 | 8th,feb,21 | 15th,feb,21 | 1st,March,21 | 8th,Mar,21 | 15th,Mar,21 |  |  |  | 22nd,Mar,21 | 29th,March,21 | 12th,April,21
Actual
14 | Renovation of Eye Clinics (New). | LASUTH/W/NS/15/21 | 1 | 22000000 | <50M | NS | BOQ | Post | Plan | Post | 8th,feb,21 | 15th,feb,21 | 22nd,feb,21 | 8th,March,21 | 15th,March,21 | 22nd,Mar,21 |  |  |  | 29th,Mar,21 | 5th,April,21 | 19th,April,21
Actual
15 | Renovation of Pharmacy Building (New). | LASUTH/W/NS/16/21 | 1 | 20804000 | <50M | NS | BOQ | Post | Plan | Post | 15th,feb, 21 | 22nd,feb,21 | 1st,March,21 | 15th,March,21 | 22nd,March, 21 | 29th,Mar,21 |  |  |  | 5th,April,21 | 12th,April,21 | 26th,April,21
Actual
[9 empty] | Plan | Post
Actual
[9 empty] | Plan | Post
Actual
[9 empty] | Plan | Post
Actual
[9 empty] | Plan | Post
Actual
[9 empty] | Plan | Post
Actual
[9 empty] | Plan | Post
Actual