## Non-Proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
LAW REFORM COMMISSION
| MINISTRY/ AGENCY: LAW REFORM COMMISSION | [5 empty] | 2021
BUDGET YEAR: 2021
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TOTAL
1 | TRAVEL & TRANSPORT | LRC/NP/NM/001/2021 | 1,740,000:00 | Plan | 145,000:00 | 145,000:00 | 145,000:00 | 145,000:00 | 145,000:00 | 145,000:00 | 145,000:00 | 145,000:00 | 145,000:00 | 145,000:00 | 145,000:00 | 145,000:00 | 1,740,000:00
Actual
2 | PROFESSIONAL FEES | LRC/NP/NM/002/2021 | 400,000:00 | Plan | 33,333:33 | 33,333:33 | 33,333:33 | 33,333:33 | 33,333:33 | 33,333:33 | 33,333:33 | 33,333:33 | 33,333:33 | 33,333:33 | 33,333:33 | 33,333:33 | 400,000:00
Actual
3 | LEGAL PROFESSIONAL DUES | LRC/NP/NM/001/2021 | 950,000:00 | Plan | 79,166:66 | 79,166:66 | 79,166:66 | 79,166:66 | 79,166:66 | 79,166:66 | 79,166:66 | 79,166:66 | 79,166:66 | 79,166:66 | 79,166:66 | 79,166:66 | 950,000:00
Actual
4 | BANKING OPERATION | LRC/NP/NM/002/2021 | 750,000:00 | Plan | 62,500:00 | 62,500:00 | 62,500:00 | 62,500:00 | 62,500:00 | 62,500:00 | 62,500:00 | 62,500:00 | 62,500:00 | 62,500:00 | 62,500:00 | 62,500:00 | 750,000:00
Actual
5 | PAYMENT FOR GENERAL UTILITY(RECHARGE CARDS & INTERNET ETC) | LRC/NP/NM/003/2021 | 2,982,000:00 | Plan | 248,500:00 | 248,500:00 | 248,500:00 | 248,500:00 | 248,500:00 | 248,500:00 | 248,500:00 | 248,500:00 | 248,500:00 | 248,500:00 | 248,500:00 | 248,500:00 | 2,982,000:00
Actual
6 | SERVICING OF MEETING | LRC/NP/NM/004/2021 | 250,000:00 | Plan | 20,833:33 | 20,833:33 | 20,833:33 | 20,833:33 | 20,833:33 | 20,833:33 | 20,833:33 | 20,833:33 | 20,833:33 | 20,833:33 | 20,833:33 | 20,833:33 | 250,000:00
Actual
7 | PAYMENTS FOR WATER BILL ETC. | LRC/NP/NM/005/2021 | 758,000:00 | Plan | 63,166:66 | 63,166:66 | 63,166:66 | 63,166:66 | 63,166:66 | 63,166:66 | 63,166:66 | 63,166:66 | 63,166:66 | 63,166:66 | 63,166:66 | 63,166:66 | 758,000:00
Actual
Plan
Actual
|  | TOTAL | 7,830,000:00 | Plan
|  |  |  | Actual | [12 empty] | 7,830,000:00

## trg conf wsh
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: LAW REFORM COMMISSION
BUDGET YEAR: 2021
S/N | Description of Training/Workshop/ Conference | Package Number | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | UNDERSTANDING GOVERNMENT LEGAL SERVICE | LRC/S-WTC/SS/001/2021 | CAPACITY BUILDING | 1 | 16TH-19TH NOV 2021 | Plan | ALPHA PARTNERS PROFESSIONAL TRAINING CONFERENCE CENTRE, LAGOS | 250,000:00 | 7,500X4DAYS=30,000:00 | 10,000:00 | N290,000:00
Actual
2 | MANPOWER ORGANIZATION SUCCESSION PLANNING AND TREND ANALYSIS | LRC/S-WTC/SS/002/2021 | CAPACITY BUILDING | 1 | 16TH-19TH NOV 2021 | Plan | ALPHA PARTNERS PROFESSIONAL TRAINING CONFERENCE CENTRE, LAGOS | 185,000:00 | 4,00X4DAYS=16,000:00 | 7,000:00 | N208,000:00
Actual
3 | TRANSFORMATIONAL LEADERSHIP SKILL FOR HUMAN RESOURCE AND ADMINISTRATIVE PERSONNEL | LRC/S-WTC/SS/003/2021 | CAPACITY BUILDING | 1 | 20TH-22TH NOV 2021 | Plan | ALPHA PARTNERS PROFESSIONAL TRAINING CONFERENCE CENTRE, LAGOS | 185,000:00 | 4,00X4DAYS=16,000:00 | 7,000:00 | N208,000:00
Actual
4 | UNDERSTANDING FINANCE AND ACCOUNTING FOR DECISION MAKING. SOUTH AFRICAN | LRC/S-WTC/SS/004/2021 | CAPACITY BUILDING | 1 | 10TH-13TH AUGUST, 2021 | Plan | ALPHA PARTNERS PROFESSIONAL TRAINING CONFERENCE CENTRE, LAGOS | 185,000:00 | 4,00X4DAYS=16,000:00 | 7,000:00 | N208,000:00
Actual
5 | STRATEGIC PUBLIC AFFAIRS AND GOVERNMENT RELATIONS | LRC/S-WTC/SS/005/2021 | CAPACITY BUILDING | 1 | 6TH-9TH JULY 2021 | Plan | ALPHA PARTNERS PROFESSIONAL TRAINING CONFERENCE CENTRE, LAGOS | 185,000:00 | 4,00X4DAYS= 16,000:00 | 7,000:00 | N208,000:00
Actual
6 | INNOVATION IN WORKFORCE PLANNING | LRC/S-WTC/SS/006/2021 | CAPACITY BUILDING | 1 | 16TH -19TH NOVEMBER 2021 | Plan | ALPHA PARTNERS PROFESSIONAL TRAINING CONFERENCE CENTRE, LAGOS | 105,000:00 | 2,500 X 4DAYS =10,000:00 | 5000 | N120,000:00
Actual
7 | ASSERTIVENESS FOR PROFESSIONALS. | LRC/S-WTC/SS/007/2021 | CAPACITY BUILDING | 1 | 20TH -22ND NOVEMBER, 2021 | Plan | ALPHA PARTNERS PROFESSIONAL TRAINING CONFERENCE CENTRE, LAGOS | 105,000:00 | 2,500 X 4DAYS =10,000:00 | 5000 | N120,000:00
Actual
8 | WORK ETHICS AND ATTITUDINAL CHANGE | LRC/S-WTC/SS/008/2021 | CAPACITY BUILDING | 1 | 25TH-29TH OCTOBER 2021 | Plan | NIM LAGOS | 105,000:00 | 2,500 X 4DAYS =10,000:00 | 5000 | N120,000:00
Actual
9 | CONFLICT MANAGEMENT | LRC/S-WTC/SS/009/2021 | CAPACITY BUILDING | 1 | 4TH-8TH OCTOBER,2021 | Plan | NIM LAGOS | 105,000:00 | 2,500 X 4DAYS =10,000:00 | 5000 | N120,000:00
Actual
10 | MANAGING PEOPLE FOR COMPETITIVE ADVANTAGE | LRC/S-WTC/SS/010/2021 | CAPACITY BUILDING | 1 | 25TH-29TH OCTOBER 2021 | Plan | NIM LAGOS | 105,000:00 | 2,500 X 4DAYS =10,000:00 | 5000 | N120,000:00
Actual
11 | PROJECT MANAGEMENT FUNDAMENTALIST | LRC/S-WTC/SS/011/2021 | CAPACITY BUILDING | 1 | 25TH-29TH OCTOBER,2021 | Plan | NIM LAGOS | 105,000:00 | 1,500 X 4DAYS =6,000:00 | 2500 | N113,500:00
Actual
12 | PROJECT MANAGEMENT FUNDAMENTALIST | LRC/S-WTC/SS/012/2021 | CAPACITY BUILDING | 1 | 25TH-29TH OCTOBER,2021 | Plan | NIM LAGOS | 105,000:00 | 1,500 X 4DAYS =6,000:00 | 2500 | N113,500:00
Actual
13 | CONFLICT MANAGEMENT | LRC/S-WTC/SS/013/2021 | CAPACITY BUILDING | 1 | 4TH-8TH OCTOBER 2021 | Plan | NIM LAGOS | 105,000:00 | 1,500 X 4DAYS =6,000:00 | 2500 | N113,500:00
Actual
14 | CONFLICT MANAGEMENT | LRC/S-WTC/SS/014/2021 | CAPACITY BUILDING | 1 | 4TH-8TH OCTOBER 2021 | Plan | NIM LAGOS | 105,000:00 | 1,500 X 4DAYS =6,000:00 | 2500 | N113,500:00
Actual
15 | DIGITISED RECORD MANAGEMENT | LRC/S-WTC/SS/015/2021 | CAPACITY BUILDING | 1 | 4TH-8TH OCTOBER 2021 | Plan | NIM LAGOS | 105,000:00 | 1,500 X 4DAYS =6,000:00 | 2500 | N113,500:00
Actual
16 | WORK ETHICS AND ATTITUDINAL CHANGE | LRC/S-WTC/SS/016/2021 | CAPACITY BUILDING | 1 | 25TH-29TH OCTOBER, 2021 | Plan | NIM LAGOS | 105,000:00 | 1,500 X 4DAYS =6,000:00 | 2500 | N113,500:00
Actual
17 | WORK ETHICS AND ATTITUDINAL CHANGE | LRC/S-WTC/SS/017/2021 | CAPACITY BUILDING | 1 | 25TH-29TH OCTOBER, 2021 | Plan | NIM LAGOS | 105,000:00 | 1,000 X 4DAYS =4,000:00 | 1,500:00 | N110,500:00
Actual
18 | DIGITISED RECORD MANAGEMENT | LRC/S-WTC/SS/018/2021 | CAPACITY BUILDING | 1 | 25TH-29TH OCTOBER, 2021 | Plan | NIM LAGOS | 105,000:00 | 1,000 X 4DAYS =4,000:00 | 1500 | N110,500:00
Actual
19 | MANAGING PEOPLE FOR COMPETITIVE ADVANTAGE | LRC/S-WTC/SS/019/2021 | CAPACITY BUILDING | 1 | 25TH-29TH OCTOBER, 2021 | Plan | NIM LAGOS | 105,000:00 | 1,000 X 4DAYS =4,000:00 | 1500 | N110,500:00
Actual
20 | MANAGING PEOPLE FOR COMPETITIVE ADVANTAGE | LRC/S-WTC/SS/020/2021 | CAPACITY BUILDING | 1 | 25TH-29TH OCTOBER 2021 | Plan | NIM LAGOS | 105,000:00 | 1,000 X 4DAYS =4,000:00 | 1500 | N110,500:00
Actual
TOTAL
N2,845,000:00

## non-cons
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY:
BUDGET YEAR: 2021 (LAW REFORM COMMISSION)
Contract Description | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
| Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
MAINTENANCE OF OFFICE BUILDING | LRC/S-NC-F/NS/001/2021 | N/A | 1 | 270,000:00 | <N10 | NS | Plan | POST | POST | 2021-03-05 | 2021-03-12 | 2021-03-24 | 2021-04-09 | N/A | 2021-04-17 | N/A | PLAN |  |  | 270,000:00 | 2021-06-07 | 2021-07-14 | 2021-09-09 | 2021-09-26
Actual
SERVICE OF MOTOR VEHICLE REPAIRS & MAINTENANCE | LRC/S-NC-F/NS/002/2021 | N/A | 2 | 130,000:00 | <N10 | NS | Plan | POST | POST | 2021-04-02 | 2021-04-09 | 2021-04-19 | 2021-04-30 | N/A | 2021-05-07 | N/A | Plan |  |  | 130,000:00 | 2021-05-20 | 2021-05-27 | 2021-06-11 | 2021-06-25
SPECIAL DUTIES EXPENSES | LRC/S-NC/NS/003/2021 | N/A |  | 600,000:00 | <N10 | NS | Plan | POST | POST | [7 empty] | Plan |  |  | 600,000:00
[7 empty] | Actual | [9 empty] | Actual
SPECIAL PROGRAMMES EXPENSES | LRC/S-NC/NS/004/2021 | N/A |  | 1,550,000:00 | <N10 | NS | Plan | [9 empty] | Plan |  |  | 1,550,000:00
[7 empty] | Actual | [9 empty] | Actual
PROCUREMENT OF PRINTING JOB | LRC/S-NC/NS/005/2021 | N/A |  | 250,000:00 | <N10 | NS | Plan | [8 empty] | 2019-03-26 | Plan |  |  | 250,000:00
[7 empty] | Actual | [9 empty] | Actual
PAYMENT OF GENERAL UTILITY(RECHARGE CARDS & INTERNET ETC) | LRC/S-NC/NS/006/2021 | N/A |  | 2,982,000:00 | <N10 | NS | Plan | [8 empty] | 2019-03-26 | Plan |  |  | 2,982,000:00
[7 empty] | Actual | [9 empty] | Actual
PAYMENT OF BOARD MEMBER SITTING ALLOWANCE | LRC/S-NC/NS/007/2021 | N/A |  | 2,250,000:00 | <N10 | NS | Plan | [8 empty] | 2019-03-26 | Plan |  |  | 2,250,000:00
[7 empty] | Actual | [9 empty] | Actual
| TOTAL |  |  | 8,032,000:00 |  |  | Plan | [8 empty] | 2019-03-26 | Plan |  |  | 8,032,000:00
[7 empty] | Actual | [9 empty] | Actual

## consultancy
PROCUREMENT PLAN FOR CONSULTING SERVICES
| MINISTRY/ AGENCY: | [14 empty] | LAW REFORM COMMISSION
BUDGET YEAR: 2021
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[5 empty] | 0 |  | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
|  |  | NS |  | 4,000,000:00 | POST | Plan | 5/03/2021 | 12/03/2021 | 19/03/2021 | 9/04/2021 | 16/04/2021 | 23/04/2021 | 14/05/2021 | 21/05/2021 | 28/05/2021 | 4/06/2021 | 18/06/2021 | 25/06/2021 | 23/07/2021 | 24/07/2021 | 4,000,000:00 | N/A | N/A | 30/07/2021 | 6/08/2021
Actual
Plan
Actual
Plan
Actual
Plan
Actual
1 | [6 empty] | Plan
Actual
[5 empty] | 4,000,000:00 |  | Plan
[7 empty] | Actual | [14 empty] | 4,000,000:00

## goods
PROCUREMENT PLAN FOR GOODS
MINISTRY/AGENCY: LAW REFORM COMMISSION
BUDGET YEAR: 2021
S/N | CONTRACT IDENTIFICATION |  |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description |  | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[12 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | PROCUREMENT OF MOTOR VEHICLE FUEL CONSUMPTIONS |  | LRC/G-F/NS/001/21 | N/A |  | 420,000:00 | <10M | NS | POST | POST | Plan | 11/3/2021 | N/A | 18/3/2021 | 01/4/2021 | 8/4/2021 | N/A | 15/04/21 | 16/04/21 |  | N/A | 23/04/20 | 2020-04-30
Actual
2 | PROCUREMENT OF STATIONERY |  | LRC/G-F/NS/002/21 | N/A |  | 1,500,000:00 | <10M | NS | POST | POST | Plan | 25/3/2021 | N/A | 1/04/2021 | 15/04/2021 | 22/04/2021 | N/A | 29/04/2021 | 30/04/2021 |  | N/A | 7/05/2021 | 2021-05-14
Actual
3 | PAYMENT OF GATE PASS & SUBSCRIPTION |  | LRC/G/NS/003/21 | N/A |  | 250,000:00 | <10M | NS | POST | POST | Plan | 25/3/2021 | N/A | 1/04/2021 | 15/04/2021 | 22/04/2021 | N/A | 29/04/2021 | 30/04/2021 |  | N/A | 7/05/2021 | 2021-05-14
Actual
4 | PROCUREMENT OF UNIFORM & PROTECTIVE OUTFIT |  | LRC/G/NS/004/21 | N/A |  | 200,000:00 | <10M | NS | POST | POST | Plan | 27/03/2021 | N/A | 3/04/2021 | 17/04/2021 | 24/04/2021 | N/A | 30/04/2021 | 01/05/2021 |  | N/A | 8/05/2021 | 2021-05-15
Actual
5 | PROCUREMENT OF RESOURCE CENTRE TOOLS |  | LRC/G/NS/005/21 | N/A |  | 1,400,000:00 | <10M | NS | POST | POST | Plan | 27/03/2020 | N/A | 3/04/2021 | 17/04/2021 | 24/04/2021 | N/A | 30/04/2021 | 01/05/2021 |  | N/A | 8/05/2021 | 2021-05-15
Actual
| PROCUREMENT OF MATERIALS &EQUIPMENT FOR PROCUREMENT UNIT |  | LRC/G/NS/006/21 | N/A |  | 500,000:00 | <10M | NS | POST | POST | Plan | 8/04/2020 | 1/4/2020 | 15/4/2021 | 29/04/2021 | 6/5/2021 | N/A | 13/05/2021 | 14/05/2021 |  | N/A | 21/05/2021 | 2021-06-11
6
7 | PROCUREMENT OF AUDIT TOOLS(MATERIALS & EQUIPMENTS ETC) |  | LRC/G/NS/006/21 | N/A |  | 500,000:00 | <10M | NS | POST | POST | Plan | 4/3/2020 | 1/4/2020 | 15/4/2021 | 13/5/2021 | 27/5/2021 | 10/6/2021 | 17/6/2021 | 18/06/2021 |  | N/A | 22/7/2021 | 2021-07-22
Actual
8 | PROCUREMENT OF PUBLIC AFFAIRS TOOLS(MATERIALS & EQUIPMENTS ETC) |  | LRC/G/NS/007/21 | N/A |  | 500,000:00 | <10M | NS | POST | POST | Plan | 29/4/2020 | 27/5/2020 | 10/6/2021 | 8/7/2021 | 22/7/2021 | 5/8/2021 | 19/08/2021 | 20/08/2021 |  | N/A | 18/9/2021 | 2021-09-18
Actual
Actual
9 | PROCUREMENT OF PLANNING RESEARCH & STATISTICS UNIT TOOLS (MATERIALS & EQUIPMENTS ETC) |  | LRC/G/NS/0011/21 | N/A |  | 525,000:00 | <10M | NS | POST | POST | Plan | 29/4/2020 | 27/5/2020 | 10/6/2021 | 8/7/2021 | 22/7/2021 | 5/8/2021 | 19/08/2021 | 20/08/2021 |  | N/A | 18/9/2021 | 2021-09-18
Actual
10 | PROCUREMENT OF CONSUMABLES FOR HUMAN RESOURCES DEPT |  | LRC/G/NS/0012/21 | N/A |  | 800,000:00 | <10M | NS | POST | POST | Plan | 29/4/2020 | 27/5/2020 | 10/6/2021 | 8/7/2021 | 22/7/2021 | 5/8/2021 | 19/08/2021 | 20/08/2021 |  | N/A | 18/9/2021 | 2021-09-18
Actual
|  | TOTAL |  |  |  | 7,645,000:00

## trg conf wsh 2
13 | CONFLICT MANAGEMENT | LRC/S-WTC/SS/013/2021 | CAPACITY BUILDING | 1 | 4TH-8TH OCTOBER 2021 | Plan | NIM LAGOS | 105,000:00 | 1,500 X 4DAYS =6,000:00 | 2500 | N113,500:00
Actual
14 | CONFLICT MANAGEMENT | LRC/S-WTC/SS/014/2021 | CAPACITY BUILDING | 1 | 4TH-8TH OCTOBER 2021 | Plan | NIM LAGOS | 105,000:00 | 1,500 X 4DAYS =6,000:00 | 2500 | N113,500:00
Actual
15 | DIGITISED RECORD MANAGEMENT | LRC/S-WTC/SS/015/2021 | CAPACITY BUILDING | 1 | 4TH-8TH OCTOBER 2021 | Plan | NIM LAGOS | 105,000:00 | 1,500 X 4DAYS =6,000:00 | 2500 | N113,500:00
Actual
16 | WORK ETHICS AND ATTITUDINAL CHANGE | LRC/S-WTC/SS/016/2021 | CAPACITY BUILDING | 1 | 25TH-29TH OCTOBER, 2021 | Plan | NIM LAGOS | 105,000:00 | 1,500 X 4DAYS =6,000:00 | 2500 | N113,500:00
Actual
17 | WORK ETHICS AND ATTITUDINAL CHANGE | LRC/S-WTC/SS/017/2021 | CAPACITY BUILDING | 1 | 25TH-29TH OCTOBER, 2021 | Plan | NIM LAGOS | 105,000:00 | 1,000 X 4DAYS =4,000:00 | 1,500:00 | N110,500:00
Actual
18 | DIGITISED RECORD MANAGEMENT | LRC/S-WTC/SS/018/2021 | CAPACITY BUILDING | 1 | 25TH-29TH OCTOBER, 2021 | Plan | NIM LAGOS | 105,000:00 | 1,000 X 4DAYS =4,000:00 | 1500 | N110,500:00
Actual
19 | MANAGING PEOPLE FOR COMPETITIVE ADVANTAGE | LRC/S-WTC/SS/019/2021 | CAPACITY BUILDING | 1 | 25TH-29TH OCTOBER, 2021 | Plan | NIM LAGOS | 105,000:00 | 1,000 X 4DAYS =4,000:00 | 1500 | N110,500:00
Actual
20 | MANAGING PEOPLE FOR COMPETITIVE ADVANTAGE | LRC/S-WTC/SS/020/2021 | CAPACITY BUILDING | 1 | 25TH-29TH OCTOBER 2021 | Plan | NIM LAGOS | 105,000:00 | 1,000 X 4DAYS =4,000:00 | 1500 | N110,500:00
Actual
TOTAL
N2,845,000:00

## works
PROCUREMENT PLAN FOR WORKS
MINISTRY: LAW REFORM COMMISSION
BUDGET YEAR: 2021
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
1 |  | LRC/W/NS/001/2021 |  | 23,578,434:00 | [6 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
[9 empty] | Plan | POST | 2021-03-05 | 2021-03-12 | 2021-03-22 | 2021-04-03 | 2021-04-10 | 2021-04-17 |  |  | 23578434
[9 empty] | Actual | [11 empty] | 2021-06-04 | 2021-06-07 | 2021-07-14 | 2021-09-09
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
|  |  |  | 23,578,434:00 |  |  |  |  | Plan | [9 empty] | 23578434
Actual

## GOODS PART2
MINISTRY/AGENCY: LAW REFORM COMMISSION
BUDGET YEAR: 2021
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | PROCUREMENT OF FURNITURES,LAPTOP & EQUIPMENT | LRC/G/NS/001/21 | N/A |  | 23,578,434:00 | <50M | NS | POST | POST | Plan | 11/3/2021 | N/A | 18/3/2021 | 01/4/2021 | 8/4/2021 | N/A | 15/04/21 | 16/04/21 | 23,578,434:00 | N/A | 23/04/20 | 2020-04-30
Actual
[5 empty] | 23,578,434:00 | [13 empty] | 23,578,434:00 |  |  | 2021-05-14