## Non-Proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: LAGOS MULTI-DOOR COURTHOUSE
BUDGET YEAR: YEAR 2021
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TOTAL
1 | PAYMENT OF STAFF SALARIES | LMDC/NM/01/2021 | 60,115,363.40 | Plan | 5012946.95 | 5012946.95 | 5012946.95 | 5012946.95 | 5012946.95 | 5012946.95 | 5012946.95 | 5012946.95 | 5012946.95 | 5012946.95 | 5012946.95 | 5012946.95 | 60,115,363.40
Actual
2 | TRAVEL & TRANSPORT | LMDC/NM/02/2021 | 900,000.00 | Plan | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 900000
Actual
3 | GENERAL UTILITY SERVICES | LMDC/NM/03/2021 | 2750000 | Plan | 62790.7 | 62790.7 | 62790.7 | 62790.7 | 62790.7 | 62790.7 | 62790.7 | 62790.7 | 62790.7 | 62790.7 | 62790.7 | 62790.7 | 2700000
Actual
4 | PROFESSIONAL & ASSOCIATION DUES | LMDC/NM/04/2021 | 800,000.00 | Plan | [5 empty] | 800000 | [6 empty] | 800000
Actual
5 | BOARD MEMBERS ALLOWANCE | LMDC/NM/05/2021 | 2,060,000.00 | Plan |  | 2060000 | [10 empty] | 2060000
Actual
6 | MEDIATORS FEES & EVENTS | LMDC/NM/06/2021 | 9,160,000.00 | Plan |  | 9160000 | [10 empty] | 9160000
Actual
7 | ADR EXPENSES | LMDC/NM/07/2021 | 4,400,000.00 | Plan |  | 4400000 | [10 empty] | 4400000
Actual
8 | MISCELLANEOUS | LMDC/NM/08/2021 | 6,146,039.00 | Plan |  | 6146039
Actual
9 | PUBLICITY & PUBLIC RELATION (HONORARIUM) | LMDC/NM/09/2021 | 1000000 | Plan |  | 1000000 | [10 empty] | 1000000
Actual
10 | SPECIAL DUTIES | LMDC/NM/10/2021 | 500000 | Plan |  | 500000 | [10 empty] | 500000
Actual
| TOTAL |  | 87831402.4 | [13 empty] | 87831402.4

## trg conf wsh
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: LAGOS MULTIDOOR COURTHOUSE
BUDGET YEAR: YEAR2021
S/N | Description of Training/Workshop/ Conference | Package Number | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | CONFERENCE AND SEMINAR | LMDC/CONF/001/2021 |  |  |  | Plan |  |  |  |  | 400000
Actual
2 | WORKSHOP AND TRAINING | LMDC/WSH/002/2021 |  |  |  | Plan |  |  |  |  | 300000
Actual
3 | TOTAL |  |  |  |  | Plan |  |  |  |  | 700000
Actual
4 | [5 empty] | Plan
Actual
5 | [5 empty] | Plan
Actual
6 | [5 empty] | Plan
Actual
7 | [5 empty] | Plan
Actual
8 | [5 empty] | Plan
Actual
9 | [5 empty] | Plan
Actual
10 | [5 empty] | Plan
Actual
11 | [5 empty] | Plan
Actual
12 | [5 empty] | Plan
Actual

## non-cons
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY:
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/ AGENCY: LAGOS MULTI-DOOR COURTHOUSE
BUDGET YEAR: YEAR 2021
Contract Description | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
| Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
MAINTENANCE OF OFFICE BUILDING | LMDC/S-NC/NS/001/2021 | 1 | 5 | 1600000 | <50million | NS | Plan | Post | Post | 2021-01-08 | NA | 2021-01-22 | 2021-01-29 | 2021-02-12 | 2021-02-19 | NA | Plan | 2021-03-25 | 2021-04-03 | 1600000 | 2021-04-29 | 2021-05-08 | 2021-05-15 | 2021-05-29
[7 empty] | Actual | [9 empty] | Actual
REPAIRS OF MOTOR VEHICLES | LMDC/S-NC/NS/002/2021 | 1 | 4 | 2050000 | <50million | NS | Plan | Post | Post | 2021-01-02 | NA | 2021-03-31 | 2021-04-22 | 2021-05-28 | 2021-06-29 | NA | Plan | 2021-08-04 | 2021-09-30 | 2050000 | 2021-10-30 | 2021-11-02 | 2021-11-30 | 2021-12-31
[7 empty] | Actual | [9 empty] | Actual
MAINTENANCE OF OFFICE EQUIPMENT & GENERATOR | LMDC/S-NCS/NS/003/2021 | 1 | 5 | 1100000 | <50million | NS | Plan | Post | Post | 2021-01-31 | NA | 2021-03-31 | 2021-04-30 | 2021-05-29 | 2021-06-30 | NA | Plan | 2021-07-31 | 2021-08-31 | 1100000 | 2021-09-30 | 2021-11-30 | 2021-12-01 | 2021-12-31
[7 empty] | Actual | [9 empty] | Actual
OFFICE BUILDING:
LMDC SIGNAGE & PUBLICITY BANNERS | LMDC/S-NC/IC/004/2021 | 1 |  | 1200000 | <50million | NS | Plan | Post | Post | 2021-01-31 | NA | 2021-03-31 | 2021-04-30 | 2021-05-29 | 2021-06-30 | NA | Plan | 2021-07-31 | 2021-08-31 | 1200000 | 2021-09-30 | 2021-11-30 | 2021-12-01 | 2021-12-31
[7 empty] | Actual | [9 empty] | Actual
EXTENSION & RENOVATION OF OFFICE | LMDC/S-NC/IC/004/2021 | 2 |  | 7442447 | <50million | NS | Plan | Post | Post | 2021-01-31 | NA | 2021-03-31 | 2021-04-30 | 2021-05-29 | 2021-06-30 | NA | Plan | 2021-07-31 | 2021-08-31 | 7442447 | 2021-09-30 | 2021-11-30 | 2021-12-01 | 2021-12-31
[7 empty] | Actual | [9 empty] | Actual
PAINTING OF OFFICES | LMDC/S-NC/IC/004/2021 | 3 |  | 350000 | <50million | NS | Plan | Post | Post | 2021-01-31 | NA | 2021-03-31 | 2021-04-30 | 2021-05-29 | 2021-06-30 | NA | Plan | 2021-07-31 | 2021-08-31 | 350000 | 2021-09-30 | 2021-11-30 | 2021-12-01 | 2021-12-31
[7 empty] | Actual | [9 empty] | Actual
ELECTRICAL WORKS | LMDC/S-NC/IC/004/2021 | 4 |  | 485000 | <50million | NS | Plan | Post | Post | 2021-01-31 | NA | 2021-03-31 | 2021-04-30 | 2021-05-29 | 2021-06-30 | NA | Plan | 2021-07-31 | 2021-08-31 | 485000 | 2021-09-30 | 2021-11-30 | 2021-12-01 | 2021-12-31
[7 empty] | Actual | [9 empty] | Actual
OFFICE FURNITURE:
GENERAL CARPENTRY WORKS | LMDC/S-NC/[C/005/2021 | 1 | 50 | 300000 | <50million | NS | Plan | Post | Post | 2021-01-08 | NA | 2021-01-22 | 2021-01-29 | 2021-02-12 | 2021-02-19 | NA | Plan | 2021-03-25 | 2021-04-03 | 1600000 | 2021-04-29 | 2021-05-08 | 2021-05-15 | 2021-05-29
[7 empty] | Actual | [9 empty] | Actual
Total Cost |  |  |  | 14527447 |  |  | Plan | [12 empty] | 14527447
Actual

## consultancy
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/ AGENCY: LAGOS MULTI-DOOR COURTHOUSE
BUDGET YEAR: YEAR 2021
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[5 empty] | 0 |  | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
1 | LAGOS SETTLEMENT WEEK (SPECIAL PROGRAMS) | LMDC/CS/CQ/001/2021 | CQ | Lumpsum | 19578000 | Prior | Plan | 11-Sep,2020 | 12-Sep,2020 | 2-Oct,2020 | 16-Oct,2020 | 23-Oct, 2020 | 30-Oct,2020 | 16-Nov, 2020 | 23-Nov,2020 | 30-Nov,2020 | 07- Dec2020 | 14-Dec,2020 | 21-Dec,2020 | 12-Jan.2021 | 13-Jan.2020 | 17300000 | N/A | N/A | N/A | 28-Jan.2020 | 1-Feb, 2021 | 17,300,000.00
Actual
2 | MANAGEMENT INFORMATION SYSTEM | LMDC/CS/LC/002/2021 | LC | Lumpsum | 3340000 | Post | Plan | 2021-03-03 | NA | 2021-03-10 | 2021-03-24 | 2021-03-31 | 2021-04-07 | 2021-04-14 | 2021-04-28 | 2021-05-05 | 2021-05-12 | 2021-05-19 | 2021-05-26 | 2021-06-23 | 2021-06-25 | 3340000 | 2021-07-01 | 2021-07-08 | 2021-07-22 | 2021-09-09 | 2021-09-30 | 340000
Actual
| Total Cost |  |  |  | 20640000 |  | Plan | [20 empty] | 20640000
[7 empty] | Actual | [14 empty] | 20640000

## goods
PROCUREMENT PLAN FOR GOODS
LAGOS MULTI-DOOR COURTHOUSE
YEAR 2021
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | PROCUREMENT OF OFFICE EQUIPMENT | LMDC/G/NS/001/2021 | 1 | 10 | 5760000 | < 50million | NS | Post | Post | Plan | 2021-02-10 | 2021-02-17 | 2021-02-24 | 2021-03-02 | 2021-03-09 | 2021-03-16 | 2021-04-20 | 2021-04-23 | 5760000 | 2021-04-30 | 2021-05-07 | 2021-05-21 | 2021-05-31 | 2021-06-03
Actual
2 | PROCUREMENT OF OFFICIAL BUS | LMDC/G/NS/002/2021 | 1 | 1 | 14500000 | <50million | NS | Prior | Prior | Plan | 2021-03-30 | 2021-04-13 | 2021-04-27 | 2021-05-25 | 2021-06-02 | 2021-06-09 | 2021-07-06 | 2021-07-09 | 14500000 | 2021-07-16 | 2021-07-30 | 2021-08-17 | 2021-10-20 | 2021-10-29
Actual
3 | PROCUREMENT OF STATIONERIES | LMDC/G/NS/003/2021 | 1 | 5 | 4200000 | < 50million | NS | Post | Post | Plan | 2021-02-02 | NA | 2021-02-10 | 2021-02-24 | 2021-02-26 | NA | 2021-03-30 | 2021-04-01 | 4200000 | 2021-04-08 | 2021-04-15 | 2021-04-22 | 2021-04-30 | 2021-05-03
Actual
4 | PRINTING | LMDC/G/NS/004/2021 | 1 | 5 | 1250000 | < 50million | NS | Post | Post | Plan | 2021-02-02 | NA | 2021-02-10 | 2021-02-24 | 2021-02-26 | NA | 2021-03-30 | 2021-04-01 | 1250000 | 2021-04-08 | 2021-04-15 | 2021-04-22 | 2021-04-30 | 2021-05-03
Actual
5 | PROCUREMENT OF OFFICE FURNITURE | LMDC/G/NS/005/2021 | 1 | 5 | 850000 | < 50million | NS | Post | Post | Plan | 2021-02-10 | 2021-02-17 | 2021-02-24 | 2021-03-02 | 2021-03-09 | 2021-03-16 | 2021-04-20 | 2021-04-23 | 850000 | 2021-04-30 | 2021-05-07 | 2021-05-21 | 2021-05-31 | 2021-06-03
Actual
6 | PROCUREMENT OF LED LIGHTENING | LMDC/G/NS/006/2021 | 1 | 30 | 600000 | <50million | NS | Post | Post | Plan | 2021-03-30 | 2021-04-13 | 2021-04-27 | 2021-05-25 | 2021-06-02 | 2021-06-09 | 2021-07-06 | 2021-07-09 | 600000 | 2021-07-16 | 2021-07-30 | 2021-08-17 | 2021-10-20 | 2021-10-29
Actual
7 | FUELING OF MOTOR VEHICLES | LMDC/G/NS/007/2021 | 1 | 8 | 2500000 | < 50million | NS | Post | Post | Plan | 2021-01-06 | NA | 2021-01-13 | 2021-01-20 | 2021-01-24 | NA | 2021-02-21 | 2021-02-25 | 2500000 | 2021-03-02 | 2021-03-09 | 2021-03-16 | 2021-12-15 | 2021-12-23
Actual
8 | PROCUREMENT OF MICROSOFT OFFICE & ANTI-VIRUS | LMDC/G/NS/008/2021 | 1 | 8 | 340000 | < 50million | NS | Post | Post | Plan | 2021-01-06 | NA | 2021-01-13 | 2021-01-20 | 2021-01-24 | NA | 2021-02-21 | 2021-02-25 | 340000 | 2021-03-02 | 2021-03-09 | 2021-03-16 | 2021-12-15 | 2021-12-23
Actual
| Total Cost |  |  |  | 30000000 |  |  |  |  | Plan | [8 empty] | 30000000
[10 empty] | Actual | [8 empty] | #REF!

## works
PROCUREMENT PLAN FOR WORKS
MINISTRY: LAGOS MULTI-DOOR COURTHOUSE
BUDGET YEAR: 2021
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual