## Non-Proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: LAGOS WATER CORPORATION
BUDGET YEAR: 2021
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TOTAL
1 | Personnel Cost (Salaries, and Wages, Allowances, pensions and gratuities | LSWC/NP/NM/001/21 | 1,303,873,592.00 | Plan | 108656132.6667 | 108656132.6667 | 108656132.6667 | 108656132.6667 | 108656132.6667 | 108656132.6667 | 108656132.6667 | 108656132.6667 | 108656132.6667 | 108656132.6667 | 108656132.6667 | 108656132.6667 | 1303873592
Actual
2 | Local Travel Allowances for Training of Junior and Senior Staff | LSWC/NP/NM/002/21 | 48,955,876.00 | Plan | 4079656.3333 | 4079656.3333 | 4079656.3333 | 4079656.3333 | 4079656.3333 | 4079656.3333 | 4079656.3333 | 4079656.3333 | 4079656.3333 | 4079656.3333 | 4079656.3333 | 4079656.3333 | 48955876
Actual
3 | Lagos Water Corporation General Utility Services (Payment of Electricity bills for Micro/mini waterworks(38nos), area offices and LWC Headquarters | LSWC/NP/NM/003/21 | 48695806 | Plan | 4057983.8333 | 4057983.8333 | 4057983.8333 | 4057983.8333 | 4057983.8333 | 4057983.8333 | 4057983.8333 | 4057983.8333 | 4057983.8333 | 4057983.8333 | 4057983.8333 | 4057983.8333 | 48695806
Actual
4 | Media & Publicity (Provisions for sensitization of customers on metering,Revenue Drive, Public awareness, Information disemination programmes, Printing of News Letter) | LSWC/NP/NM/004/21 | 5500000 | Plan |  |  | 1375000 |  |  | 1375000 |  |  | 1375000 |  |  | 1375000 | 5500000
Actual
5 |  |  |  | Plan
Actual
6 |  |  |  | Plan
Actual
7 |  |  |  | Plan
Actual
8 |  |  |  | Plan
Actual
9 |  |  |  | Plan
Actual
| GRANDTOTAL |  | 1407025274 | [13 empty] | 1407025274

## trg conf wsh
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY:
BUDGET YEAR:
S/N | Description of Training/Workshop/ Conference | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 |  |  |  |  | Plan
Actual
2 |  |  |  |  | Plan
Actual
3 |  |  |  |  | Plan
Actual
4 |  |  |  |  | Plan
Actual
5 |  |  |  |  | Plan
Actual
6 |  |  |  |  | Plan
Actual
7 |  |  |  |  | Plan
Actual
8 |  |  |  |  | Plan
Actual
9 |  |  |  |  | Plan
Actual
10 |  |  |  |  | Plan
Actual
11 |  |  |  |  | Plan
Actual
12 |  |  |  |  | Plan
Actual

## non-cons
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY: LAGOS WATER CORPORATION
BUDGET YEAR: 2021
| Contract Description | BASIC DATA | [7 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
|  | Package Number |  | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
1 | Servicing and Maintenance of Power Generators at the Lagos Water Corporation Treatment Plants and Offices. | LSWC\¦S-NC\NS\001/21 | LSWC\¦G-F\NS\01\2019 | NA | - | 26727870 | <50M | NS | Plan | Post | Prior | 2021-04-12 | 2021-04-26 | 2021-05-10 | 2021-06-21 | 2021-07-05 | 2021-07-12 | 2021-07-26 | Plan | 2021-08-23 | 2021-08-25 |  | 2021-10-06 | 2021-11-03 | 2021-12-29
[9 empty] | Actual | [9 empty] | Actual
2 | Repair and Maintenance of Motor vehicles in Lagos Water Corporation | LSWC\¦S-NC\NS\002/21 |  | N/A | - | 32312000 | <50M | NS | Plan | Post | Prior | 2021-03-04 | 2021-03-18 | 2021-04-01 | 2021-05-13 | 2021-05-27 | 2021-06-03 | 2021-06-17 | Plan | 2021-07-15 | 2021-07-17 |  | 2021-08-28 | 2021-09-25 | 2021-11-20
[9 empty] | Actual | [9 empty] | Actual
[9 empty] | Plan | [9 empty] | Plan
[9 empty] | Actual | [9 empty] | Actual
[9 empty] | Plan | [9 empty] | Plan
[9 empty] | Actual | [9 empty] | Actual
[9 empty] | Plan | [9 empty] | Plan
[9 empty] | Actual | [9 empty] | Actual
[9 empty] | Plan | [9 empty] | Plan
[9 empty] | Actual | [9 empty] | Actual
[9 empty] | Plan | [9 empty] | Plan
[9 empty] | Actual | [9 empty] | Actual
[9 empty] | Plan | [9 empty] | Plan
[9 empty] | Actual | [9 empty] | Actual
| GRANDTOTAL |  |  |  |  | 59039870
Formulas:
PPA No Objection Date (1-2wks) = [BIDDING PERIOD]+14
Bid Invitation Date (1-2wks) = [PPA No Objection Date (1-2wks)]+14
BID EVALUATION = [Bid Invitation Date (1-2wks)]+42
CONTRACT FINALIZATION = [Minutes of Negotiation (1 wk)]+14
Mr. Governor's Approval (1-4 wks) = [CONTRACT FINALIZATION]+28
Mobilization Advance Payment (2-4 wks) = [Date Contract Signature (4-6 wks)]+28
Complete Delivery/Install (2-8 wks) = [Mobilization Advance Payment (2-4 wks)]+56

## consultancy
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/ AGENCY:
BUDGET YEAR:
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[5 empty] | 0 |  | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual

## goods
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: LAGOS WATER CORPORATION
BUDGET YEAR: 2021
| CONTRACT IDENTIFICATION |  |  |  | BASIC DATA | [7 empty] | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
S/N | Contract Description |  | Package Number |  | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Plan Vs Actual | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[13 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Procurement of Printing and Stationery equipment, materials and consumables for the operation of Lagos Water Corporation | Procurement of Printing and Stationery equipment, materials and consumables for the operation of Lagos Water Corporation | LSWC\¦G-F\NS\01\21 | LSWC\¦G-F\NS\01\2019 | N/A |  | 8000348 | <50M | NS | Post | Post | Plan | 2021-03-01 | 2021-03-15 | 2021-03-29 | 2021-04-12 | 2021-04-26 | 2021-05-03 |  |  |  | 2021-05-10 | 2021-05-24 | 2021-06-07
Actual
2 | Procurement of Computer Equipment and Accessories including Laptops and Desktops in Lagos water Corporation | Procurement of Computer Equipment and Accessories including Laptops and Desktops in Lagos water Corporation | LSWC\G\NS\02\21 | LSWC\G\NS\02\2019 | N/A |  | 20115086 | <50M | NS | Post | Prior | Plan | 2021-03-04 | 2021-03-18 | 2021-04-01 | 2021-04-15 | 2021-04-29 | 2021-05-06 |  |  |  | 2021-05-13 | 2021-05-27 | 2021-06-10
|  |  | LSWC/GDS/2016/02 | LSWC/GDS/2016/02 | [7 empty] | Actual
3 | Procurement of Fuel for the Lagos Water Corporation Operations at the Head Office, Water Treatment Plant and for Trucks operations | Procurement of Fuel for the Lagos Water Corporation Operations at the Head Office, Water Treatment Plant and for Trucks operations | LSWC\DC\NCB\03\21 | LSWC\G-F\NCB\03\2019 | N/A |  | 98410000 | <100M | NCB | Post | Prior | Plan | 2021-03-05 | 2021-03-12 | 2021-03-19 | 2021-04-02 | 2021-04-09 | 2021-04-16 |  |  |  | 2021-04-23 | 2021-05-07 | 2021-05-21
|  |  | LSWC/GDS/2016/02 | LSWC/GDS/2016/02 | [7 empty] | Actual
4 | Procurement of Aluminium Sulphate (Alum)/Coagulant Aid for the water treatment in Lagos Water Corporation | Procurement of Aluminium Sulphate (Alum)/Coagulant Aid for the water treatment in Lagos Water Corporation | LSWC\G\ICB\04\21 | LSWC\G\DC\04\2019 | N/A |  | 1092750000 | <5B | ICB | Post | Prior | Plan | 2021-03-04 | 2021-03-18 | 2021-04-01 | 2021-04-29 | 2021-05-13 | 2021-05-20 | 2021-06-17 | 2021-06-21 |  | 2021-06-28 | 2021-07-12 | 2021-08-09
|  |  | LSWC/GDS/2016/02 | LSWC/GDS/2016/02 | [7 empty] | Actual
5 | Procurement of Water Treatment Chemicals (Calcium Hydroxide (Hydrated Lime) for the water treatment in Lagos Water Corporation | Procurement of Calcium Hydroxide (Hydrated Lime) for the water treatment in Lagos Water Corporation | LSWC\G\NS\05/001/21 | LSWC\G\NS\05/2019 | N/A |  | 7840000 | <10M | NS | Post | Post | Plan | 2021-04-08 | 2021-04-22 | 2021-05-06 | 2021-05-20 | 2021-06-03 | 2021-06-10 |  |  |  | 2021-06-17 | 2021-07-01 | 2021-07-15
|  |  | LSWC/GDS/2016/02 | LSWC/GDS/2016/02 | [7 empty] | Actual
6 | Procurement of Water Treatment Chemicals (Sodium Carbonate (Soda Ash) for the water treatment in Lagos Water Corporation | Procurement of Sodium Carbonate (Soda Ash) for the water treatment in Lagos Water Corporation | LSWC\G\NS\05/002/21 | LSWC\G\NCB\06/2019 | N/A |  | 48000000 | <50M | NS | Post | Prior | Plan | 2021-04-12 | 2021-04-26 | 2021-05-10 | 2021-06-07 | 2021-06-21 | 2021-07-05 | 2021-08-02 | 2021-08-05 |  | 2021-08-12 | 2021-08-26 | 2021-09-23
|  |  | LSWC/GDS/2016/02 | LSWC/GDS/2016/02 | [7 empty] | Actual
7 | Procurement of Water Treatment Chemicals (Sodium Hypochlorite (Hypo)/Calcium Hypochlorite (Briquettes) for the water treatment in Lagos Water Corporation | Procurement of Sodium Hypochlorite (Hypo)/Calcium Hypochlorite (Briquettes) for the water treatment in Lagos Water Corporation | LSWC\G\NS\05/003/21 | LSWC\G\NS\07/2019 | N/A |  | 8150000 | <10M | NS | Post | Post | Plan | 2021-04-15 | 2021-04-29 | 2021-05-13 | 2021-05-27 | 2021-06-10 | 2021-06-17 |  |  |  | 2021-06-24 | 2021-07-08 | 2021-07-22
|  |  | LSWC/GDS/2016/02 | LSWC/GDS/2016/02 | [7 empty] | Actual
8 | Procurement of Calcium Hypochlorite (HTH)/Chlorine Dioxide for the water treatment in Lagos Water Corporation | Procurement of Calcium Hypochlorite (HTH)/Chlorine Dioxide for the water treatment in Lagos Water Corporation | LSWC\G\NCB\06/21 | LSWC\G\NS\07/2019 | N/A |  | 153150000 | <500M | NCB | Post | Prior | Plan | 2021-03-17 | 2021-03-31 | 2021-04-14 | 2021-05-12 | 2021-05-26 | 2021-06-09 | 2021-07-07 | 2021-07-09 |  | 2021-07-16 | 2021-07-30 | 2021-08-27
|  |  | LSWC/GDS/2016/02 | LSWC/GDS/2016/02 | [7 empty] | Actual
9 | Procurement of Safety and Protective Wears and Equipment and Uniforms for all formatioms in Lagos Water Corporation | Procurement of Safety and Protective Wears and Equipment and Uniforms for all formatioms in Lagos Water Corporation | LSWC\G\NS\07/21 | LSWC\G\NS\09/2019 | N/A | - | 5000000 | <10M | NS | Post | Post | Plan | 2021-03-24 | 2021-04-07 | 2021-04-21 | 2021-05-05 | 2021-05-19 | 2021-05-26 |  |  |  | 2021-06-02 | 2021-06-16 | 2021-06-30
|  |  | LSWC/GDS/2016/02 | LSWC/GDS/2016/02 | [7 empty] | Actual
10 | Procurement of Variety of Pumps for Mini and Micro Waterworks of Lagos Water Corporation(Clearwater Pumps,aeration pumps,abstraction pumps etc) | Procurement of Pumps for various plants of Lagos Water Corporation | LSWC\G\NCB\08/21 | LSWC\G\NCB\10/2019 | N/A |  | 105000000 | <500M | NCB | Post | Prior | Plan | 2021-04-05 | 2021-04-19 | 2021-05-03 | 2021-05-31 | 2021-06-14 | 2021-06-28 | 2021-07-26 | 2021-07-28 |  | 2021-08-04 | 2021-08-18 | 2021-09-15
|  |  | LSWC/GDS/2016/02 | LSWC/GDS/2016/02 | [7 empty] | Actual
11 | Procurement of Pipes and Connection Materials for the Distribution Network Operations of Lagos Water Corporation | Procurement of Pipes and Connection Materials for the Distribution Network Operations of Lagos Water Corporation | LSWC\G\NCB\09/21 | LSWC\G\NCB\11/2019 | N/A |  | 55630000 | <100M | NCB | Post | Prior | Plan | 2021-04-12 | 2021-04-26 | 2021-05-10 | 2021-06-07 | 2021-06-21 | 2021-07-05 | 2021-08-02 | 2021-08-04 |  | 2021-08-11 | 2021-08-25 | 2021-09-22
|  |  | LSWC/GDS/2016/02 | LSWC/GDS/2016/02 | [7 empty] | Actual
12 | Procurement of Laboraroty Equipment and Reagents | Procurement of Laboraroty Equipment and Reagents | LSWC\G\NS\10/21 | LSWC\G\NS\13/2019 | N/A |  | 11824050 | <50M | NS | Post | Prior | Plan | 2021-04-06 | 2021-04-20 | 2021-05-04 | 2021-05-18 | 2021-06-01 | 2021-06-08 |  |  |  | 2021-06-15 | 2021-06-29 | 2021-07-13
|  |  | LSWC/GDS/2016/02 | LSWC/GDS/2016/02 | [7 empty] | Actual
13 | Procurement of Dosing Systems in Selected Treatment Plants of Lagos Water Corporation in Selected Stations | Procurement of Dosing Systems in Selected Treatment Plants of Lagos Water Corporation in Selected Stations | LSWC\G\NCB\11/21 | LSWC\G\NS\16/2019 | N/A |  | 95000000 | <100M | NCB | Post | Prior | Plan | 2021-04-14 | 2021-04-28 | 2021-05-12 | 2021-06-09 | 2021-06-23 | 2021-07-07 | 2021-08-04 | 2021-08-06 |  | 2021-08-13 | 2021-08-27 | 2021-09-24
|  |  | LSWC/GDS/2016/02 | LSWC/GDS/2016/02 | [7 empty] | Actual
14 | Procurement of Generating Set for Lagos Water Corporation |  | LSWC/G/NS/12/21 |  | N/A | 1 | 65000000 | <100M | NS | Post | Prior | Plan | 2021-05-11 | 44341 | 2021-06-08 | 2021-07-06 | 2021-07-20 | 2021-08-03 | 2021-08-31 | 2021-09-02 |  | 2021-09-09 | 2021-09-23 | 2021-10-21
Actual
| GRANDTOTAL | [5 empty] | 1773869484
Formulas:
PPA No Objection Date = [BIDDING PERIOD (DATES)]+14
Bid Invitation Date = [PPA No Objection Date]+14
Bid Closing & Opening = [Bid Invitation Date]+14
BID EVALUATION (DATES) = [Bid Closing & Opening]+14
PPA Issue Certificate of Compliance = [BID EVALUATION (DATES)]+7
Notification of Award = [PPA Issue Certificate of Compliance]+7
Contract Award = [Notification of Award]+14
Mobilization Advance Payment = [Contract Award]+14
APPROVAL = [PPA Issue Certificate of Compliance]+28

## Sheet1
| 4650 | 235000 | 1092750000
| 2000 | 4075 | 8150000
| 3000 | 51050 | 153150000
| 2800 | 2800 | 7840000
| 3200 | 15000 | 48000000
| Reagents | 11824050 | 11824050
1321714050
1050000000
Procurement of pumps |  | 30 | 3500000 | 105000000 | 238227720 | 123630000
Procuremnet of pipes |  | 1 | 37000000 | 37000000
Servicing of pumps |  | 45 | 527286 | 23727870
Maintence of Generators |  | 15 | 2900000 | 43500000
Connection Materials |  | 1 | 18630000 | 18630000
Lubricants |  | 1 | 3000000 | 3000000
Dosing Pumps |  | 20 | 4750000 | 95000000
Repair of electric pannels |  | 38 | 381575 | 14499850
Procurement of 1 no gen |  | 1 | 65000000 | 65000000
Maintence of Pipes |  | 1 | 35320000 | 35320000
440677720

## works
PROCUREMENT PLAN FOR WORKS
MINISTRY: LAGOS WATER CORPORATION
BUDGET YEAR: 2021
| CONTRACT IDENTIFICATION |  |  | BASIC DATA | [7 empty] | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
S/N | Contract Description |  | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification | Plan Vs Actual | Prior or Post Review | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[12 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Rehabilitation of Selected Pumps, Filter Beds, Dosing Systems at Adiyan and Iju Waterworks of Lagos Water Corporation | Rehabilitation of Selected Pumps, Filter Beds, Dosing Systems at Adiyan and Iju Waterworks of Lagos Water Corporation | LSWC\W\NCB\01/21 | N/A | 150000000 | <500M | NCB | BOQ | Post | Plan |  | 2021-05-04 | 2021-05-18 | 2021-06-01 | 2021-06-29 | 2021-07-13 | 2021-07-27 |  |  |  | 2021-08-03 | 2021-08-17 | 2021-09-14
[10 empty] | Actual | Prior
2 | Installation of new 11/33KVa Control Panel at Akute-Adiyan Raw Water Pumping Station | Installation of new 11/33KVa Control Panel at Akute-Adiyan Raw Water Pumping Station | LSWC\W\NS\02\21 | N/A | 25000000 | <50M | NS | BOQ | Post | Plan |  | 2021-07-07 | 2021-07-21 | 2021-08-04 | 2021-08-18 | 2021-09-01 | 2021-09-15 |  |  |  | 2021-09-22 | 2021-10-06 | 2021-10-20
[10 empty] | Actual | Prior
3 | Rehabililtation of 14Nos Existing Mini/Micro waterworks of Lagos Water Corporation | Upgrade of Epe Town water Supply Scheme | LSWC\W\NCB\03/21 | N/A | 200000000 | <500M | NCB | BOQ | Post | Plan |  | 2021-06-03 | 2021-06-17 | 2021-07-01 | 2021-07-29 | 2021-08-12 | 2021-08-26 |  |  |  | 2021-09-02 | 2021-09-16 | 2021-09-30
[10 empty] | Actual | Prior
4 | Renovation of Selected Staff Quarters and LSWC Zonal Offices within Lagos Metropolis | Renovation of Selected Staff Quarters and LSWC Zonal Offices within Lagos Metropolis | LSWC/W/NS\04/21 | N/A | 81650000 | <100M | NS | BOQ | Post | Plan |  | 2021-05-11 | 2021-05-25 | 2021-06-08 | 2021-07-06 | 2021-07-20 | 2021-08-03 |  |  |  | 2021-08-10 | 2021-08-24 | 2021-09-07
[10 empty] | Actual | Prior
5 | Renovation of LWC Infrastructure ( OFMM) | Maintenace of LWC Infrastructure ( OFMM) | LSWC\W\NCB\05\21 | N/A | 45000000 | <50M | NCB | BOQ | Post | Plan |  | 2021-05-05 | 2021-05-19 | 2021-06-02 | 2021-06-30 | 2021-07-14 | 2021-07-28 |  |  |  | 2021-08-04 | 2021-08-18 | 2021-09-01
[10 empty] | Actual | Prior
6 | Procurement and installation of various pumps at Iju & Adiyan Intakes and Adiyan Headworks to improve efficiency at Major Waterworks of Lagos Waster Corporation. | Procurement and installation of Neomatics valves Assembly, inclined plates Settler (IPS). Repairs of Clarifiers Control Panel | LSWC\W\ICB\06/21 | N/A | 597806085 | <1B | ICB | BOQ | Post | Plan |  | 2021-06-09 | 2021-06-23 | 2021-07-07 | 2021-08-18 | 2021-09-01 | 2021-09-15 |  |  |  | 2021-09-22 | 2021-10-06 | 2021-10-20
[10 empty] | Actual | Prior
7 | Rehabilitation of LWC Transmission Mains |  | LSWC\W-F\NS/07/21 | N/A | 35320000 | <50M | NS | BOQ | Post | Plan |  | 2021-03-08 | 2021-03-22 | 2021-04-05 | 2021-05-17 | 2021-05-31 | 2021-06-14 |  |  |  | 2021-06-21 | 2021-07-05 | 2021-07-19
[10 empty] | Actual | Prior
8 | Repair of Electrical Panels at 38 Mini/Micro waterworks of Lagos Water Corporation |  | LSWC\W\NS\08/21 | N/A | 14499850 | <50M | NS | BOQ | Post | Plan |  | 2021-03-15 | 2021-03-29 | 2021-04-12 | 2021-05-24 | 2021-06-07 | 2021-06-21 |  |  |  | 2021-06-28 | 2021-07-12 | 2021-07-26
[10 empty] | Actual | Prior
9 | Procurement and replacement of Mains Pipes (Iju and Adiyan Waterwoks) |  | LSWC\W\NCB\09\21 | N/A | 100000000 | <500M | NCB | BOQ | Post | Plan |  | 2021-06-22 | 2021-07-06 | 2021-07-20 | 2021-08-31 | 2021-09-14 | 2021-09-28 |  |  |  | 2021-10-05 | 2021-10-19 | 2021-11-02
[10 empty] | Actual | Prior
10 | Adiyan Phase II Construction (Bond Finance) |  | LSWC\W\ICB\10\21 | N/A | 1950000000 | <2B | ICB | BOQ | Post | Plan |  | 2021-03-02 | 2021-03-16 | 2021-03-30 | 2021-05-11 | 2021-05-25 | 2021-06-08 |  |  |  | 2021-06-15 | 2021-06-29 | 2021-07-13
[10 empty] | Actual | Prior
| GRANDTOTAL |  |  |  | 3199275935
Formulas:
PPA No Objection = [BIDDING PERIOD (DATES)]+14
Bid Invitation Date = [PPA No Objection]+14
Bid Closing & Opening = [Bid Invitation Date]+28
BID EVALUATION = [Bid Closing & Opening]+14
PPA Issue Certificate of Compliance = [BID EVALUATION]+14
Notification of Award = [PPA Issue Certificate of Compliance]+7
Contract Award = [Notification of Award]+14
Mobilization Advance Payment = [Contract Award]+28

## Works( Liabilities)
PROCUREMENT PLAN FOR WORKS (LIABILITIES)
MINISTRY: LAGOS WATER CORPORATION
BUDGET YEAR: 2021
| CONTRACT IDENTIFICATION |  |  | BASIC DATA | [7 empty] | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
S/N | Contract Description |  | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification | Plan Vs Actual | Prior or Post Review | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[12 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Outstanding Payment on 2NUWSRP World Bank Projects. (Liabilities) | Rehabilitation of Selected Pumps, Filter Beds, Dosing Systems at Adiyan and Iju Waterworks of Lagos Water Corporation | LSWC/2NUWSRP/WKS/IDA 40860-UNI | N/A | 124582545 |  |  |  | N/A | Plan |  | N/A
[10 empty] | Actual | Prior
1a | Procurement of Works for Rehabilitation of Raw Water Intake-Cum pumping station at Akute Lot 1 |  | LSWC/2NUWSRP/LS/WKS/OO7 | N/A | [5 empty] | Plan |  | N/A | [7 empty] | 51811825.03
[10 empty] | Actual | Prior
1b | Completion of Outstanding Works (Boreholes and Electro-Mechanical) at Alexandria Waterworks |  | LSWC/2NUWSRP/LS/WKS/102 | N/A | [5 empty] | Plan |  | N/A | [7 empty] | 9764320
[10 empty] | Actual | Prior
1c | Repair of Outstanding Snags at Alexandria Waterworks |  | LSWC/2NUWSRP/LS/WKS/103 | N/A | [5 empty] | Plan |  | N/A | [7 empty] | 2895262.5
[10 empty] | Actual | Prior
1d | Completion of Outstanding Works (Civil and Overhead Tank) at Alexandra Waterworks |  | LSWC/2NUWSRP/LS/WKS/108 | N/A | [5 empty] | Plan |  | N/A | [7 empty] | 25221724
[10 empty] | Actual | Prior
1e | Construction of 2MGD New Water Treatment Plant at Alexander Avenue Lot 3 |  | LSWC/2NUWSRP/LS/WKS/005 | N/A | [5 empty] | Plan |  | N/A | [7 empty] | 38070192.5
[10 empty] | Actual | Prior
2 | Outstanding Payment on Construction of 4MGD Ota-Ikosi Water Supply Scheme (Liabilities) |  | CON.12/2011/84 | N/A | 355197261 |  |  |  | N/A |  |  | N/A | [7 empty] | 4518093605.67
Prior
3 | Outstanding Payments on Construction of 15nos Mini\Micro Waterworks of Lagos Water Corporation (Liabilities) |  | LSWC/CON/WKS/01-15 | N/A | 166861018 |  |  |  | N/A |  |  | N/A
Prior
3a | Outstanding Payments on Construction of 15nos Mini\Micro Waterworks of Lagos Water Corporation, Ikate (Liabilities) |  | LSWC/WKS/001 | N/A |  |  |  |  | N/A |  |  | N/A | [7 empty] | 23000000
Prior
3b | Outstanding Payments on Construction of 15nos Mini\Micro Waterworks of Lagos Water Corporation, Badagry (Liabilities) |  | LSWC/CON/WKS/05 | N/A |  |  |  |  | N/A | [10 empty] | 49503049
Prior
3c | Outstanding Payments on Construction of 15nos Mini\Micro Waterworks of Lagos Water Corporation, Abule Egba/Oke Odo (Liabilities) |  | LSWC/CON/WKS/010 | N/A |  |  |  |  | N/A | [10 empty] | 32423163
Prior
3d | Outstanding Payments on Construction of 15nos Mini\Micro Waterworks of Lagos Water Corporation, Mosan Okunola (Liabilities) |  | LSWC/CON/WKS/011 | N/A |  |  |  |  | N/A | [10 empty] | 22734805
Prior
| GRANDTOTAL |  |  |  | 646640824

## Summary Page
SUMMARY
S/N | DESCRIPTION | BUDGET ESTIMATE
1 | GOODS | 1773869484
2 | WORKS | 3199275935
3 | WORKS (LIABILITIS) | 646640824
4 | NON CONSULTANCY | 59039870
5 | NON PROCURABLE ITEMS | 1407025274
| GRANDTOTAL | 7085851387