## Non-Proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: OFFICE OF DRAINAGE SERVICES
BUDGET YEAR: 2021
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TOTAL
1 | Provision for Casual workers Wages on Maintenance of Drains | MOE/ODS/NP/NM/001/2021 | 472764800 | Plan | 39397066.67 | 39397066.67 | 39397066.67 | 39397066.67 | 39397066.67 | 39397066.67 | 39397066.67 | 39397066.67 | 39397066.67 | 39397066.67 | 39397066.67 | 39397066.67 | 472764800
Actual
2 | Provision of Insurances/ Hazard Allowances for Casual/ EFAG Gang for out-station duties | MOE/ODS/NP/NM/002/2021 | 34611000 | Plan | 2884250 | 2884250 | 2884250 | 2884250 | 2884250 | 2884250 | 2884250 | 2884250 | 2884250 | 2884250 | 2884250 | 2884250 | 34611000
Actual
3 | Allowances for security guard on site for River guage station | MOE/ODS/NP/NM/003/2021 | 2880000 | Plan | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 2880000
Actual
4 | Armed Security backup for Demolition of Contraventing structure on drain alignment and for Enforcement Team | MOE/ODS/NP/NM/004/2021 | 63000000 | Plan | 5250000 | 5250000 | 5250000 | 5250000 | 5250000 | 5250000 | 5250000 | 5250000 | 5250000 | 5250000 | 5250000 | 5250000 | 63000000
Actual
5 | Up keep of Rain Guard Weather Station and Hydrological Out Station | MOE/ODS/NP/NM/005/2021 | 1000000 | Plan |  |  | 250000 |  |  | 250000 |  |  | 250000 |  |  | 250000 | 1000000
Actual
6 | Wages for Casual Workers (cleaners) | MOE/ODS/NP/NM/006/2021 | 1080000 | Plan | 90000 | 90000 | 90000 | 90000 | 90000 | 90000 | 90000 | 90000 | 90000 | 90000 | 90000 | 90000 | 1080000
Actual
7 | Payment of Water Quality test | MOE/ODS/NP/NM/007/2021 | 1500000 | Plan
Actual
8 | Subscription to various publications & journal from water & drainage related professional bodies | MOE/ODS/NP/NM/008/2021 | 1500000 | Plan
Actual
9 | Establishment of Technical Advisory committee and monitoring of the effects of the Ogun, Osun River flooding on Lagos & its environs | MOE/ODS/NP/NM/009/2021 | 10000000 | Plan |  |  | 2500000 |  |  | 2500000 |  |  | 2500000 |  |  | 2500000 | 10000000
Actual
| TOTAL |  | 588335800 | Plan
Actual

## Non-Proc Items 2
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: OFFICE OF DRAINAGE SERVICES
BUDGET YEAR: 2021
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TOTAL
10 | TRAVEL AND TRANSPORT | MOE/ODS/NP/NM/010/2021 | 10425000 | Plan | 868750 | 868750 | 868750 | 868750 | 868750 | 868750 | 868750 | 868750 | 868750 | 868750 | 868750 | 868750 | 10425000
Actual
11 | GENERAL UTILITY SERVICES | MOE/ODS/NP/NM/011/2021 | 1490400 | Plan | 124200 | 124200 | 124200 | 124200 | 124200 | 124200 | 124200 | 124200 | 124200 | 124200 | 124200 | 124200 | 1490400
Actual
12 | COMMITTEE EXPENSES | MOE/ODS/NP/NM/012/2021 | 1001600 | Plan |  |  | 250400 |  |  | 250400 |  |  | 250400 |  |  | 250400 | 1001600
Actual
13 | ANNUAL PRESS BRIEFING HONORARIUM | MOE/ODS/NP/NM/013/2021 | 1000000 | Plan | [6 empty] | 1000000 | [5 empty] | 1000000
Actual
14 | MONITORING & EVALUATION ALLOWANCE FOR H.C & P.S OFFICE | MOE/ODS/NP/NM/014/2021 | 5000000 | Plan |  |  | 1250000 |  |  | 1250000 |  |  | 1250000 |  |  | 1250000 | 5000000
Actual
15 | H.O.S CUP COMPETITION HONORARIUM | MOE/ODS/NP/NM/015/2021 | 500000 | Plan |  |  |  | 500000 | [8 empty] | 500000
Actual
16 | RENEWAL OF UTILITY VEHICLE LIECENCES | MOE/ODS/NP/NM/016/2021 | 1000000 | Plan |  |  | 250000 |  |  | 250000 |  |  | 250000 |  |  | 250000 | 1000000
Actual
17 | PROVISION FOR PERSONNEL BUDGET, P.M.B FOR CONFIRMATION, ADVANCEMENT AND PROMOTION AND LAST DAY IN OFFICE CEREMONY | MOE/ODS/NP/NM/017/2021 | 1000000 | Plan |  |  | 250000 |  |  | 250000 |  |  | 250000 |  |  | 250000 | 1000000
Actual
18 | RUNNING COST FOR S.A. TO H.C. ON DRAINAGE & WATER RESOURCES AND HIS MEMBERS OF STAFF | MOE/ODS/NP/NM/018/2021 | 6000000 | Plan | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 6000000
Actual
19 | SPECIAL EXPENSES FOR ACCOUNTS DEPT. | MOE/ODS/NP/NM/019/2021 | 3000000 | Plan |  |  | 750000 |  |  | 750000 |  |  | 750000 |  |  | 750000 | 3000000
Actual
20 | PROVISION FOR COURTSEY AND REACHOUT VISIT BY THE OFFICE OF THE SPECIAL ADVISER | MOE/ODS/NP/NM/020/2021 | 3400000 |  |  |  | 850000 |  |  | 850000 |  |  | 850000 |  |  | 850000 | 3400000
21 | Quarterly Stakeholders Meeting for Storm Water Management | MOE/ODS/NP/NM/021/2021 | 4000000
22 | PROVISION FOR SPECIAL DUTIES EXPENSES TOWARDS STORM WATER, DRAINAGE & WATER RESOURCES EXPENSES 7 ENVIRONMENTAL PARTNERSHIP PROJECTS | MOE/ODS/NP/NM/022/2021 | 7975000 | Plan |  |  | 1993750 |  |  | 1993750 |  |  | 1993750 |  |  | 1993750 | 4500000
Actual
| TOTAL |  | 45792000

## trg conf wsh
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: OFFICE OF DRAINAGE SERVICES
BUDGET YEAR: 2021
S/N | Description of Training/Workshop/ Conference | Package Number | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | Incidental and Transport expenses incurred on official training (PSSDC, Magodo & co) of Officers in the Ministry i.e Junior & Senior staff in all repective cadres in all departments including Officers in the HC, SA & PS Offices. | MOE/ODS/S-WTC/SS/001/21 |  |  |  | Plan |  |  |  |  | 1500000
Actual
2 | Conference & Seminars for HC office | MOE/ODS/S-WTC/SS/002/21 |  | 5 |  | Plan |  |  |  |  | 1800000
Actual
3 | Conference & Seminars for SA office | MOE/ODS/S-WTC/SS/003/21 |  | 4 |  | Plan |  |  |  |  | 1500000
Actual
4 | Conference & Seminars for PS office | MOE/ODS/S-WTC/SS/004/21 |  | 5 |  | Plan |  |  |  |  | 1500000
Actual
5 | Conference & Seminar for Drainage Construction/Dredging Dept. | MOE/ODS/S-WTC/SS/005/21 |  | 25 |  | Plan |  |  |  |  | 2500000
Actual
6 | Conference & Seminars for Drainage Maintenance Dept | MOE/ODS/S-WTC/SS/006/21 |  | 13 |  | Plan |  |  |  |  | 2500000
Actual
7 | Conference & Seminars for Project Planning & Design Dept. | MOE/ODS/S-WTC/SS/007/21 |  | 10 |  | Plan |  |  |  |  | 2300000
Actual
8 | Conference & Seminar for Drainage Enforcement & Compliance Dept. | MOE/ODS/S-WTC/SS/008/21 |  | 5 |  | Plan |  |  |  |  | 2300000
Actual
9 | Conference & Seminars for Water Resources Dept. | MOE/ODS/S-WTC/SS/009/21 |  | 17 |  | Plan |  |  |  |  | 2500000
Actual
10 | Conference & Seminars for Accounts Dept. | MOE/ODS/S-WTC/SS/010/21 |  | 7 |  | Plan |  |  |  |  | 1500000
Actual
11 | Cowslo for officers & Wives of Officers | MOE/ODS/S-WTC/SS/011/21 |  | 20 |  | Plan |  |  |  |  | 1700000
Actual
12 | Provision for Co-participation of House of Assembly Members in Training, Conferences and Seminars | MOE/ODS/S-WTC/SS/012/21 |  |  |  | Plan |  |  |  |  | 5000000
Actual
13 | Conferences & Seminars for Procurement Unit | MOE/ODS/S-WTC/SS/013/21 |  | 2 |  | Plan |  |  |  |  | 1500000
Actual
14 | CONFERENCES & SEMINARS FOR PLANNING RESEARCH & STATISTICS UNIT | MOE/ODS/S-WTC/SS/014/21 |  | 2 |  | Plan |  |  |  |  | 1500000
Actual
15 | CONFERENCES & SEMINARS FOR PUBLIC RELATION UNIT | MOE/ODS/S-WTC/SS/015/21 |  | 3 |  | Plan |  |  |  |  | 1000000
Actual
16 | CONFERENCES & SEMINARS FOR ICT UNIT | MOE/ODS/S-WTC/SS/016/21 |  | 3 |  | Plan |  |  |  |  | 1000000
Actual
17 | ENVIRONMENTAL MANAGEMENT EXCHANGE & TRAINING PROGRAMS (LOGISTICS & BONDING) | MOE/ODS/S-WTC/SS/017/21 |  | 3 |  | Plan |  |  |  |  | 3000000
Actual
18 | CONFERENCES & SEMINARS FOR AUDIT UNIT | MOE/ODS/S-WTC/SS/018/21 |  | 1 |  | Plan |  |  |  |  | 850000
Actual
| Professional development and modern advocacy on modern trend Stormwater Management for Health, Safety and Environmental sustainability, Seminars & Honorariums Honorariums (Training expenses for casual workers(engineers)) | [9 empty] | 10000000
19 | Conference & Seminars for Admin and HR. Dept. | MOE/ODS/S-WTC/SS/019/21 |  | 10 |  | Plan |  |  |  |  | 2000000
Actual
| TOTAL |  |  |  |  | Plan |  |  |  |  | 47450000
Actual

## non-cons
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY:
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY: OFFICE OF DRAINAGE SERVICES & WATER RESOURCES
BUDGET YEAR: 2021
Contract Description | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
| Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
MOTOR VEHICLE REPAIRS & MAINTENANCE | MOE/ODS/S-NC-F/NS/001/2021 |  |  | 7860000 | <10,000,000 | National Shopping | Plan | Post | Post | 17/2/2021 | N.A. | 21/2/2021 | 28/2/2021 | 2021-03-03 | 2021-05-03 | N.A. | Plan | 28/3/2021 | 30/3/2021 |  | 20/4/2021 | 2021-04-05 | 14/12/2021 | 18/12/2021
[7 empty] | Actual | [9 empty] | Actual
MAINTENANCE & REPAIR OF PLANTS & MACHINERY | MOE/ODS/S-NC-F/NS/002/2021 |  |  | 40590000 | <50,000,000 | National Shopping | Plan | Post | Prior | 17/2/2021 | 19/2/2021 | 21/2/2021 | 28/2/2021 | 2021-03-03 | 2021-05-03 | 2021-07-03 | Plan | 28/3/2021 | 30/3/2021 |  | 20/4/2021 | 2021-04-05 | 14/12/2021 | 18/12/2021
[7 empty] | Actual | [9 empty] | Actual
MAINT.& REPAIRS OF OFFICE EQUIPMENT | MOE/ODS/S-NC-F/NS/003/2021 |  |  | 4438000 | <10,000,000 | National Shopping | Plan | Post | Post | 18/2/2021 | N.A. | 24/2/2021 | 2021-02-03 | 2021-05-03 | 2021-09-03 | N.A. | Plan | 2021-01-04 | 2021-03-04 |  | 24/4/2021 | 2021-08-05 | 16/12/2021 | 21/12/2021
[7 empty] | Actual | [9 empty] | Actual
Printing of Letter Head paper, Contravention Notices booklet, Photographs, banners, reports and others | MOE/ODS/S-NC-F/NS/006/2021 |  |  | 5309544 | <10,000,000 | National Shopping | Plan | Post | Post | 24/2/2021 | N.A. | 2021-02-03 | 2021-09-03 | 2021-12-03 | 16/3/2021 | N.A. | Plan | 2021-08-04 | 2021-09-04 |  | 30/4/2021 | 14/5/2021 | 18/12/2021 | 23/12/2021
[7 empty] | Actual | [9 empty] | Actual
Office Retreat | MOE/ODS/S-NC/NS/007/2021 |  |  | 10000000 | <50,000,000 | National Shopping | Plan | Post | Prior | 24/2/2021 | N.A. | 2021-02-03 | 2021-09-03 | 2021-12-03 | 16/3/2021 | N.A. | Plan | 2021-08-04 | 2021-09-04 |  | 30/4/2021 | 14/5/2021 | 18/12/2021 | 23/12/2021
[7 empty] | Actual | [9 empty] | Actual
Stakeholders Summit on Integrated Water Resource Management in Lagos State | MOE/ODS/S-NC/NS/008/2021 |  |  | 15000000 | <50,000,000 | National Shopping | Plan | Post | Prior | 17/2/2021 | 19/2/2021 | 21/2/2021 | 28/2/2021 | 2021-03-03 | 2021-05-03 | 2021-07-03 | Plan | 28/3/2021 | 30/3/2021 |  | 20/4/2021 | 2021-04-05 | 14/12/2021 | 18/12/2021
[7 empty] | Actual | [9 empty] | Actual
Year 2020 Annual Water Day Symposium and Other Celebrations | MOE/ODS/S-NC/NS/009/2021 |  |  | 10000000 | <50,000,000 | National Shopping | Plan | Post | Prior | 17/2/2021 | 19/2/2021 | 21/2/2021 | 28/2/2021 | 2021-03-03 | 2021-05-03 | 2021-07-03 | Plan | 28/3/2021 | 30/3/2021 |  | 20/4/2021 | 2021-04-05 | 14/12/2021 | 18/12/2021
[7 empty] | Actual | [9 empty] | Actual
Creation of Awareness on Water Supply Sanitation & Hygeine (WASH) with the Stakeholders in Local Govt. areas along the 5 Divisions | MOE/ODS/S-NC/NS/010/2021 |  |  | 20000000 | <50,000,000 | National Shopping | Plan | Post | Prior | 17/2/2021 | 19/2/2021 | 21/2/2021 | 28/2/2021 | 2021-03-03 | 2021-05-03 | 2021-07-03 | Plan | 28/3/2021 | 30/3/2021 |  | 20/4/2021 | 2021-04-05 | 14/12/2021 | 14/12/2021
[7 empty] | Actual | [9 empty] | Actual
Annual Ministerial Press Briefing | MOE/ODS/S-NC/NS/011/2021 |  |  | 4000000 | <10,000,000 | National Shopping | Plan | Post | Post | 17/2/2021 | 19/2/2021 | 21/2/2021 | 28/2/2021 | 2021-03-03 | 2021-05-03 | 2021-07-03 | Plan | 28/3/2021 | 30/3/2021 |  | 20/4/2021 | 2021-04-05 | 14/12/2021 | 18/12/2021
[7 empty] | Actual | [9 empty] | Actual
Installation of automated river gauging system in Lagos Lagoon,Osun river & Badagry creek | MOE/ODS/S-NC/NS/012/2021 |  |  | 45000000 | <50,000,000 | National Shopping | Plan | Post | Prior | 17/2/2021 | 19/2/2021 | 21/2/2021 | 28/2/2021 | 2021-03-03 | 2021-05-03 | 2021-07-03 | Plan | 28/3/2021 | 30/3/2021 |  | 20/4/2021 | 2021-04-05 | 14/12/2021 | 18/12/2021
[7 empty] | Actual | [9 empty] | Actual
WAGES FOR SECURITY PERSONNEL | MOE/ODS/S-NC/NS/013/2021 |  |  | 1500000 | <10,000,000 | National Shopping | Plan | Post | Post | 17/2/2021 | 19/2/2021 | 21/2/2021 | 28/2/2021 | 2021-03-03 | 2021-05-03 | 2021-07-03 | Plan | 28/3/2021 | 30/3/2021 |  | 20/4/2021 | 2021-04-05 | 14/12/2021 | 18/12/2021
[7 empty] | Actual | [9 empty] | Actual
Sensitization/Awareness Campaign & Stakeholder's Forum | MOE/ODS/S-NC/NS/0142021 |  |  | 30000000 | <50,000,000 | National Shopping | Plan | Post | Prior | 17/2/2021 | 19/2/2021 | 21/2/2021 | 28/2/2021 | 2021-03-03 | 2021-05-03 | 2021-07-03 | Plan | 28/3/2021 | 30/3/2021 |  | 20/4/2021 | 2021-04-05 | 14/12/2021 | 18/12/2021
[7 empty] | Actual | [9 empty] | Actual
TOTAL |  |  |  | 185837544

## consultancy
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/ AGENCY: OFFICE OF DRAINAGE SERVICES & WATER RESOURCES
BUDGET YEAR: 2021
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[5 empty] | 0 |  | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
1 | Lagos State Drainage Master Plan for Secondary Drainage Systems (Collector Drain MasterPlan) in (6) six LGA(Agege, Amuwo-odofin, Ikorodu, Mushin, Ojo, Apapa). | MOE/ODS/S-C/QCBS/001/2021 | Quality Cost Based Selection | Time Based | 370000000 | Prior | Plan | 18/2/2021 | 21/2/2021 | 28/2/2021 | 13/3/2021 | 17/3/2021 | 19/3/2021 | 2021-09-04 | 16/4/2021 | 20/4/2021 | 23/4/2021 | 28/4/2021 | 4/5/2021 | 18/5/2021 | 19/5/2021 |  | 22/5/2021 | 29/5/2021 | 12/6/2021 | 14/9/2021 | 28/9/2021
Actual
2 | Isheri North Flood Mitigation Plan Study | MOE/ODS/S-C/QCBS/002/2021 | Quality Cost Based Selection | Time Based | 110000000 | Prior | Plan | 18/2/2021 | 21/2/2021 | 28/2/2021 | 13/3/2021 | 17/3/2021 | 19/3/2021 | 2021-09-04 | 16/4/2021 | 20/4/2021 | 23/4/2021 | 28/4/2021 | 4/5/2021 | 18/5/2021 | 19/5/2021 |  | 22/5/2021 | 29/5/2021 | 12/6/2021 | 14/9/2021 | 28/9/2021
Actual
3 | Establishment of Flood forecasting system with 5 Nos of Weather stations (PHASE 1) | MOE/ODS/S-C/CQ/001/2021 | Consultant Qualification | Time Based | 95000000 | Prior | Plan | 18/2/2021 | 21/2/2021 | 28/2/2021 | 13/3/2021 | 17/3/2021 | 19/3/2021 | 2021-09-04 | 16/4/2021 | 20/4/2021 | 23/4/2021 | 28/4/2021 | 4/5/2021 | 18/5/2021 | 19/5/2021 |  | 22/5/2021 | 29/5/2021 | 12/6/2021 | 14/9/2021 | 28/9/2021
Actual
4 | Evironmental Study for Water Resources Management, i.e Environmental studies of surface water in Lagos & Studies of waste water discharges into the environment. | MOE/ODS/S-C/QBS/001/2021 | Quality Based Selection | Time Based | 35000000 | Prior | Plan | 17/2/2021 | 20/2/2021 | 27/2/2021 | 2021-12-03 | 16/3/2021 | 18/3/2021 | 2021-08-04 | 15/4/2021 | 17/4/2021 | 22/4/2021 | 27/4/2021 | 1/5/2021 | 15/5/2021 | 18/5/2021 |  | 21/5/2021 | 28/5/2021 | 11/6/2021 | 11/8/2021 | 18/8/2021
Actual
5 | Drainage Clearance Geo Data Archiving | MOE/ODS/S-C/LCS/001/2021 | Least Cost Selection | Time Based | 20000000 | Prior | Plan | 25/2/2021 | 28/2/2021 | 2021-06-03 | 20/3/2021 | 24/3/2021 | 26/3/2021 | 16/4/2021 | 23/4/2021 | 27/4/2021 | 30/4/2021 | 5/5/2021 | 11/5/2021 | 29/5/2021 | 2021-01-06 |  | 2021-04-06 | 2021-11-06 | 25/6/2021 | 25/9/2021 | 2021-02-10
Actual
6 | Infrastructural Development Plan for Water supply, sanitation & hygeine (WASH) programmes | MOE/ODS/S-C/QCBS/002/2021 | Quality Cost Based Selection | Time Based | 210000000 | Prior | Plan | 17/2/2021 | 20/2/2021 | 27/2/2021 | 2021-12-03 | 16/3/2021 | 18/3/2021 | 2021-08-04 | 15/4/2021 | 17/4/2021 | 22/4/2021 | 27/4/2021 | 1/5/2021 | 15/5/2021 | 18/5/2021 |  | 21/5/2021 | 28/5/2021 | 11/6/2021 | 11/8/2021 | 18/8/2021
Actual
| TOTAL |  |  |  | 840000000

## goods
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: OFFICE OF DRAINAGE SERVICES & WATER RESOURCES
BUDGET YEAR: 2021
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Procurement of Vehicles |  |  |  | 349000000 |  |  |  |  | Plan
Actual
| Procurement of operational vehicle (4x4 ) & 4 Wheel Pickups | MOE/ODS/G/NCB/001-01/2021 | 1 |  | 130000000 | <500,000,000 | National Competitive Bidding | Post | Prior | Plan | 17/2/2021 | 19/2/2021 | 21/2/2021 | 28/2/2021 | 2021-03-03 | 2021-05-03 | 19/3/2021 | 20/3/2021 |  | 27/3/2021 | 2021-03-04 | 17/4/2021 | 2021-01-05 | 2021-01-05
Actual
| Procurement of Tipper Trucks, Light Trucks, Cart Pulling Truck & Track Loader | MOE/ODS/G/NCB/001-02/2021 | 2 |  | 219000000 | <500,000,000 | National Competitive Bidding | Post | Prior | Plan | 17/2/2021 | 19/2/2021 | 21/2/2021 | 28/2/2021 | 2021-03-03 | 2021-05-03 | 19/3/2021 | 20/3/2021 |  | 27/3/2021 | 2021-03-04 | 17/4/2021 | 2021-01-05 | 2021-01-05
Actual
2 | Procuement of Specialized Equipment |  |  |  | 751000000 |  |  |  |  | Plan
Actual
| Procurement of Swamp Buggy | MOE/ODS/G/NCB/002-01/2021 | 1 |  | 550000000 | >500,000,000 | International Competitive Bidding | Post | Prior | Plan | 24/2/2021 | 26/2/2021 | 2021-02-03 | 2021-09-03 | 2021-12-03 | 16/3/2021 | 30/3/2021 | 31/3/2021 |  | 2021-07-04 | 14/4/2021 | 28/4/2021 | 2021-12-05 | 2021-12-05
Actual
| Procurement of Truck mounted Pressure Washing Machine, Backhoe, Refuse Compactor, Skid Steer Loader, Truck mounted suction/flushing machine & Mini Excavator | MOE/ODS/G/NCB/002-02/2021 | 2 |  | 201000000 | <500,000,000 | National Competitive Bidding | Post | Prior | Plan | 24/2/2021 | 26/2/2021 | 2021-02-03 | 2021-09-03 | 2021-12-03 | 16/3/2021 | 30/3/2021 | 31/3/2021 |  | 2021-07-04 | 14/4/2021 | 28/4/2021 | 2021-12-05 | 2021-12-05
Actual
3 | Procurement of Fuel | MOE/ODS/G-F/NCB/003/2021 |  |  | 214860000 | <500,000,000 | National Competitive Bidding | Post | Prior | Plan | 17/2/2021 | 19/2/2021 | 21/2/2021 | 28/2/2021 | 2021-03-03 | 2021-05-03 | 19/3/2021 | 20/3/2021 |  | 27/3/2021 | 2021-03-04 | 17/4/2021 | 2021-01-05 | 2021-01-05
Actual
| TOTAL |  |  |  | 1314860000

## goods 2
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: OFFICE OF DRAINAGE SERVICES & WATER RESOURCES
BUDGET YEAR: 2021
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
4 | Procurement of Photo Mosaic Map, Arial Contour Maps, Street Maps and others | MOE/ODS/G/NS/002/2021 |  |  | 20000000 | <50,000,000 | National Shopping | Post | Prior | Plan | 2021-03-03 | 2021-06-03 | 13/3/2021 | 27/3/2021 | 2021-02-04 | 2021-06-04 | 20/4/2021 | 21/4/2021 |  | 28/4/2021 | 2021-05-05 | 19/5/2021 | 2021-09-06 | 2021-09-06
Actual
5 | PROCUREMENT OF SOLAR INVERTER | MOE/ODS/G/NS/003/2021 |  | 20 | 20000000 | <50,000,000 | National Shopping | Post | Prior | Plan | 2021-06-03 | 2021-09-03 | 16/3/2021 | 30/3/2021 | 2021-03-04 | 2021-07-04 | 21/4/2021 | 22/4/2021 |  | 29/4/2021 | 2021-06-05 | 20/5/2021 | 17/5/2021 | 22/5/2021
Actual
6 | Procurement of Tools (Wheelbarrows, shovels, headpans etc) for DMO/EFAG & Enforcement Team | MOE/ODS/G/NS/004/2021 |  |  | 10000000 | <50,000,000 | National Shopping | Post | Post | Plan | 2021-06-03 | N.A. | 16/3/2021 | 30/3/2021 | 2021-03-04 | N .A. | 21/4/2021 | 22/4/2021 |  | 29/4/2021 | 2021-06-05 | 20/5/2021 | 17/5/2021 | 22/5/2021
Actual
7 | Procurement of Uniform and Protectives (Safari Jackets, shirt & Trouser; Rain Coats; Boots; Helments; Hand gloves & Nose Mask; Reflective Jackets; Site Shoes etc. | MOE/ODS/G/NS/005/2021 |  |  | 29842475 | <50,000,000 | National Shopping | Post | Prior | Plan | 2021-06-03 | N.A. | 16/3/2021 | 30/3/2021 | 2021-03-04 | N.A. | 21/4/2021 | 22/4/2021 |  | 29/4/2021 | 2021-06-05 | 20/5/2021 | 17/5/2021 | 22/5/2021
Actual
8 | Procurement of Stationery | MOE/ODS/G-F/NS/006/2021 |  |  | 3325000 | <10,000,000 | National Shopping | Post | Post | Plan | 17/2/2021 | N.A. | 21/2/2021 | 28/2/2021 | 2021-03-03 | N.A. | 19/3/2021 | 20/3/2021 |  | 27/3/2021 | 2021-03-04 | 17/4/2021 | 2021-01-05 | 2021-01-05
Actual
9 | Procurement of First Aid kits for zonal offices | MOE/ODS/G/NS/007/2021 |  | 20 | 6162000 | <10,000,000 | National Shopping | Post | Post | Plan | 17/2/2021 | 19/2/2021 | 21/2/2021 | 28/2/2021 | 2021-03-03 | 2021-05-03 | 19/3/2021 | 20/3/2021 |  | 27/3/2021 | 2021-03-04 | 17/4/2021 | 2021-01-05 | 2021-01-05
Actual
10 | Procurement of Office Cleaning Materials | MOE/ODS/G-F/NS/008/2021 |  |  | 1000000 | <10,000,000 | National Shopping | Post | Post |  | 17/2/2021 | N.A. | 21/2/2021 | 28/2/2021 | 2021-03-03 | N.A. | 19/3/2021 | 20/3/2021 |  | 27/3/2021 | 2021-03-04 | 17/4/2021 | 2021-01-05 | 2021-01-05
11 | Procurement of Specialised Items by Various Units | MOE/ODS/G-F/NS/009/2021 |  |  | 15150000 | <50,000,000 | National Shopping | Post | Prior |  | 17/2/2021 | 19/2/2021 | 21/2/2021 | 28/2/2021 | 2021-03-03 | 2021-05-03 | 19/3/2021 | 20/3/2021 |  | 27/3/2021 | 2021-03-04 | 17/4/2021 | 2021-01-05 | 2021-01-05
12 | Procurement Management Information System (Provision for: Flash drives, APC surge, USB printer cable, VGA cable and cards, USB mouse, Keyboard, Printers, Toners, External Hard drive, CD ROM, RAM DDR3, CD/DUD Disc, Power pack, Clipping tools, Law Testers, Extension Boxes, External DUD ROM | MOE/ODS/G-F/NS/010/2021 |  |  | 22000000 | <50,000,000 | National Shopping | Post | Prior | Plan | 17/2/2021 | 19/2/2021 | 21/2/2021 | 28/2/2021 | 2021-03-03 | 2021-05-03 | 19/3/2021 | 20/3/2021 |  | 27/3/2021 | 2021-03-04 | 17/4/2021 | 2021-01-05 | 2021-01-05
Actual
| TOTAL |  |  |  | 127479475

## works 1
PROCUREMENT PLAN FOR WORKS
MINISTRY: OFFICE OF DRAINAGE SERVICES & WATER RESOURCES
BUDGET YEAR: 2021
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification | Prior-or Post Review |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[12 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Maintenance of Primary Channels in the 20 LGA in Lagos State | MOE/ODS/W/DL/001/2021 |  | 1000000000 | >500,000,000 | Direct Labour | BOQ | Post | Prior | Plan | Prior | 17/2/2021 | 20/2/2021 | 27/2/2021 | 2021-12-03 | 19/3/2021 | 26/3/2021 | 2021-09-04 | 10/4/2021 |  | 17/4/2021 | 24/4/2021 | 2021-08-05 | 2021-08-07 | 22/7/2021
Actual
2 | Restoration and Protection of R.O.W of System |  |  | 1000000000 | [5 empty] | Plan | Prior
Actual
| Restoration and Protection of R.O.W of System 1A (Odo Iya Alaro Channel) Storm Water Channel | MOE/ODS/W/NCB/002-01/2021 | 1 | 340000000 | <500,000,000 | National Competitive Bidding | BOQ | Post | Prior | Plan | Prior | 2021-03-03 | 2021-10-03 | 17/3/2021 | 31/3/2021 | 2021-07-04 | 14/4/2021 | 28/4/2021 | 29/4/2021 |  | 2021-06-05 | 13/5/2021 | 20/5/2021 | 20/7/2021 | 2021-03-08
Actual
| Restoration and Protection of R.O.W of System 1C (Ketu Alapere Channel) Storm Water Channel | MOE/ODS/W/NCB/002-02/2021 | 2 | 92000000 | <500,000,000 | National Competitive Bidding | BOQ | Post | Prior | Plan | Prior | 2021-03-03 | 2021-10-03 | 17/3/2021 | 31/3/2021 | 2021-07-04 | 14/4/2021 | 28/4/2021 | 29/4/2021 |  | 2021-06-05 | 13/5/2021 | 20/5/2021 | 20/7/2021 | 2021-03-08
Actual
| Restoration and Protection of R.O.W of System 5 (Irede Satellite) Storm Water Channel | MOE/ODS/W/NCB/002-03/2021 | 3 | 84400000 | <500,000,000 | National Competitive Bidding | BOQ | Post | Prior | Plan | Prior | 2021-03-03 | 2021-10-03 | 17/3/2021 | 31/3/2021 | 2021-07-04 | 14/4/2021 | 28/4/2021 | 29/4/2021 |  | 2021-06-05 | 13/5/2021 | 20/5/2021 | 20/7/2021 | 2021-03-08
Actual
| Restoration and Protection of R.O.W of System 9C (Bucknor Channel) Storm Water Channel | MOE/ODS/W/NCB/002-04/2021 | 4 | 77000000 | <500,000,000 | National Competitive Bidding | BOQ | Post | Prior | Plan |  | 2021-03-03 | 2021-10-03 | 17/3/2021 | 31/3/2021 | 2021-07-04 | 14/4/2021 | 28/4/2021 | 29/4/2021 |  | 2021-06-05 | 13/5/2021 | 20/5/2021 | 20/7/2021 | 2021-03-08
Actual
| Restoration and Protection of R.O.W of System 12C (Iju Ogundimu Channel) Storm Water Channel. | MOE/ODS/W/NCB/002-05/2021 | 5 | 65400000 | <500,000,000 | National Competitive Bidding | BOQ | Post | Prior |  |  | 2021-03-03 | 2021-10-03 | 17/3/2021 | 31/3/2021 | 2021-07-04 | 14/4/2021 | 28/4/2021 | 29/4/2021 |  | 2021-06-05 | 13/5/2021 | 20/5/2021 | 20/7/2021 | 2021-03-08
| Restoration and Protection of R.O.W of System 40 (Ikota Stream) Storm Water Channel | MOE/ODS/W/NCB/002-06/2021 | 6 | 172200000 | <500,000,000 | National Competitive Bidding | BOQ | Post | Prior |  |  | 2021-03-03 | 2021-10-03 | 17/3/2021 | 31/3/2021 | 2021-07-04 | 14/4/2021 | 28/4/2021 | 29/4/2021 |  | 2021-06-05 | 13/5/2021 | 20/5/2021 | 20/7/2021 | 2021-03-08
| Restoration and Protection of R.O.W of System 50 (Eputu Channel) Storm Water Channel | MOE/ODS/W/NCB/002-07/2021 | 7 | 77000000 | <500,000,000 | National Competitive Bidding | BOQ | Post | Prior |  |  | 2021-03-03 | 2021-10-03 | 17/3/2021 | 31/3/2021 | 2021-07-04 | 14/4/2021 | 28/4/2021 | 29/4/2021 |  | 2021-06-05 | 13/5/2021 | 20/5/2021 | 20/7/2021 | 2021-03-08
| Restoration and Protection of R.O.W of System 105 (Igbogbo Solebo Ajewo Channel) Storm Water Channel | MOE/ODS/W/NCB/002-08/2021 | 8 | 92000000 | <500,000,000 | National Competitive Bidding | BOQ | Post | Prior |  |  | 2021-03-03 | 2021-10-03 | 17/3/2021 | 31/3/2021 | 2021-07-04 | 14/4/2021 | 28/4/2021 | 29/4/2021 |  | 2021-06-05 | 13/5/2021 | 20/5/2021 | 20/7/2021 | 2021-03-08
3 | Construction/Deflooding of Drainages |  |  | 3800000000 | [5 empty] | Plan | Prior
Actual
| CONSTRUCTION OF DRAIN AT SHOSANYA ALABATA STREET, IJEGUN,ALIMOSHO | MOE/ODS/W/NCB/003-01/2021 | 1 | 87219286.31 | <500,000,000 | National Competitive Bidding | BOQ | Post | Prior | Plan | Prior | 20/2/2021 | 2021-05-03 | 19/3/2021 | 2021-02-04 | 16/4/2021 | 30/4/2021 | 14/4/2021 | 15/4/2021 |  | 22/5/2021 | 2021-05-05 | 19/5/2021 | 19/8/2021 | 2021-02-09
Actual
| CONSTRUCTION OF DRAIN AT SHASHA SENIOR HIGH SCHOOL, ALIMOSHO | MOE/ODS/W/NCB/003-02/2021 | 2 | 113300000 | <500,000,000 | National Competitive Bidding | BOQ | Post | Prior | Plan | Prior | 20/2/2021 | 2021-05-03 | 19/3/2021 | 2021-02-04 | 16/4/2021 | 30/4/2021 | 14/4/2021 | 15/4/2021 |  | 22/5/2021 | 2021-05-05 | 19/5/2021 | 19/8/2021 | 2021-02-09
Actual
| CONSTRUCTION OF ARIDA COLLECTOR DRAIN, ALIMOSHO | MOE/ODS/W/NCB/003-03/2021 | 3 | 172185682.3 | <500,000,000 | National Competitive Bidding | BOQ | Post | Prior | Plan | Prior | 20/2/2021 | 2021-05-03 | 19/3/2021 | 2021-02-04 | 16/4/2021 | 30/4/2021 | 14/4/2021 | 15/4/2021 |  | 22/5/2021 | 2021-05-05 | 19/5/2021 | 19/8/2021 | 2021-02-09
Actual
| CONSTRUCTION OF LOW COST HOUSING ESTATE COLLECTOR DRAIN, FESTAC EXTENSION, MILE 2, AMUWO ODOFIN | MOE/ODS/W/NCB/003-04/2021 | 4 | 99831950.15 | <500,000,000 | National Competitive Bidding | BOQ | Post | Prior | Plan | Prior | 20/2/2021 | 2021-05-03 | 19/3/2021 | 2021-02-04 | 16/4/2021 | 30/4/2021 | 14/4/2021 | 15/4/2021 |  | 22/5/2021 | 2021-05-05 | 19/5/2021 | 19/8/2021 | 2021-02-09
Actual

## works 2
PROCUREMENT PLAN FOR WORKS
MINISTRY: OFFICE OF DRAINAGE SERVICES & WATER RESOURCES
BUDGET YEAR: 2021
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification | Prior-or Post Review |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[12 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
| CONSTRUCTION OF DRAIN WITHIN GBARA JUNIOR SECONDARY SCHOOL, ETI OSA | MOE/ODS/W/NS/003-05/2021 | 5 | N33,540,887.71 | <50,000,000 | National Shopping | BOQ | Post | Prior | Plan | Prior | 20/2/2021 | 2021-05-03 | 19/3/2021 | 2021-02-04 | 16/4/2021 | 30/4/2021 | 14/4/2021 | 15/4/2021 |  | 22/5/2021 | 2021-05-05 | 19/5/2021 | 19/8/2021 | 2021-02-09
Actual
| LINING OF PEACEVILLE-GREENVILLE COLLECTOR DRAIN,ETI OSA | MOE/ODS/W/ NCB/003-06/2021 | 6 | N265,023,747.72 | <500,000,000 | National Competitive Bidding | BOQ | Post | Prior | Plan | Prior | 20/2/2021 | 2021-05-03 | 19/3/2021 | 2021-02-04 | 16/4/2021 | 30/4/2021 | 14/4/2021 | 15/4/2021 |  | 22/5/2021 | 2021-05-05 | 19/5/2021 | 19/8/2021 | 2021-02-09
Actual
| CONSTRUCTION OF DRAINAGE NETWORKS WITHIN TEMIDIRE COMMUNITY, POKA, EPE LGA | MOE/ODS/W/NCB/003-07/2021 | 7 | N103,418,424.66 | <500,000,000 | National Competitive Bidding | BOQ | Post | Prior | Plan | Prior | 20/2/2021 | 2021-05-03 | 19/3/2021 | 2021-02-04 | 16/4/2021 | 30/4/2021 | 14/4/2021 | 15/4/2021 |  | 22/5/2021 | 2021-05-05 | 19/5/2021 | 19/8/2021 | 2021-02-09
Actual
| CONSTRUCTION OF KAJOLA DRAINAGE CHANNEL, IBEJU LEKKI | MOE/ODS/W/NCB/003-08/2021 | 8 | N327,962,940.20 | <500,000,000 | National Competitive Bidding | BOQ | Post | Prior | Plan | Prior | 20/2/2021 | 2021-05-03 | 19/3/2021 | 2021-02-04 | 16/4/2021 | 30/4/2021 | 14/4/2021 | 15/4/2021 |  | 22/5/2021 | 2021-05-05 | 19/5/2021 | 19/8/2021 | 2021-02-09
Actual
| CONSTRUCTION OF ELEKO ROAD COLLECTOR DRAIN IBEJU LEKKI | MOE/ODS/W/NCB/003-09/2021 | 9 | N176,905,204.10 | <500,000,000 | National Competitive Bidding | BOQ | Post | Prior | Plan | Prior | 20/2/2021 | 2021-05-03 | 19/3/2021 | 2021-02-04 | 16/4/2021 | 30/4/2021 | 14/4/2021 | 15/4/2021 |  | 22/5/2021 | 2021-05-05 | 19/5/2021 | 19/8/2021 | 2021-02-09
Actual
| CONSTRUCTION OF OLOWOSAYO COLLECTOR DRAIN, IFAKO IJAIYE. | MOE/ODS/W/NCB/003-010/2021 | 10 | N91,591,140.90 | <500,000,000 | National Competitive Bidding | BOQ | Post | Prior | Plan | Prior | 20/2/2021 | 2021-05-03 | 19/3/2021 | 2021-02-04 | 16/4/2021 | 30/4/2021 | 14/4/2021 | 15/4/2021 |  | 22/5/2021 | 2021-05-05 | 19/5/2021 | 19/8/2021 | 2021-02-09
Actual
| CONSTRUCTION OF AB MANU COLLECTOR DRAIN, IJU ROAD, IFAKO IJAIYE | MOE/ODS/W/NCB/003-011/2021 | 11 | N214,740,540.76 | <500,000,000 | National Competitive Bidding | BOQ | Post | Prior | Plan | Prior | 20/2/2021 | 2021-05-03 | 19/3/2021 | 2021-02-04 | 16/4/2021 | 30/4/2021 | 14/4/2021 | 15/4/2021 |  | 22/5/2021 | 2021-05-05 | 19/5/2021 | 19/8/2021 | 2021-02-09
Actual
| CONSTRUCTION OF BARUWA COLLECTOR DRAIN, IFAKO IJAIYE | MOE/ODS/W/NCB/003-012/2021 | 12 | N78,355,211.98 | <500,000,000 | National Competitive Bidding | BOQ | Post | Prior | Plan | Prior | 20/2/2021 | 2021-05-03 | 19/3/2021 | 2021-02-04 | 16/4/2021 | 30/4/2021 | 14/4/2021 | 15/4/2021 |  | 22/5/2021 | 2021-05-05 | 19/5/2021 | 19/8/2021 | 2021-02-09
Actual
| CONSTRUCTION OF PA AGO OJO COLLECTOR DRAIN, IFAKO IJAIYE | MOE/ODS/W/NCB/003-013/2021 | 13 | N93,663,065.01 | <500,000,000 | National Competitive Bidding | BOQ | Post | Prior | Plan | Prior | 20/2/2021 | 2021-05-03 | 19/3/2021 | 2021-02-04 | 16/4/2021 | 30/4/2021 | 14/4/2021 | 15/4/2021 |  | 22/5/2021 | 2021-05-05 | 19/5/2021 | 19/8/2021 | 2021-02-09
Actual
| CONSTRUCTION OF DOWNSTREAM OF MAJEOBAJE COLLECTOR DRAIN, IFAKO IJAIYE | MOE/ODS/W/NCB/003-014/2021 | 14 | N229,407,456.94 | <500,000,000 | National Competitive Bidding | BOQ | Post | Prior | Plan | Prior | 20/2/2021 | 2021-05-03 | 19/3/2021 | 2021-02-04 | 16/4/2021 | 30/4/2021 | 14/4/2021 | 15/4/2021 |  | 22/5/2021 | 2021-05-05 | 19/5/2021 | 19/8/2021 | 2021-02-09
Actual
| CONSTRUCTION OF JAGAL CLOSE/KUDIRAT ABIOLA/GUEST ESTIMATE AVENUE/SYSTEM 1 CHANNEL, IKEJA | MOE/ODS/W/NCB/003-015/2021 | 15 | N212,585,504.80 | <500,000,000 | National Competitive Bidding | BOQ | Post | Prior | Plan | Prior | 20/2/2021 | 2021-05-03 | 19/3/2021 | 2021-02-04 | 16/4/2021 | 30/4/2021 | 14/4/2021 | 15/4/2021 |  | 22/5/2021 | 2021-05-05 | 19/5/2021 | 19/8/2021 | 2021-02-09
Actual

## works 3
PROCUREMENT PLAN FOR WORKS
MINISTRY: OFFICE OF DRAINAGE SERVICES & WATER RESOURCES
BUDGET YEAR: 2021
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification | Prior-or Post Review |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[12 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
| CONSTRUCTION OF IKORODU GRA 2 BEACH COLLECTOR DRAIN CULVERT, IBESHE, IKORODU | MOE/ODS/W/NS/003-016/2021 | 16 | N42,422,624.20 | <50,000,000 | National Shopping | BOQ | Post | Prior | Plan | Prior | 20/2/2021 | 2021-05-03 | 19/3/2021 | 2021-02-04 | 16/4/2021 | 30/4/2021 | 14/4/2021 | 15/4/2021 |  | 22/5/2021 | 2021-05-05 | 19/5/2021 | 19/8/2021 | 2021-02-09
Actual
| CONSTRUCTION OF DRAIN FOR OMOLAIYE PRIMARY SCHOOL, IKORODU | MOE/ODS/W/NCB/003-017/2021 | 17 | N56,558,125.03 | <500,000,000 | National Competitive Bidding | BOQ | Post | Prior | Plan | Prior | 20/2/2021 | 2021-05-03 | 19/3/2021 | 2021-02-04 | 16/4/2021 | 30/4/2021 | 14/4/2021 | 15/4/2021 |  | 22/5/2021 | 2021-05-05 | 19/5/2021 | 19/8/2021 | 2021-02-09
Actual
| CONSTRUCTION OF BANJOKO COLLECTOR DRAIN, IKORODU | MOE/ODS/W/NCB/003-018/2021 | 18 | N177,205,025.43 | <500,000,000 | National Competitive Bidding | BOQ | Post | Prior | Plan | Prior | 20/2/2021 | 2021-05-03 | 19/3/2021 | 2021-02-04 | 16/4/2021 | 30/4/2021 | 14/4/2021 | 15/4/2021 |  | 22/5/2021 | 2021-05-05 | 19/5/2021 | 19/8/2021 | 2021-02-09
Actual
| CONSTRUCTION OF RAFATU AYINKE COLLECTOR DRAIN, IKORODU | MOE/ODS/W/NCB/003-019/2021 | 19 | N89,476,592.85 | <500,000,000 | National Competitive Bidding | BOQ | Post | Prior | Plan | Prior | 20/2/2021 | 2021-05-03 | 19/3/2021 | 2021-02-04 | 16/4/2021 | 30/4/2021 | 14/4/2021 | 15/4/2021 |  | 22/5/2021 | 2021-05-05 | 19/5/2021 | 19/8/2021 | 2021-02-09
Actual
| CONSTRUCTION OF COLLECTOR DRAIN AT IBIRONKE STREET OFF SUNMOLA ROAD, KOSOFE | MOE/ODS/W/NS/003-020/2021 | 20 | N20,360,261.52 | <50,000,000 | National Shopping | BOQ | Post | Prior | Plan | Prior | 20/2/2021 | 2021-05-03 | 19/3/2021 | 2021-02-04 | 16/4/2021 | 30/4/2021 | 14/4/2021 | 15/4/2021 |  | 22/5/2021 | 2021-05-05 | 19/5/2021 | 19/8/2021 | 2021-02-09
Actual
| CONSTRUCTION OF DR. OKEY ONUZO/DELE ONABULE COLLECTOR DRAIN, KOSOFE | MOE/ODS/W/NCB/003-021/2021 | 21 | N68,147,803.77 | <500,000,000 | National Competitive Bidding | BOQ | Post | Prior | Plan | Prior | 20/2/2021 | 2021-05-03 | 19/3/2021 | 2021-02-04 | 16/4/2021 | 30/4/2021 | 14/4/2021 | 15/4/2021 |  | 22/5/2021 | 2021-05-05 | 19/5/2021 | 19/8/2021 | 2021-02-09
Actual
| CONSTRUCTION OF UPSTREAM AND DOWNSTREAM ALARA/ADESHINA COLLECTOR DRAIN, IWAYA, LAGOS MAINLAND | MOE/ODS/W/NCB/003-022/2021 | 22 | N96,544,429.71 | <500,000,000 | National Competitive Bidding | BOQ | Post | Prior | Plan | Prior | 20/2/2021 | 2021-05-03 | 19/3/2021 | 2021-02-04 | 16/4/2021 | 30/4/2021 | 14/4/2021 | 15/4/2021 |  | 22/5/2021 | 2021-05-05 | 19/5/2021 | 19/8/2021 | 2021-02-09
Actual
| CONCRETE LINING OF AGBOROKO PRIMARY CHANNEL, OJO LGA | MOE/ODS/W/NCB/003-023/2021 | 23 | N144,971510.50 | <500,000,000 | National Competitive Bidding | BOQ | Post | Prior | Plan | Prior | 20/2/2021 | 2021-05-03 | 19/3/2021 | 2021-02-04 | 16/4/2021 | 30/4/2021 | 14/4/2021 | 15/4/2021 |  | 22/5/2021 | 2021-05-05 | 19/5/2021 | 19/8/2021 | 2021-02-09
Actual
| CONSTRUCTION OF COLLECTOR DRAIN AT ABULE ALAFIA STREET, OKOMAIKO, OJO LGA, | MOE/ODS/W/NCB/003-024/2021 | 24 | N52,402,608.20 | <500,000,000 | National Competitive Bidding | BOQ | Post | Prior | Plan | Prior | 20/2/2021 | 2021-05-03 | 19/3/2021 | 2021-02-04 | 16/4/2021 | 30/4/2021 | 14/4/2021 | 15/4/2021 |  | 22/5/2021 | 2021-05-05 | 19/5/2021 | 19/8/2021 | 2021-02-09
Actual
| CONSTRUCTION OF FUNSHO KINOSHI/JEMTOK/CANAL AVENUE COLLECTOR DRAIN, OSHODI ISOLO | MOE/ODS/W/NCB/003-025/2021 | 25 | N84,715,446.50 | <500,000,000 | National Competitive Bidding | BOQ | Post | Prior | Plan | Prior | 20/2/2021 | 2021-05-03 | 19/3/2021 | 2021-02-04 | 16/4/2021 | 30/4/2021 | 14/4/2021 | 15/4/2021 |  | 22/5/2021 | 2021-05-05 | 19/5/2021 | 19/8/2021 | 2021-02-09
Actual
| CONSTRUCTION OF AJISEGIRI COLLECTOR, SHOGUNLE, OSHODI ISOLO | MOE/ODS/W/NCB/003-026/2021 | 26 | N185,481,138.87 | <500,000,000 | National Competitive Bidding | BOQ | Post | Prior | Plan | Prior | 20/2/2021 | 2021-05-03 | 19/3/2021 | 2021-02-04 | 16/4/2021 | 30/4/2021 | 14/4/2021 | 15/4/2021 |  | 22/5/2021 | 2021-05-05 | 19/5/2021 | 19/8/2021 | 2021-02-09
Actual
| CONSTRUCTION OF ISHERI OSHUN ROAD/JAKANDE ESTATE/SYSTEM 6E, OSHODI ISOLO. | MOE/ODS/W/NCB/003-027/2021 | 27 | N237,995,216.60 | <500,000,000 | National Competitive Bidding | BOQ | Post | Prior | Plan | Prior | 20/2/2021 | 2021-05-03 | 19/3/2021 | 2021-02-04 | 16/4/2021 | 30/4/2021 | 14/4/2021 | 15/4/2021 |  | 22/5/2021 | 2021-05-05 | 19/5/2021 | 19/8/2021 | 2021-02-09
Actual

## work 4
PROCUREMENT PLAN FOR WORKS
MINISTRY: OFFICE OF DRAINAGE SERVICES & WATER RESOURCES
BUDGET YEAR: 2021
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification | Prior-or Post Review |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[12 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
| CONSTRUCTION OF DRAIN AT ALHAJI ARIYO/ODUNSI/AROBADADE TO LAGOS LAGOON, BARIGA, SHOMOLU | MOE/ODS/W/NCB/003-028/2021 | 28 | N99,952,104.71 | <500,000,000 | National Competitive Bidding | BOQ | Post | Prior | Plan | Prior | 20/2/2021 | 2021-05-03 | 19/3/2021 | 2021-02-04 | 16/4/2021 | 30/4/2021 | 14/4/2021 | 15/4/2021 |  | 22/5/2021 | 2021-05-05 | 19/5/2021 | 19/8/2021 | 2021-02-09
Actual
| CONSTRUCTION OF AKINSEMOYIN COLLECTOR DRAIN, SURULERE | MOE/ODS/W/NCB/003-029/2021 | 29 | N66,397,368.10 | <500,000,000 | National Competitive Bidding | BOQ | Post | Prior | Plan | Prior | 20/2/2021 | 2021-05-03 | 19/3/2021 | 2021-02-04 | 16/4/2021 | 30/4/2021 | 14/4/2021 | 15/4/2021 |  | 22/5/2021 | 2021-05-05 | 19/5/2021 | 19/8/2021 | 2021-02-09
Actual
| CONSTRUCTION OF IYUN COLLECTOR DRAIN, SURULERE | MOE/ODS/W/NCB/003-030/2021 | 30 | N77,638,610.37 | <500,000,000 | National Competitive Bidding | BOQ | Post | Prior | Plan | Prior | 20/2/2021 | 2021-05-03 | 19/3/2021 | 2021-02-04 | 16/4/2021 | 30/4/2021 | 14/4/2021 | 15/4/2021 |  | 22/5/2021 | 2021-05-05 | 19/5/2021 | 19/8/2021 | 2021-02-09
Actual
| Drilling of investigative borehole in various areas | MOE/ODS/W/NS/001-01/2020 |  | N10,000,000 | <50,000,000 | National Shopping | BOQ | Post | Prior | Plan | Prior | 17/2/2021 | 20/2/2021 | 27/2/2021 | 2021-12-03 | 19/3/2021 | 26/3/2021 | 2021-09-04 | 10/4/2021 |  | 17/4/2021 | 24/4/2021 | 2021-08-05 | 2021-08-07 | 22/7/2021
Actual
| Rehabilitation of water scheme in Lagos metropolis | MOE/ODS/W/NCB/004-32/2020 |  | N80,000,000 | <500,000,000 | National Competitive Bidding | BOQ | Post | Prior | Plan | Prior | 20/2/2020 | 2020-05-03 | 19/3/2020 | 2020-02-04 | 16/4/2020 | 30/4/2020 | 14/4/2020 | 15/4/2020 |  | 22/5/2020 | 2020-05-05 | 19/5/2020 | 19/8/2020 | 2020-02-09
Actual
| Rehabilitation of 1,632 metres of Collapsed Culverts & Drains within the state | MOE/ODS/W/NCB/004-33/2020 |  | N50,000,000.00 | <500,000,000 | National Competitive Bidding | BOQ | Post | Prior | Plan | Prior | 2021-03-03 | 2021-10-03 | 17/3/2021 | 31/3/2021 | 2021-07-04 | 14/4/2021 | 28/4/2021 | 29/4/2021 |  | 2021-06-05 | 13/5/2021 | 20/5/2021 | 20/7/2021 | 2021-03-08
Actual
| MAINTENANCE & UPGRADE OF EFAG YARD | MOE/ODS/W/NCB/004-34/2020 |  | 50000000 | <500,000,000 | National Competitive Bidding | BOQ | Post | Prior | Plan | Prior | 17/2/2021 | 20/2/2021 | 27/2/2021 | 2021-12-03 | 19/3/2021 | 26/3/2021 | 2021-09-04 | 10/4/2021 |  | 17/4/2021 | 24/4/2021 | 2021-08-05 | 2021-08-07 | 22/7/2021
Actual
| TOTAL |  |  | 5990000000

## Outstanding Liabilities 1
PROCUREMENT PLAN FOR WORKS
MINISTRY: OFFICE OF DRAINAGE SERVICES & WATER RESOURCES
BUDGET YEAR: 2021
OUTSTANDING LIABILITIES
| S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
|  | Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[12 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
|  | CONSTRUCTION OF AJIRAN-OUTFALL CHANNEL, ETI-OSA |  |  | 167950212.624 |  |  |  | Prior | Plan | Prior |  | 2021-05-03 | [11 empty] | 19/3/2021
Actual
|  | CONSTRUCTION OF MOTOR WAYS/EXPRESS FLOOD SOLUTION, IKEJA |  |  | 8258055.852 |  |  |  | Prior | Plan | Prior |  | 2021-05-03 | [11 empty] | 19/3/2021
Actual
|  | CONSTRUCTION OF JOSHUA EDE DOWNSTREAM CHANNEL, ABARANJE, ALIMOSHO |  |  | 30513056.79 |  |  |  | Prior | Plan | Prior |  | 2021-05-03 | [11 empty] | 19/3/2021
Actual
|  | CONSTRUCTION OF KUSHORO/IGBAYILOLA STREET COLLECTOR DRAIN, PHASE II, AGEGE |  |  | 33889438.88 |  |  |  | Prior | Plan | Prior |  | 2021-05-03 | [11 empty] | 19/3/2021
Actual
|  | CONSTRUCTION OF JOHNSON/ BAWALA/ONISEMO CHANNEL, SHOMOLU LGA |  |  | 16477646.36 |  |  |  | Prior | Plan | Prior |  | 2021-05-03 | [11 empty] | 19/3/2021
Actual
|  | CONSTRUCTION OF ILOGBO EREMI PHASE II COLELCTOR DRAIN, BADAGRY LGA |  |  | 20887674.45 |  |  |  | Prior | Plan | Prior |  | 2021-05-03 | [11 empty] | 19/3/2021
Actual
|  | CONSTRUCTION OF BADA COLLECTOR DRAIN, MUSHIN LGA |  |  | 2174742.62 |  |  |  | Prior | Plan | Prior |  | 2021-05-03 | [11 empty] | 19/3/2021
Actual
|  | CONSTRUCTION OF SOMOYE/EJIKUNLE/SHAKIRU COLLECTOR DRAIN, ORILE AGEGE |  |  | 35684102.51 |  |  |  | Prior | Plan | Prior |  | 2021-05-03 | [11 empty] | 19/3/2021
Actual
|  | CONSTRUCTION OF CANAL ROAD COLLECTOR DRAIN, AJEROMI IFELODUN |  |  | 25781182.31 |  |  |  | Prior | Plan | Prior |  | 2021-05-03 | [11 empty] | 19/3/2021
Actual
|  | CONSTRUCTION OF LEFI AWOSE CRESCENT/ AFOYONDE STREET COLLECTOR DRAIN, BADAGRY LGA |  |  | 3458677.61 |  |  |  | Prior | Plan | Prior |  | 2021-05-03 | [11 empty] | 19/3/2021
Actual
|  | CONSTRUCTION OF ADENUGA/DFRRI/JESOGBOGO COLLECTOR DRAINS WITHIN ARO COMMUNITY, BADAGRY |  |  | 4113085.97 |  |  |  | Prior | Plan | Prior |  | 2021-05-03 | [11 empty] | 19/3/2021
Actual
|  | CONSTRUCTION OF ELEMORO COLLECTOR DRAIN, IBEJU LEKKI |  |  | 28734615.71 |  |  |  | Prior | Plan | Prior |  | 2021-05-03 | [11 empty] | 19/3/2021
Actual
|  | TOTAL |  |  | 377922491.686

## Outstanding L 2
PROCUREMENT PLAN FOR WORKS
MINISTRY: OFFICE OF DRAINAGE SERVICES & WATER RESOURCES
BUDGET YEAR: 2021
OUTSTANDING LIABILITIES
| S/N | CONTRACT IDENTIFICATION |  |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
|  | Contract Description |  | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[13 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
|  | CONSTRUCTION OF ORCHID ROAD CHANNEL, ETI-OSA | CONSTRUCTION OF ORCHID ROAD CHANNEL, ETI-OSA (OUTSTANDING PAYMENT) |  |  | 56863657.2 |  |  |  | Prior | Plan | Prior |  | 2021-05-03 | [11 empty] | 19/3/2021
Actual
|  | CONSTRUCTION OF MC GREGOR CHANNEL DRAIN EXTENSION, ETI-OSA | CONSTRUCTION OF MC GREGOR CHANNEL DRAIN EXTENSION, ETI-OSA |  |  | 14722516.89 |  |  |  | Prior | Plan | Prior |  | 2021-05-03 | [11 empty] | 19/3/2021
Actual
|  | CONSTRUCTION OF SEASIDE MEGA ESTATE COLLECTOR DRAIN, BADORE, AJAH, ETI-OSA | CONSTRUCTION OF SEASIDE MEGA ESTATE COLLECTOR DRAIN, BADORE, AJAH, ETI-OSA (OUTSTANDING PAYMENT) |  |  | 48687335.43 |  |  |  | Prior | Plan | Prior |  | 2021-05-03 | [11 empty] | 19/3/2021
Actual
|  | CONSTRUCTION OF SENATOR OLUREMI TINUBU NEW ERA FOUNDATION COLLECTOR DRAIN, IBEJU LEKKI | CONSTRUCTION OF SENATOR OLUREMI TINUBU NEW ERA FOUNDATION COLLECTOR DRAIN, IBEJU LEKKI (OUTSTANDING PAYMENT) |  |  | 2975512.02 |  |  |  | Prior | Plan | Prior |  | 2021-05-03 | [11 empty] | 19/3/2021
Actual
|  | CONSTRUCTION OF EDUN ALARAN ROAD/OBADEYI/AJALA ROAD COLLECTOR DRAIN, OJOKORO, IFAKO IJAIYE | CONSTRUCTION OF EDUN ALARAN ROAD/OBADEYI/AJALA ROAD COLLECTOR DRAIN, OJOKORO, IFAKO IJAIYE |  |  | 45146406.36 |  |  |  | Prior | Plan | Prior |  | 2021-05-03 | [11 empty] | 19/3/2021
Actual
|  | CONSTRUCTION OF COLLECTOR DRAIN TO DEFLOOD OPEBI, IKEJA | CONSTRUCTION OF COLLECTOR DRAIN TO DEFLOOD OPEBI, IKEJA (OUTSTANDING PAYMENT) |  |  | 20089953.79 |  |  |  | Prior | Plan | Prior |  | 2021-05-03 | [11 empty] | 19/3/2021
Actual
|  | CONSTRUCTION OF FISH FARM ESTATE COLLECTOR DRAIN, ODONGUNYAN, IKORODU | CONSTRUCTION OF FISH FARM ESTATE COLLECTOR DRAIN, ODONGUNYAN, IKORODU (OUTSTANDING PAYMENT) |  |  | 36721216.37 |  |  |  | Prior | Plan | Prior |  | 2021-05-03 | [11 empty] | 19/3/2021
Actual
|  | CONSTRUCTION OF COLLECTOR DRAIN TO DEFLOOD THIRD AXIAL ROAD, KOSOFE | CONSTRUCTION OF COLLECTOR DRAIN TO DEFLOOD THIRD AXIAL ROAD, KOSOFE (OUTSTANDING PAYMENT) |  |  | 46857292.59 |  |  |  | Prior | Plan | Prior |  | 2021-05-03 | [11 empty] | 19/3/2021
Actual
|  | CONSTRUCTION OF COLLECTOR DRAIN AND EROSION CONTROL WORKS AT UNITY OMOLE PHASE II EXTENSION, KOSOFE LGA | CONSTRUCTION OF COLLECTOR DRAIN AND EROSION CONTROL WORKS AT UNITY OMOLE PHASE II EXTENSION, KOSOFE LGA (OUTSTANDING PAYMENT) |  |  | 34354749.76 |  |  |  | Prior | Plan | Prior |  | 2021-05-03 | [11 empty] | 19/3/2021
Actual
|  | CONSTRUCTION OF ODUNFA/ADENIJI ADELE COLLECTOR DRAIN, LAGOS ISLAND | CONSTRUCTION OF ODUNFA/ADENIJI ADELE COLLECTOR DRAIN, LAGOS ISLAND |  |  | 25970261.38 |  |  |  | Prior | Plan | Prior |  | 2021-05-03 | [11 empty] | 19/3/2021
Actual
|  | CONSTRUCTION OF DACOSTA/ADESINA/ZANZI COLLECTOR DRAIN, LAGOS MAINLAND | CONSTRUCTION OF DACOSTA/ADESINA/ZANZI COLLECTOR DRAIN, LAGOS MAINLAND |  |  | 32925670.4 |  |  |  | Prior | Plan | Prior |  | 2021-05-03 | [11 empty] | 19/3/2021
Actual
|  | CONSTRUCTION OF DRAIN TO DEFLOOD ADEBISI STREET AND ITS ENVIRONS OFF MUSILIU SMITH STREET, PANTI, LAGOS MAINLAND | CONSTRUCTION OF DRAIN TO DEFLOOD ADEBISI STREET AND ITS ENVIRONS OFF MUSILIU SMITH STREET, PANTI, LAGOS MAINLAND |  |  | 25075997.61 |  |  |  | Prior | Plan | Prior |  | 2021-05-03 | [11 empty] | 19/3/2021
Actual
|  | TOTAL |  |  |  | 390390569.8

## Outstanding L 3
PROCUREMENT PLAN FOR WORKS
MINISTRY: OFFICE OF DRAINAGE SERVICES & WATER RESOURCES
BUDGET YEAR: 2021
OUTSTANDING LIABILITIES
| S/N | CONTRACT IDENTIFICATION |  |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
|  | Contract Description |  | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[13 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
|  | CONSTRUCTION OF LAWANSON BY OMOBOLA/DUROJAIYE COLLECTOR MUSHIN LGA | CONSTRUCTION OF LAWANSON BY OMOBOLA/DUROJAIYE COLLECTOR MUSHIN LGA |  |  | 61132668.94 |  |  |  | Prior | Plan | Prior |  | 2021-05-03 | [11 empty] | 19/3/2021
Actual
|  | CONSTRUCTION OF ABEOKUTA/OLANREWAJU COLLECTOR DRAIN, OKOKOMAIKO, IBA LCDA, OJO | CONSTRUCTION OF ABEOKUTA/OLANREWAJU COLLECTOR DRAIN, OKOKOMAIKO, IBA LCDA, OJO |  |  | 39144628.87 |  |  |  | Prior | Plan | Prior |  | 2021-05-03 | [11 empty] | 19/3/2021
Actual
|  | CONSTRUCTION OF REV. ADEGOKE/SANUSI ASHIATA COLLECTOR DRAIN, OSHODI ISOLO | CONSTRUCTION OF REV. ADEGOKE/SANUSI ASHIATA COLLECTOR DRAIN, OSHODI ISOLO (OUTSTANDING PAYMENT) |  |  | 13058020.06 |  |  |  | Prior | Plan | Prior |  | 2021-05-03 | [11 empty] | 19/3/2021
Actual
|  | CONSTRUCTION OF OMOLADE OSILOWO NEW EWU TOWN COLLECTOR DRAIN, OSHODI ISOLO | CONSTRUCTION OF OMOLADE OSILOWO NEW EWU TOWN COLLECTOR DRAIN, OSHODI ISOLO (OUTSTANDING PAYMENT) |  |  | 3795562.05 |  |  |  | Prior | Plan | Prior |  | 2021-05-03 | [11 empty] | 19/3/2021
Actual
|  | CONSTRUCTION OF ELETU ODIBO JUNIOR HIGH SCHOOL COLLECTOR DRAIN, ABULE IJESHA, SHOMOLU | CONSTRUCTION OF ELETU ODIBO JUNIOR HIGH SCHOOL COLLECTOR DRAIN, ABULE IJESHA, SHOMOLU (OUTSTANDING PAYMENT) |  |  | 2968917.64 |  |  |  | Prior | Plan | Prior |  | 2021-05-03 | [11 empty] | 19/3/2021
Actual
|  | CONSTRUCTION OF COMMUNITY PRIMARY SCHOOL COLLECTOR DRAIN, ALABA EXPRESS | CONSTRUCTION OF COMMUNITY PRIMARY SCHOOL COLLECTOR DRAIN, ALABA EXPRESS (OUTSTANDING PAYMENT) |  |  | 758499.35 |  |  |  | Prior | Plan | Prior |  | 2021-05-03 | [11 empty] | 19/3/2021
Actual
|  | CONSTRUCTION OF MONILOLA ADEPOJU/ODEBIYI/AMEME COLLECTOR DRAIN | CONSTRUCTION OF MONILOLA ADEPOJU/ODEBIYI/AMEME COLLECTOR DRAIN (OUTSTANDING PAYMENT) |  |  | 1648001.43 |  |  |  | Prior | Plan | Prior |  | 2021-05-03 | [11 empty] | 19/3/2021
Actual
|  | CONSTRUCTION OF ABIODUN IBIKUNLE COLLECTOR DRAIN, PHASE II, AGBADO OKEODO | CONSTRUCTION OF ABIODUN IBIKUNLE COLLECTOR DRAIN, PHASE II, AGBADO OKEODO (OUTSTANDING PAYMENT) |  |  | 15444974.09 |  |  |  | Prior | Plan | Prior |  | 2021-05-03 | [11 empty] | 19/3/2021
Actual
|  | CONSTRUCTION OF ONIBUORE COLLECTOR DRAIN, SURULERE | CONSTRUCTION OF ONIBUORE COLLECTOR DRAIN, SURULERE (OUTSTANDING PAYMENT) |  |  | 16614589.83 |  |  |  | Prior | Plan | Prior |  | 2021-05-03 | [11 empty] | 19/3/2021
Actual
|  | CONSTRUCTION OF COMMUNITY PRIMARY SCHOOL COLLECTOR DRAIN, AMUWO ODOFIN | CONSTRUCTION OF COMMUNITY PRIMARY SCHOOL COLLECTOR DRAIN, AMUWO ODOFIN (OUTSTANDING PAYMENT) |  |  | 829565.16 |  |  |  | Prior | Plan | Prior |  | 2021-05-03 | [11 empty] | 19/3/2021
Actual
|  | CONSTRUCTION OF IJU SENIOR GRAMMAR SCHOOL COLLECTOR DRAIN, IFAKO IJAIYE | CONSTRUCTION OF IJU SENIOR GRAMMAR SCHOOL COLLECTOR DRAIN, IFAKO IJAIYE |  |  | 674766.81 |  |  |  | Prior | Plan | Prior |  | 2021-05-03 | [11 empty] | 19/3/2021
Actual
|  | CONSTRUCTION OF KEKE SENIOR GRAMMAR SCHOOL COLELCTOR DRAIN, IFAKO IJAIYE | CONSTRUCTION OF KEKE SENIOR GRAMMAR SCHOOL COLELCTOR DRAIN, IFAKO IJAIYE |  |  | 785039.65 |  |  |  | Prior | Plan | Prior |  | 2021-05-03 | [11 empty] | 19/3/2021
Actual
|  | TOTAL |  |  |  | 156855233.88

## Outstanding L 4
PROCUREMENT PLAN FOR WORKS
MINISTRY: OFFICE OF DRAINAGE SERVICES & WATER RESOURCES
BUDGET YEAR: 2021
OUTSTANDING LIABILITIES
| S/N | CONTRACT IDENTIFICATION |  |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
|  | Contract Description |  | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[13 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
|  | CONSTRUCTION OF STATION JUNIOR GRAMMAR SCHOOL COLLECTOR DRAIN, IFAKO IJAIYE | CONSTRUCTION OF STATION JUNIOR GRAMMAR SCHOOL COLLECTOR DRAIN, IFAKO IJAIYE |  |  | 613424.37 |  |  |  | Prior | Plan | Prior |  | 2021-05-03 | [11 empty] | 19/3/2021
Actual
|  | CONSTRUCTION OF COLLECTOR DRAIN TO DEFLOOD DIVINE ESTATE THROUGH TANK FARM ESTATE, AMUWO ODOFIN | CONSTRUCTION OF COLLECTOR DRAIN TO DEFLOOD DIVINE ESTATE THROUGH TANK FARM ESTATE, AMUWO ODOFIN |  |  | 72723889.32 |  |  |  | Prior | Plan | Prior |  | 2021-05-03 | [11 empty] | 19/3/2021
Actual
|  | CONSTRUCTION OF BROWN STREET/AIYETORO/SYSTEM 5 COLLECTOR, SURULERE | CONSTRUCTION OF BROWN STREET/AIYETORO/SYSTEM 5 COLLECTOR, SURULERE |  |  | 14952091.04 |  |  |  | Prior | Plan | Prior |  | 2021-05-03 | [11 empty] | 19/3/2021
Actual
|  | CONSTRUCTION OF OKE ODO JUNIOR COLLEGE COLLECTOR DRAIN, AGBADO OKEODO, ALIMOSHO | CONSTRUCTION OF OKE ODO JUNIOR COLLEGE COLLECTOR DRAIN, AGBADO OKEODO, ALIMOSHO |  |  | 1107422.62 |  |  |  | Prior | Plan | Prior |  | 2021-05-03 | [11 empty] | 19/3/2021
Actual
|  | CONSTRUCTION OF AGOLONTO COLLECTOR DRAIN, BADAGRY LGA | CONSTRUCTION OF AGOLONTO COLLECTOR DRAIN, BADAGRY LGA (OUTSTANDING PAYMENT) |  |  | 1601271.06 |  |  |  | Prior | Plan | Prior |  | 2021-05-03 | [11 empty] | 19/3/2021
Actual
|  | CONSTRUCTION OF IMULOKANLE COLLECTOR DRAIN, PHASE II, MEIRAN, AGBADO OKE ODO, ALIMOSHO | CONSTRUCTION OF IMULOKANLE COLLECTOR DRAIN, PHASE II, MEIRAN, AGBADO OKE ODO, ALIMOSHO.(OUTSTANDING PAYMENT) |  |  | 41200566.58 |  |  |  | Prior | Plan | Prior |  | 2021-05-03 | [11 empty] | 19/3/2021
Actual
|  | DEFLOODING OF SCHOOLS WITHIN EDUCATION DISTRICT IV ERIC MOORE, SURULERE | DEFLOODING OF SCHOOLS WITHIN EDUCATION DISTRICT IV ERIC MOORE, SURULERE (OUTSTANDING PAYMENT) |  |  | 89196685.4 |  |  |  | Prior | Plan | Prior |  | 2021-05-03 | [11 empty] | 19/3/2021
Actual
|  | DEFLOODING OF KATANGOWA AND ABEOKUTA EXPRESSWAY, ALIMOSHO | DEFLOODING OF KATANGOWA AND ABEOKUTA EXPRESSWAY, ALIMOSHO (OUTSTANDING PAYMENT) |  |  | 81863229.13 |  |  |  | Prior | Plan | Prior |  | 2021-05-03 | [11 empty] | 19/3/2021
Actual
|  | DEFLOODING OF AKOWONJO/EGBEDA ROAD AND ITS ADJOINING STREETS, ALIMOSHO LGA | DEFLOODING OF AKOWONJO/EGBEDA ROAD AND ITS ADJOINING STREETS, ALIMOSHO LGA. (OUTSTANDING PAYMENT) |  |  | 101948789.91 |  |  |  | Prior | Plan | Prior |  | 2021-05-03 | [11 empty] | 19/3/2021
Actual
|  | CONSTRUCTION OF COLLECTOR DRAIN TO SOLVE FLOODING ON AGO PALACE WAY AROUND COMMUNITY JUNCTION, OSHODI ISOLO LGA | CONSTRUCTION OF COLLECTOR DRAIN TO SOLVE FLOODING ON AGO PALACE WAY AROUND COMMUNITY JUNCTION, OSHODI ISOLO LGA. (OUTSTANDING PAYMENT) |  |  | 103893962.22 |  |  |  | Prior | Plan | Prior |  | 2021-05-03 | [11 empty] | 19/3/2021
Actual
|  | CLEARING OF ODO ASHIMOWU (SYSTEM 6C AND ITS TRIBUTARIES), MUSHIN | CLEARING OF ODO ASHIMOWU (SYSTEM 6C AND ITS TRIBUTARIES), MUSHIN (OUTSTANDING PAYMENT) |  |  | 273694033.9 |  |  |  | Prior | Plan | Prior |  | 2021-05-03 | [11 empty] | 19/3/2021
Actual
|  | CLEANING OF SYSTEM 6C (ODO-ASHIMOWU) FROM AGEGE MOTOR ROAD TO CELE IJESHA EXPRESSWAY, MUSHIN | CLEANING OF SYSTEM 6C (ODO-ASHIMOWU) FROM AGEGE MOTOR ROAD TO CELE IJESHA EXPRESSWAY, MUSHIN (OUTSTANDING PAYMENT) |  |  | 139536339.09 |  |  |  | Prior | Plan | Prior |  | 2021-05-03 | [11 empty] | 19/3/2021
Actual
|  | TOTAL |  |  |  | 922331704.64