## Non-Proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: ONIKAN HEALTH CENTRE
BUDGET YEAR 2021
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TOTAL
1 | SPECIAL DUTIES | OHCL/NP/NM/001/21 | 1,964,535.00 | Plan | 163711.25 | 163711.25 | 163711.25 | 163711.25 | 163711.25 | 163711.25 | 163711.25 | 163711.25 | 163711.25 | 163711.25 | 163711.25 | 163711.25 | 1964535
Actual
2 | TRAVEL & TRANSPORT | OHCL/NP/NM/002/21 | 400,000.00 | Plan | 33333 | 33333 | 33333 | 33333 | 3333 | 33333 | 33333 | 33333 | 33333 | 33333 | 33333 | 33333 | 400000
Actual
3 | PROCUREMENT OF COOKING GAS,SUBSCRITION OF INTERNET & HOSPITAL TELEPPHONE BILLS. | OHCL/NP/NM/003/21 | 550000 | Plan | 45833.33 | 45833.33 | 45833.33 | 45833.33 | 45833.33 | 45833.33 | 45833.33 | 45833.33 | 45833.33 | 45833.33 | 45833.33 | 45833.33
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual

## trg conf wsh
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: ONIKAN HEALTH CENTRE
BUDGET YEAR 2021
S/N | Description of Training/Workshop/ Conference | Package Number | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | COWSLO | OHCL/S-WTC/SS/001/21 | NOT YET KNOWN | 5 PARTICIPANT | 3 DAYS | Plan | EKO HOTEL | 80000 |  |  | 400000
Actual
2 | CIPSMN | OHCL/S-WTC/SS/002/21 | NOT YET KNOWN | 1 PARTICIPANT | 3 DAYS | Plan |  | 60000 |  |  | 60000
[6 empty] | Actual | EXCELLENC HOTEL
3 | NURSES CONFERENCE | OHCL/S-WTC/SS/003/21 | NOT YET KNOWN | 4 PARTICIPANT |  | Plan |  | 80000 |  |  | 320000
Actual
4 | ANNUAL CONFERENCE FOR LABORATORY SCIENTIST | OHCL/S-WTC/SS/004/21 | NOT YET KNOWN | 2 PARTICIPANT | 3 DAYS | Plan |  | 90000 |  |  | 180000
Actual
5 | ANNUAL CONFERENCE FOR HEALTH INFORMATION | OHCL/S-WTC/SS/005/20 | NOT YET KNOWN | 2 PARTICIPANT | 3 DAYS | Plan |  | 50000 |  |  | 100000
Actual
6 | NMA HEALTH SUMMIT FOR DOCTORS | OHCL/S-WTC/SS/006/20 | NOT YET KNOWN | 1 PARTICIPANT | 3 DAYS | Plan |  | 269146 |  |  | 269146
Actual
7 | [5 empty] | Plan
Actual
8 | [5 empty] | Plan
Actual
9 | [5 empty] | Plan
Actual
10 | [5 empty] | Plan
Actual
11 | [5 empty] | Plan
Actual
12 |  |  | TOTAL |  |  | Plan
[6 empty] | Actual |  |  |  |  | 1329146

## non-cons
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY:
MINISTRY/AGENCY: ONIKAN HEALTH CENTRE
BUDGET YEAR 2021
Contract Description | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
| Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
MAINTENANCE OF OFFICE BUILDING | OHCL/S-NC/NCB/001/21 | 1 |  | 450000 | <10M | NS | Plan | POST | POST | 2021-05-04 | N/A | 19/4/2021 | 2021-03-05 | 2021-10-05 | 17/5/2021 | N/A | Plan | N/A | N/A |  | 24/5/2021 | N/A | 31/5/2021 | 31//5/2021
[7 empty] | Actual | [9 empty] | Actual
MOTOR VEHICLE MAINTENANCE AND REPAIRS | OHCL/S-NC/NCB/002/21 | 1 |  | 350000 | <10M | NS | Plan | POST | POST | 19/4/2021 | N/A | 2021-03-05 | 17/5/2021 | 24/5/2021 | 31/5/2021 | N/A | Plan | N/A | N/A |  | 2021-07-06 | N/A | 14/6/2021 | 14/6/2021
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
TOTAL |  |  |  | 800000 |  |  | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual

## consultancy
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/ AGENCY:
BUDGET YEAR:
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[5 empty] | 0 |  | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual

## Goods 1
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: ONIKAN HEALTH CENTRE
YEAR 2021
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | PROCUREMENT OF FUEL FOR MOTOR VEHICLE CONSUMPTION | OHCL/G-F/NS/001/21 | 1 |  | 350000 | <10M | NS | POST | POST | Plan | 2021-11-01 | N/A | 18/1/2021 | 2021-08-02 | 15/2/2021 | 22/2/2021 | N/A | N/A |  | 2021-01-03 | 2021-08-03 | N/A
Actual
2 | PURCHASE OF CLEANING MATERIALS | OHCL/G-F/NS/002/21 | 1 |  | 458584 | <10M | NS | POST | POST | Plan | 25/1/2021 | N/A | 2021-01-02 | 15/2/2021 | 22/2/2021 | 2021-01-03 | N/A | N/A |  | 25/1/2021 | 25/1/2021 | N/A
Actual
3 | PROCUREMENT OF STATIONERY | OHC/G-F/NS/003/21 | 1 |  | 350000 | <10M | NS | POST | POST | Plan | 2021-08-02 | N/A | 15/2/2021 | 2021-01-03 | 2021-08-03 | 15/3/2021 | N/A | N/A |  | 22/3/21 | 22/3/2021 | N/A
Actual
4 | PROCUREMENT OF MEDICAL FORMS | OHCL/G-F/NS/004/21 | 1 |  | 2000000 | <10M | NS | POST | POST | Plan | 22/2/2021 | N/A | 2021-01-03 | 15/3/2021 | 22/3/2021 | 29/3/2021 | N/A | N/A |  | 2021-05-04 | 2021-12-04 | N/A
Actual
5 | PROCUREMENT OF CHEMICAL AND LABORATORY REAGENT | OHCL/G-F/NS/005/21 | 1 |  | 2400000 | <10M | NS | POST | POST | Plan | 2021-08-03 | N/A | 15/3/2021 | 29/3/2021 | 2021-05-04 | 2021-12-04 | N/A | N/A |  | 19/4/2021 | 26/4/2021 | N/A
Actual
6 | PROCUREMENT OF MEDICAL GAS CONSUMPTION | OHCL/G-F/NS/006/21 | 1 |  | 1800000 | <10M | NS | POST | POST | Plan | 22/3/2021 | N/A | 29/3/2021 | 2021-12-04 | 19/4/2021 | 26/4/2021 | N/A | N/A |  | 2021-03-05 | 2021-10-05 | N/A
Actual
Plan
Actual
Plan
Actual
Plan
Actual
| TOTAL | [8 empty] | Plan
Actual

## Goods 2
PROCUREMENT PLAN FOR IGR.
MINISTRY/AGENCY: ONIKAN HEALTH CENTRE
YEAR 2021
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | DRUG REVOLVING FUND | OHCL/G-F/NS/007/21 | 1 |  | 63480000 | >10M | NS | POST | POST | Plan | 2021-03-05 | N/A | 2021-10-05 | 17/5/2021 | 24/5/2021 | 31/5/2021 | N/A | N/A |  | 2021-07-06 | 14/6/2021 | N/A
Actual
2 | OBSTETRICS | OHCL/G-F/NS/008/21 | 1 |  | 9890000 | >10M | NS | POST | POST | Plan | 2021-10-05 | N/A | 17/5/2021 | 24/5/2021 | 31/5/2021 | 2021-07-06 | N/A | N/A |  | 14/6/2021 | 21/6/2021 | N/A
Actual
3 | THEATRE PACK | OHCL/G-F/NS/009/21 | 1 |  | 5822000 | <10M | NS | POST | POST | Plan | 17/5/2021 | N/A | 24/5/2021 | 31/5/2021 | 2021-07-06 | 14/6/2021 | N/A | N/A |  | 21/6/2021 | 28/6/2021 | N/A
Actual
4 | ANAESTHESIA | OHCL/G-F/NS/010/21 | 1 |  | 7176000 | <10M | NS | POST | POST | Plan | 24/5/2021 | N/A | 31/5/2021 | 2021-07-06 | 14/6/2021 | 21/6/2021 | N/A | N/A |  | 28/6/2021 | 2021-05-07 | N/A
Actual
5 | SURGERY | OHCL/G-F/NS/011/21 | 1 |  | 5313000 | <10M | NS | POST | POST | Plan | 31/5/2021 | N/A | 2021-07-06 | 14/6/2021 | 21/6/2021 | 28/6/2021 | N/A | N/A |  | 2021-05-07 | 2021-12-07 | N/A
Actual
6 | GYNAECOLOGY | OHCL/G-F/NS/012/21 | 1 |  | 6926000 | <10M | NS | POST | POST | Plan | 2021-07-06 | N/A | 14/6/2021 | 21/6/2021 | 28/6/2021 | 2021-05-07 | N/A | N/A |  | 2021-12-07 | 19/7/2021 | N/A
Actual
7 | LABORATORY | OHCL/G-F/NS/013/21 | 1 |  | 47520000 | >10M | NS | POST | POST | Plan | 14/6/2021 | N/A | 21/6/2021 | 28/6/2021 | 2021-05-07 | 2021-12-07 | N/A | N/A |  | 19/7/2021 | 26/7/2021 | N/A
Actual
8 | ACC0MMODATION | 0HCL/G-F/NS/014/21 | 1 |  | 10340000 | >10M | N/S | POST | POST | Plan | 21/6/2021 | N/A | 28/6/2021 | 2021-05-07 | 2021-12-07 | 19/7/2021 | N/A | N/A |  | 26/7/2021 | 2021-02-08 | N/A
Actual
9 | GOWN | OHCL/G-F/NS/015/21 | 1 |  | 3465000 | <10M | N/S | POST | POST | Plan | 28/6/2021 | N/A | 2021-05-07 | 2021-12-07 | 19/7/2021 | 26/7/2021 | N/A | N/A |  | 2021-02-08 | 2021-09-08 | N/A
Actual
| TOTAL | [8 empty] | Plan
Actual

## Goods 3
PROCUREMENT PLAN FOR IGR.
MINISTRY/AGENCY: ONIKAN HEALTH CENTRE
YEAR 2021
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | DIET/CANTEEN | OHCL/G-F/NS/016/21 | 1 |  | 9936000 | <10M | NS | POST | POST | Plan | 2021-05-07 | N/A | 2021-12-07 | 19/7/2021 | 26/7/2021 | 2021-02-08 | N/A | N/A |  | 2021-09-08 | 16/8/2021 | N/A
Actual
2 | MISCELLANEOUS | OHCL/G-F/NS/017/21 | 1 |  | 4140000 | <10M | NS | POST | POST | Plan | 2021-12-07 | N/A | 19/7/2021 | 26/7/2021 | 2021-02-08 | 2021-09-08 | N/A | N/A |  | 16/8/2021 | 23/8/2021 | N/A
Actual
3 | ADMISSION PACK | OHCL/G-F/NS/018/21 | 1 |  | 4485000 | <10M | NS | POST | POST | Plan | 19/7/2021 | N/A | 26/7/2021 | 2021-02-08 | 2021-09-08 | 16/8/2021 | N/A | N/A |  | 23/8/2021 | 30/8/2021 | N/A
Actual
4 | DRESS & SUTURING | OHCL/G-F/NS/019/21 | 1 |  | 1512000 | <10M | NS | POST | POST | Plan | 26/7/2021 | N/A | 2021-02-08 | 2021-09-08 | 16/8/2021 | 23/8/2021 | N/A | N/A |  | 30/8/2021 | 2021-06-09 | N/A
Actual
5 | MEDICAL RECORDS & YELLOW CARD | OHCL/G-F/NS/020/21 | 1 |  | 7590000 | <10M | NS | POST | POST | Plan | 2021-02-08 | N/A | 2021-09-08 | 16/8/2021 | 23/8/2021 | 30/8/2021 | N/A | N/A |  | 2021-06-09 | 13/9/2021 | N/A
Actual
6 | SCAN | OHCL/G-F/NS/021/21 | 1 |  | 3630000 | <10M | NS | POST | POST | Plan | 2021-09-08 | N/A | 16/8/2021 | 23/8/2021 | 30/8/2021 | 2021-06-09 | N/A | N/A |  | 13/9/2021 | 20/9/2021 | N/A
Actual
7 | CASUALTY ADMISSION | OHCL/G-F/NS/022/21 | 1 |  | 2654000 | <10M | NS | POST | POST | Plan | 16/8/2021 | N/A | 23/8/2021 | 30/8/2021 | 2021-06-09 | 13/9/2021 | N/A | N/A |  | 20/9/2021 | 27/9/2021 | N/A
Actual
8 | X-RAY | OHCL/G-F/NS/023/21 | 1 |  | 4121000 | <10M | N/S | POST | POST | Plan | 23/8/2021 | N/A | 30/8/2021 | 2021-06-09 | 13/9/2021 | 20/9/2021 | N/A | N/A |  | 27/9/2021 | 2021-04-10 | N/A
Actual
Plan
Actual
| TOTAL | [8 empty] | Plan
Actual

## works
PROCUREMENT PLAN FOR WORKS
MINISTRY:
BUDGET YEAR:
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual