## Goods
PROCUREMENT PLAN FOR GOODS
MINISTRY/ AGENCY: LAGOS STATE POLYTECHNIC
BUDGET YEAR: 2021
| CONTRACT IDENTIFICATION |  |  | BASIC DATA | [5 empty] | Plan/Actual | BIDDING PERIOD (DATES) |  |  |  | BIDS EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
S/N | Contract Description | Package Number | Lot Number | No. of Unit | Budget Avail. in Naira | Approval Threshold | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDA | PPA No-Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Rpt | PPA Issues Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's Approval with PPA | Contract Amount in N'000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Substantial Completion/Istall | Inspection and Final Acceptance
[11 empty] | 1-4 wks | 1-2 wks | 1-2 wks | 2-6 wks | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hours | 0 | 1 wk | 1-2wks | 2-4 wks | 4wk
1 | Procurement of Computer systems & accessories | LSP/G/NCB/001/21 | 1 | 431 | 113,020,000.00 | >100M | NCB | POST | PRIOR | Plan | 29/01/2021 | 12/02/2021 | 26/02/2021 | 09/04/2021 | 23/04/2021 | 07/05/2021 | 04/06/2021 | 04/06/2021 |  | 11/06/2021 | 25/06/2021 | 23/07/2021 | 20/08/2021 | NA
Actual
2 | Procurement of Classroom/Lab. Furniture & Fittings | LSP/G/NS/002/21 | 1 | Various | 31,500,000.00 | <100M | NS | POST | PRIOR | Plan | 05/02/2021 | 19/02/2021 | 05/03/2021 | 16/04/2021 | 30/04/2021 | NA | NA | NA |  | 18/06/2021 | 02/07/2021 | 30/07/2021 | 27/08/2021 | NA
Actual
3 | Procurement of Motor Vehicles & Buses | LSP/G/NCB/003/21 | 1 | 8 | 93,060,000.00 | <100M | NCB | POST | PRIOR | Plan | 12/02/2021 | 26/02/2021 | 12/03/2021 | 23/04/2021 | 07/05/2021 | 21/05/2021 | 18/06/2021 | 18/06/2021 |  | 25/06/2021 | 09/07/2021 | 06/08/2021 | 03/09/2021 | NA
Actual
4 | Procurement of Plant & Machinery- 350kva, 60kva and 20kva soundproof generating set | LSP/G/NCB/004/21 | 1 | Various | 50,000,000.00 | <100M | NCB | POST | PRIOR | Plan | 19/02/2021 | 05/03/2021 | 19/03/2021 | 30/04/2021 | 14/05/2021 | 28/05/2021 | 25/06/2021 | 25/06/2021 |  | 02/07/2021 | 16/07/2021 | 13/08/2021 | 10/09/2021 | NA
Actual
5 | Procurement of Security Equipment | LSP/G/NS/005/21 | 1 | Various | 10,000,000.00 | <100M | NS | POST | PRIOR | Plan | 26/02/2021 | 12/03/2021 | 26/03/2021 | 07/05/2021 | 21/05/2021 | 04/06/2021 | 02/07/2021 | 02/07/2021 |  | 09/07/2021 | 23/07/2021 | 20/08/2021 | 17/09/2021 | NA
Actual
6 | Maintenance of Equipment & Machine -Procurement of 10hp submersible pump, workshop tools & equipment, gun powder for fire arms | LSP/G/NS/006/21 | 1 | Various | 1,210,000.00 | <10M | NS | POST | POST | Plan | 05/03/2021 | 19/03/2021 | 02/04/2021 | 14/05/2021 | 28/05/2021 | NA | NA | NA |  | 16/07/2021 | 30/07/2021 | 27/08/2021 | 24/09/2021 | NA
Actual
7 | Procurement of Stationeries- Hardcover note book, A4 paper, Flat file, student file jacket, official envelop, black RZ ink, biros, staple pin, staple machine | LSP/G/NS/007/21 | 1 | Various | 38,310,160.00 | <100M | NS | POST | PRIOR | Plan | 19/03/2021 | 02/04/2021 | 16/04/2021 | 28/05/2021 | 11/06/2021 | 25/06/2021 | 23/07/2021 | 23/07/2021 |  | 30/07/2021 | 13/08/2021 | 10/09/2021 | 08/10/2021 | NA
Actual
8 | Procurement of Uniform & Protective Outfit-production of academic gown, laboratory uniform, watchman uniform and cardigan, safety boat, raincoat for security personnel | LSP/G/NS/008/21 | 1 | 101 | 1,738,000.00 | <10M | NS | POST | POST | Plan | 26/03/2021 | 09/04/2021 | 23/04/2021 | 04/06/2021 | 18/06/2021 | NA | NA | NA |  | 06/08/2021 | 20/08/2021 | 17/09/2021 | 15/10/2021 | NA
Actual
9 | Printing & Production Expenses - printing of seasonal publication (Calendar), EED Logbook, EED textbook, SIWES log book, Answer sheets, academic certificate | LSP/G/NCB/009/21 | 1 | Various | 101,373,818.00 | >100M | NCB | POST | PRIOR | Plan | 02/04/2021 | 16/04/2021 | 30/04/2021 | 11/06/2021 | 25/06/2021 | 09/07/2021 | 06/08/2021 | 06/08/2021 |  | 13/08/2021 | 27/08/2021 | 24/09/2021 | 22/10/2021 | NA
Actual
10 | Procurement of Laboratory Reagent, Consumables & Teaching aid - vacination, medication & vet expenses, procurement of Seedding, livestock & fish feeds, teaching aid and consumables | LSP/G/NCB/010/21 | 1 | Various | 60,267,600.00 | <100M | NCB | POST | PRIOR | Plan | 12/03/2021 | 26/03/2021 | 09/04/2021 | 21/05/2021 | 04/06/2021 | 18/06/2021 | 16/07/2021 | 16/07/2021 |  | 23/07/2021 | 06/08/2021 | 03/09/2021 | 01/10/2021 | NA
Actual
11 | Management Information System expenses- procurement of photocopy toner, laptop battery charger, APC Extension box, printers toner, flash drive, motherboard | LSP/G/NS/011/21 | 1 | Various | 32,985,000.00 | <100M | NS | POST | PRIOR | Plan | 12/03/2021 | 26/03/2021 | 09/04/2021 | 21/05/2021 | 04/06/2021 | 18/06/2021 | 16/07/2021 | 16/07/2021 |  | 23/07/2021 | 06/08/2021 | 03/09/2021 | 01/10/2021 | NA
Actual
12 | Health Care & Medical Expenses- Procurement of Medical Lab reagent, (chemicals, x-ray films, gloves), procurement of drugs from manufacturer for students on needs basis | LSP/G/NS/012/21 | 1 | Various | 13,500,000.00 | <100M | NS | POST | PRIOR | Plan | 19/03/2021 | 02/04/2021 | 16/04/2021 | 28/05/2021 | 11/06/2021 | 25/06/2021 | 23/07/2021 | 23/07/2021 |  | 30/07/2021 | 13/08/2021 | 10/09/2021 | 08/10/2021 | NA
Actual
13 | Accreditation-Procurement of Equipments for School of Agric & Bio. Envirn.Engr, Chemical Engr, Civil Engr, Mechanical Engr, Mechatronic Engr, Instrumentation Lab. | LSP/G/NS/013/21 | 1 | Various | 216,423,984.00 | >100M | NCB | POST | PRIOR | Plan | 26/03/2021 | 09/04/2021 | 23/04/2021 | 04/06/2021 | 18/06/2021 | 02/07/2021 | 30/07/2021 | 30/07/2021 |  | 06/08/2021 | 20/08/2021 | 17/09/2021 | 15/10/2021 | NA
Actual
14 | Cleaning & Landscaping expenses- Chemical for weed weakening such as forceup & tools for park and Garden | LSP/G/NS/014/21 | 1 | Various | 3,828,000.00 | <10M | NS | POST | POST | Plan | 02/04/2021 | 16/04/2021 | 30/04/2021 | 11/06/2021 | 25/06/2021 | NA | NA | NA |  | 13/08/2021 | 27/08/2021 | 24/09/2021 | 22/10/2021 | NA
Actual
15 | Motor Vehicle Fuel Consumption-Fuel Grant for Principal officer, School/departmental officers car, Fuelling of Utility Buses and other Polytechnic event | LSP/G-F/NS/001/21 | 1 | Various | 45,655,274.00 | <100M | NS | POST | PRIOR | Plan | 12/03/2021 | 26/03/2021 | 09/04/2021 | 21/05/2021 | 04/06/2021 | 18/06/2021 | 16/07/2021 | 16/07/2021 |  | 23/07/2021 | 06/08/2021 | 03/09/2021 | 01/10/2021 | NA
Actual
16 | Maintenance of office Building-replacement of bulb & door lock | LSP/G-F/NS/002/21 | 1 | Various | 2,175,000.00 | <10M | NS | POST | POST | Plan | 05/02/2021 | 19/02/2021 | 05/03/2021 | 16/04/2021 | 30/04/2021 | NA | NA | NA |  | 18/06/2021 | 02/07/2021 | 30/07/2021 | 27/08/2021 | NA
Actual
17 | Motor Vehicle Repair & Maintenance - replacement of tyres and batteries | LSP/G-F/NS/003/21 | 1 | Various | 2,867,520.00 | <10M | NS | POST | POST | Plan | 12/02/2021 | 26/02/2021 | 12/03/2021 | 23/04/2021 | 07/05/2021 | NA | NA | NA |  | 25/06/2021 | 09/07/2021 | 06/08/2021 | 03/09/2021 | NA
Actual
18 | Maintenance of Infrastructures (Laboratory & Lecture Room)- provision for electrical maintenance materials needs to central store, provision for Electrical, Plumbing fitting purchases, repairs and other sundry maintenance needs | LSP/G-F/NS/004/21 | 1 | Various | 9,500,000.00 | <10M | NS | POST | POST | Plan | 19/02/2021 | 05/03/2021 | 19/03/2021 | 30/04/2021 | 14/05/2021 | NA | NA | NA |  | 02/07/2021 | 16/07/2021 | 13/08/2021 | 10/09/2021 | NA
Actual
19 | Governing Council-- Provision for council Utility Bus Fuelling and Stationeries | LSP/G-F/NS/005/21 | 1 | Various | 7,520,000.00 | <10M | NS | POST | POST | Plan | 26/02/2021 | 12/03/2021 | 26/03/2021 | 07/05/2021 | 21/05/2021 | NA | NA | NA |  | 09/07/2021 | 23/07/2021 | 20/08/2021 | 17/09/2021 | NA
Actual
20 | Fueling of Generator | LSP/G-F/NCB/006/21 | 1 | 12 | 99,360,000.00 | <100M | NCB | POST | PRIOR | Plan | 05/03/2021 | 19/03/2021 | 02/04/2021 | 14/05/2021 | 28/05/2021 | 11/06/2021 | 09/07/2021 | 09/07/2021 |  | 16/07/2021 | 30/07/2021 | 27/08/2021 | 24/09/2021 | NA
Actual
| TOTAL COST |  |  |  | 934294356 |  |  |  |  | Plan

## Works
PROCUREMENT PLAN FOR WORKS
MINISTRY/ AGENCY: LAGOS STATE POLYTECHNIC
BUDGET YEAR: 2021
| CONTRACT IDENTIFICATION |  |  | BASIC DATA |  |  |  |  | Plan vs. Actual | Prior or Post Review | BIDDING PERIOD |  |  |  | BIDS EVALUATION |  |  |  | CONTRACT FINALIZATION
S/N | Contract Description | Package Number | Lot Number | Budget Avail. in Naira | Approval Threshold | Procurement Method | Lumpsum or Bill of Quantities | Pre-or Post Qual |  |  | Bid Prep & Submission by MDA | PPA No-Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Rpt | PPA Issues Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governors Approval with PPA | Contract Amount in N'000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Substantial Completion/Istall | Inspection and Final Acceptance
[11 empty] | 1-4 wks | 1-2 wks | 1-2 wks | 2-6 wks | 1-2 wks | 1-2 wks | 1-4wks | 48hrs | 0 | 1 wk | 1-2wks | 2-4 wks | 4wks
1 | Construction of School of Technology Complex at Ikorodu Campus (Block D) | LSP/W/NCB/001/21 | 1 | 173,266,262.00 | >100M | NCB | BOQ | POST | Plan | PRIOR | 29/01/2021 | 12/02/2021 | 26/02/2021 | 2021-09-04 | 23/04/2021 | 07/05/2021 | 04/06/2021 | 04/06/2021 |  | 2021-11-06 | 25/6/2021 | 23/07/2021 | 20/08/2021 | NA
Actual
2 | Painting of Library Complex, Ikorodu Campus | LSP/W/NS/002/21 | 1 | 5,026,339.00 | <10M | NS | BOQ | POST | Plan | Post | 05/02/2021 | 19/02/2021 | 05/03/2021 | 16/04/2021 | 30/04/2021 | NA | NA | NA |  | 18/06/2021 | 02/07/2021 | 30/07/21 | 27/08/2021 | NA
Actual
3 | Erection of Perimeter Fence on Ikorodu Campus Landscape (Erikorodo Axis) (ON-GOING) |  | 1 | [5 empty] | Plan | PRIOR
|  | LSP/W/NCB/004/20 | 1 | 17,944,436.11 | <100M | NS | BOQ | POST | Actual | PRIOR | 01/2020 | 25/02/20 | 26/02/20 | 11/03/20 | 11/03/20 | 18/03/20 | 08/01/20 | 08/01/20 | 59,814,787.00 | 07/05/20 |  | 11,962,957.40
4 | Construction & Facilities of Fire Station on Ikorodu Campus (ON-GOING) | [7 empty] | Plan | PRIOR
|  | LSP/W/NCB/005/20 | 1 | 30,000,000.00 | <100M | NCB | BOQ | POST | Actual | PRIOR | 03/2020 | 07/05/20 | 11/05/20 | 25/05/20 | 11/06/20 | 07/05/20 | 13/03/20 | 13/03/20 | 85,241,777,.51 | 06/07/20 |  | 59,669,244.26
5 | Construction of Administrative Block (ON-GOING) | [7 empty] | Plan | PRIOR
|  | LSP/W/ICB/006/20 | 1 | 1,000,000,000.00 | >100M | ICB | BOQ | POST | Actual | PRIOR | 03/2020 | 12/05/20 | 26/03/20 | 14/05/20 | 14/05/20 | 02/06/20 | 13/03/20 | 13/03/20 | 2,406,468,012.82 | 05/06/20 |  | 962,587,205.13
6 | Motor Vehicle Repair & Maintenance - servicing and repair of saloon cars, utility buses, pick-up buses, coaster buses, tata buses | LSP/W-F/NS/001/21 | 1 | 19,609,800.00 | <100M | NS | BOQ | POST | Plan | PRIOR | 12/02/2021 | 26/02/2021 | 12/03/2021 | 23/04/2021 | 07/05/2021 | 21/05/2021 | 18/06/2021 | 18/06/2021 |  | 25/06/2021 | 09/07/2021 | 06/08/2021 | 03/09/2021 | NA
Actual
7 | Maintenance of Infrastructures (Laboratory & Lecture Room)- for maintenance of School laboratories, Workshops & Classroom, provision for staff quarters structure maintenance, to address roadnetwork maintenance, maintenance/repair of students toilets | LSP/W-F/NS/002/21 | 1 | 38,528,000.00 | <100M | NS | BOQ | POST | Plan | PRIOR | 19/02/2021 | 05/03/2021 | 19/03/2021 | 30/04/2021 | 14/05/2021 | 28/05/2021 | 25/06/2021 | 25/06/2021 |  | 02/07/2021 | 16/07/2021 | 13/08/2021 | 10/09/2021 | NA
Actual
| TOTAL COST |  |  | 1284374837.11 |  |  |  |  | Plan
Actual

## non proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: LAGOS STATE POLYTECHNIC
BUDGET YEAR: 2021
Plan/Actual
S/N | Activity Description | Package Number | Budget Avail |  | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER
1 | Transport & Travels- Rector and Registrar travel for CAPPA, oversea meeting, Travel on official duties within Nigeria by staff (teaching & non-teaching), travel on academic assignment, transport allowance to staff on official assignment | LSP/NP/NM/001/21 | 34,845,704.00 | Plan | 2,903,808.66 | 2,903,808.66 | 2,903,808.66 | 2,903,808.66 | 2,903,808.66 | 2,903,808.66 | 2,903,808.66 | 2,903,808.66 | 2,903,808.66 | 2,903,808.66 | 2,903,808.66 | 2,903,808.66
Actual
2 | General Utility Services - Electricity expenses, telephone monetisation, Subscription for DSTV & CUG telephone, internet subscription expenses | LSP/NP/NM/002/21 | 73,379,328.00 | Plan | 6,114,944.00 | 6,114,944.00 | 6,114,944.00 | 6,114,944.00 | 6,114,944.00 | 6,114,944.00 | 6,114,944.00 | 6,114,944.00 | 6,114,944.00 | 6,114,944.00 | 6,114,944.00 | 6,114,944.00
Actual
3 | Press & Public Relation Expenses - Donation & Gift to host community of Laspotech, Internal & External Publics, Gift for monitoring activities of regulatory bodies, Gift for friends of the Polytechnic | LSP/NP/NM/003/21 | 27,709840.00 | Plan | 2,309,153.33 | 2,309,153.33 | 2,309,153.33 | 2,309,153.33 | 2,309,153.33 | 2,309,153.33 | 2,309,153.33 | 2,309,153.33 | 2,309,153.33 | 2,309,153.33 | 2,309,153.33 | 2,309,153.33
Actual
4 | Bank Charges - on all transaction with the Bank | LSP/NP/NM/004/21 | 3,500,000.00 | Plan | 291,666.66 | 291,666.66 | 291,666.66 | 291,666.66 | 291,666.66 | 291,666.66 | 291,666.66 | 291,666.66 | 291,666.66 | 291,666.66 | 291,666.66 | 291,666.66
Actual
5 | Insurance Expenses- Group life Insurance Premium, Group Personal Accident Insurance Premium, provision for all Polytechnic Vehicle Insurance, provision for Fire & other Peril | LSP/NP/NM/005/21 | 150,500,000.00 | Plan | 12,541,666.66 | 12,541,666.66 | 12,541,666.66 | 12,541,666.66 | 12,541,666.66 | 12,541,666.66 | 12,541,666.66 | 12,541,666.66 | 12,541,666.66 | 12,541,666.66 | 12,541,666.66 | 12,541,666.66
Actual
6 | Special Academic Programmes-for Excursion/field visit of Schools to location within the country, admission exercise screening committee honorarium, publicity expenses on post UTME, UTME screening sending of SMS message | LSP/NP/NM/006/21 | 34,740,000.00 | Plan | 2,895,000.00 | 2,895,000.00 | 2,895,000.00 | 2,895,000.00 | 2,895,000.00 | 2,895,000.00 | 2,895,000.00 | 2,895,000.00 | 2,895,000.00 | 2,895,000.00 | 2,895,000.00 | 2,895,000.00
Actual
7 | Examination Administrative Expenses-- Honorarium for External Moderators, question moderators, vetting of script and project defence, honorarium for textbook assessment by external Assessors, honorarium for Interview Panelist | LSP/NP/NM/007/21 | 26,660,000.00 | Plan | 2,221,666.66 | 2,221,666.66 | 2,221,666.66 | 2,221,666.66 | 2,221,666.66 | 2,221,666.66 | 2,221,666.66 | 2,221,666.66 | 2,221,666.66 | 2,221,666.66 | 2,221,666.66 | 2,221,666.66
Actual
8 | Personnel Cost (Subvention) | LSP/NP/NM/008/21 | 3,526,076,924.00 | Plan | 293,839,743.66 | 293,839,743.66 | 293,839,743.66 | 293,839,743.66 | 293,839,743.66 | 293,839,743.66 | 293,839,743.66 | 293,839,743.66 | 293,839,743.66 | 293,839,743.66 | 293,839,743.66 | 293,839,743.66
Actual
9 | Professional Affiliation expenses-subscription due of the Polytechnic to CAPPA, ANSTI & COHEADS, Annual dues to COREG, Annual dues for SIWES to ITF, annual dues to BUSCON, annual dues to Coplin, subscription to E-Journal, E-Books. | LSP/NP/NM/009/21 | 36,320,125.00 | Plan | 3,026,677.08 | 3,026,677.08 | 3,026,677.08 | 3,026,677.08 | 3,026,677.08 | 3,026,677.08 | 3,026,677.08 | 3,026,677.08 | 3,026,677.08 | 3,026,677.08 | 3,026,677.08 | 3,026,677.08
Actual
10 | Governing Council--Council member Regular & other Ad-hoc Committee meetings composition honorarium, festival celebration gifts to Council members, provision for quarterly honorarium & percuniary allowance for council member | LSP/NP/NM/010/21 | 66,478,800.00 | Plan | 5,539,900.00 | 5,539,900.00 | 5,539,900.00 | 5,539,900.00 | 5,539,900.00 | 5,539,900.00 | 5,539,900.00 | 5,539,900.00 | 5,539,900.00 | 5,539,900.00 | 5,539,900.00 | 5,539,900.00
Actual
11 | ICT expenses - for internet subscription for the Polytechnic. | LSP/NP/NM/011/21 | 31,500,000.00 | Plan | 2,625,000.00 | 2,625,000.00 | 2,625,000.00 | 2,625,000.00 | 2,625,000.00 | 2,625,000.00 | 2,625,000.00 | 2,625,000.00 | 2,625,000.00 | 2,625,000.00 | 2,625,000.00 | 2,625,000.00
Actual
12 | Debt Obligation | LSP/NP/NM/012/21 | 186,278,600.00 | Plan | 15,523,216.66 | 15,523,216.66 | 15,523,216.66 | 15,523,216.66 | 15,523,216.66 | 15,523,216.66 | 15,523,216.66 | 15,523,216.66 | 15,523,216.66 | 15,523,216.66 | 15,523,216.66 | 15,523,216.66
Actual
13 | Meeting & Hospitality--prov. For monthly mgt committee meeting & Executive Mgt Committee secretariate expenses, support for student Union for annual week activities, transport & Accommodation support to attend NANS meeting within west zone | LSP/NP/NM/013/21 | 41,725,000.00 | Plan | 3,477,083.33 | 3,477,083.33 | 3,477,083.33 | 3,477,083.33 | 3,477,083.33 | 3,477,083.33 | 3,477,083.33 | 3,477,083.33 | 3,477,083.33 | 3,477,083.33 | 3,477,083.33 | 3,477,083.33
Actual
14 | Research & Development | LSP/NP/NM/014/21 | 17,000,000.00 | Plan | 1,416,666.67 | 1,416,666.67 | 1,416,666.67 | 1,416,666.67 | 1,416,666.67 | 1,416,666.67 | 1,416,666.67 | 1,416,666.67 | 1,416,666.67 | 1,416,666.67 | 1,416,666.67 | 1,416,666.67
Actual
15 | Consultancy & Legal Expenses- Honorarium to chairman in-house legal committee | LSP/NP/NM/015/21 | 200,000.00 | Plan | 16,666.66 | 16,666.66 | 16,666.66 | 16,666.66 | 16,666.66 | 16,666.66 | 16,666.66 | 16,666.66 | 16,666.66 | 16,666.66 | 16,666.66 | 16,666.66
Actual
16 | Cleaning & Landscaping expenses-quarterly landscaping of the Polytechnic, disposal of campus waste inclusive medical waste- LAWMA. | LSP/NP/NM/016/21 | 4,455,000.00 | Plan | 371,250.00 | 371,250.00 | 371,250.00 | 371,250.00 | 371,250.00 | 371,250.00 | 371,250.00 | 371,250.00 | 371,250.00 | 371,250.00 | 371,250.00 | 371,250.00
Actual
14 | Procurement of Laboratory Reagent, Consumables & Teaching aid - Expense on students project exhibition and defence | LSP/NP/NM/017/21 | 2,800,000.00 | Plan | 233,333.33 | 233,333.33 | 233,333.33 | 233,333.33 | 233,333.33 | 233,333.33 | 233,333.33 | 233,333.33 | 233,333.33 | 233,333.33 | 233,333.33 | 233,333.33
Actual
18 | Security Expenses - Relation with external security agencies grant, operational intelligent grant, under cover security honorarium, emergency security expenses | LSP/NP/NM/018/21 | 29,800,000.00 | Plan | 2,483,333.33 | 2,483,333.33 | 2,483,333.33 | 2,483,333.33 | 2,483,333.33 | 2,483,333.33 | 2,483,333.33 | 2,483,333.33 | 2,483,333.33 | 2,483,333.33 | 2,483,333.33 | 2,483,333.33
Actual
19 | Special Duty expenses-provision for enterprise resource packages (ERP), Financial Manual, welfare expenses, provision for revolving loan, special essential expenditure transformation to University expenses, school of Agric Farming expenses | LSP/NP/NM/019/21 | 232,233,697.00 | Plan | 19,352,808.08 | 19,352,808.08 | 19,352,808.08 | 19,352,808.08 | 19,352,808.08 | 19,352,808.08 | 19,352,808.08 | 19,352,808.08 | 19,352,808.08 | 19,352,808.08 | 19,352,808.08 | 19,352,808.08
Actual
20 | Ceremonies - NIPOGA & WAPOGA games, senior staff games of Polytechnic, NIPOGA Host fee, Annual subscription to NIPOGA, Annual subscription to WAPOGA | LSP/NP/NM/020/21 | 34,300,000.00 | Plan | 2,858,333.33 | 2,858,333.33 | 2,858,333.33 | 2,858,333.33 | 2,858,333.33 | 2,858,333.33 | 2,858,333.33 | 2,858,333.33 | 2,858,333.33 | 2,858,333.33 | 2,858,333.33 | 2,858,333.33
Actual
| TOTAL COST |  | 4560503018

## Consultancy services
PROCUREMENT PLAN FOR CONSULTANCY SERVICES ®
MINISTRY/ AGENCY: LAGOS STATE POLYTECHNIC
BUDGET YEAR: 2021
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) | [6 empty] | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selection Method | Lumpsum or Time-Based | Estimated Amount in N '000 | Prior/Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Submission of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's Approval | Register Mr. Governor's Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[5 empty] | 0 |  |  | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1wk | 2wks | 2-4 wks | 1-2wks | 1-2wks | 0
1 | Consultancy Services- External auditors fee for Y2019 Financial record audit, pursuance of legal cases before the Polytechnic & other Administrative legal unit runnings | LSP/S-C/LC/001/21 | Least Cost | Time base | 23575050 | PRIOR | Plan vs. Actual | 05/02/2021 | 19/02/2021 | 26/06/2021 | 26/03/2021 | 09/04/2021 | 23/04/2021 | 04/06/2021 | 18/06/2021 | 02/07/2021 | 09/07/2021 | 23/07/2021 | 06/08/2021 | 03/09/2021 | 18/09/2020 |  | 10/09/2021 | 24/09/2021 | 22/10/2021 | 05/11/2021 | 19/11/2021
Actual
2 | Review of Polytechnic Master Plan | LSP/S-C/LC/002/21 | Least Cost | Time base | 25,000,000.00 | PRIOR | Plan | 12/02/2021 | 26/02/2021 | 05/03/2021 | 02/04/2021 | 16/02/2021 | 30/04/2021 | 11/06/2021 | 25/06/2021 | 09/07/2021 | 16/07/2021 | 30/07/2021 | 13/08/2021 | 10/09/2021 | 10/09/2021 |  | 17/09/2021 | 01/10/2021 | 29/10/2021 | 12/11/2021 | 26/11/2021
Actual
| Total Cost |  |  |  | 48575050 | [16 empty] | #REF! | [5 empty] | #REF!

## Non-Consultancy Services
PROCUREMENT PLAN FOR NON-CONSULTANCY SERVICES
MINISTRY/ AGENCY: LAGOS STATE POLYTECHNIC
BUDGET YEAR: 2021
| CONTRACT IDENTIFICATION |  |  |  | BASIC DATA |  |  |  |  | Prior or Post Review | BIDDING PERIOD |  |  |  | BIDS EVALUATION |  |  | Plan vs. Actual |  |  | CONTRACT FINALIZATION
S/N | Contract Description | Package Number | Lot Number | No. of Unit | Budget Avail. in Naira | Approval Threshold | Procurement Method | Plan Vs Actual | Pre-or Post Qual |  | Bid Prep & Submission by MDA | PPA No-Objection Date | Bid Invitation Date | Bid Closing & Opening Date | Submission of Bid Evaluation Rpt | Minutes of Negotiation | PPA Issues Certificate of Compliance |  | Mr. Governor's Approval | Register Mr. Governor's Approval | Contract Amount in N'000 | Date Contract Signature | Mobilization/ Advance Payment | Complete Delivery/Istall | Inspection and Final Acceptance
[11 empty] | 1-4 wks | 1-2 wks | 1-2 wks | 2-6 wks | 1-2 wks | 1wk | 1-2 wks | Plan | 1-4wks | 48Hours | 0 | 4-6 wks | 2-4 wks | 2-8wks | 4WKS
1 | Cleaning & Landscaping expenses- for 160nos outsourced cleaners, 40nos outsourced gardners, quarterly landscaping of the Polytechnic, disposal of campus waste inclusive medical waste- LAWMA, fumigation expenses | LSP/S-NC/NCB/001/21 | 1 | Various | 120,503,100.00 | >100M | NCB | Plan | POST | PRIOR | 05/02/2021 | 19/02/2021 | 05/03/2021 | 16/04/2021 | 30/04/2021 | 07/05/2021 | 21/05/2021 | Plan | 18/06/2021 | 18/06/2021 |  | 30/07/2021 | 27/08/2021 | 22/10/2021 | 19/11/2021
[8 empty] | Actual | [9 empty] | Actual
2 | ICT expenses - ICT Infrastructure routine maintenance | LSP/S-NC/NS/002/21 | 1 | Various | 25,200,000.00 | <100M | NS | Plan | POST | PRIOR | 12/02/2021 | 26/02/2021 | 12/03/2021 | 23/04/2021 | 07/05/2021 | 14/05/2021 | 28/05/2021 | Plan | 25/06/2021 | 25/06/2021 |  | 06/08/2021 | 03/09/2021 | 29/10/2021 | 26/11/2021
[8 empty] | Actual | [9 empty] | Actual
3 | Ceremonies -convocation ceremony expenses, tree planting event, Production of Flex Banner | LSP/S-NC/NS/003/21 | 1 | Various | 40,830,000.00 | <100M | NS | Plan | POST | PRIOR | 19/02/2021 | 05/03/2021 | 19/04/2021 | 30/04/2021 | 14/05/2021 | 21/05/2021 | 04/06/2021 | Plan | 02/07/2021 | 02/07/2021 |  | 13/08/2021 | 10/09/2021 | 2021-05-11 | 2021-03-12
[8 empty] | Actual | [9 empty] | Actual
4 | Management Information System- maintenance charge for Registry, Bursary, Library and Audit Softwares, renewal of Kaspersky Antivirus, repair of printers | LSP/S-NC/NS/004/21 | 1 | Various | 6,044,600.00 | <10M | NS | Plan | POST | POST | 26/02/2021 | 12/03/2021 | 26/03/2021 | 07/05/2021 | 21/05/2021 | 28/05/2021 | NA | Plan | NA | NA |  | 20/08/2021 | 17/09/2021 | 12/11/2021 | 2021-10-12
[8 empty] | Actual | [9 empty] | Actual
5 | Miscellaneous- Entertaiment during ACB, SESAPCO, JUSAPCO, Board of School Meeting, courier expense on transcript, postage of administrative correspondence, postage stamp provision, renewal of Polytechnic private mail bag, production of Staff ID | LSP/S-NC/NS/005/21 | 1 | Various | 40,097,637.00 | <100M | NS | Plan | POST | PRIOR | 05/03/2021 | 19/03/2021 | 02/04/2021 | 14/05/2021 | 28/05/2021 | 04/06/2021 | 18/06/2021 | Plan | 16/07/2021 | 16/07/2021 |  | 27/08/2021 | 24/09/2021 | 19/11/2021 | 17/12/2021
[8 empty] | Actual | [9 empty] | Actual
6 | Maintenance of Infrastructures (Laboratory & Lecture Room)- for maintenance of School laboratories, Workshops & Classroom, provision for staff quarters structure maintenance, to address roadnetwork maintenance, maintenance/repair of students toilets | LSP/S-NC/NS/006/21 | 1 | Various | 2,492,700.00 | <10M | NS | Plan | POST | POST | 12/03/2021 | 26/03/2021 | 09/04/2021 | 21/05/2021 | 04/06/2021 | 11/06/2021 | NA | Plan | NA | NA |  | 03/09/2021 | 01/10/2021 | 26/11/2021 | 24/12/2021
[8 empty] | Actual | [9 empty] | Actual
7 | Maintenance of Equipment & Machine -mtce of office photocopier machine, repair & mtce of library complex PABX system, mtc of projectors, public address system, mtce of walkie talkie machine | LSP/S-NC/NS/007/21 | 1 | Various | 21,855,000.00 | <100M | NS | Plan | POST | PRIOR | 05/02/2021 | 19/02/2021 | 05/03/2021 | 16/04/2021 | 30/04/2021 | 07/05/2021 | 21/05/2021 | Plan | 18/06/2021 | 18/06/2021 |  | 30/07/2021 | 27/08/2021 | 22/10/2021 | 19/11/2021
[8 empty] | Actual | [9 empty] | Actual
8 | Advertisement & Awareness Campaign - Publicity for HND admission, newspaper placement for UTME screening, weekly Polytechnic newsflash | LSP/S-NC/NS/008/21 | 1 | Various | 11893000 | <100M | NS | Plan | POST | PRIOR | 06/03/2020 | 20/03/2020 | 03/04/2020 | 01/05/2020 | 15/05/2020 | 22/05/2020 | 05/06/2020 | Plan | 03/07/2020 | 03/07/2020 |  | 07/08/2020 | 04/09/2020 | 16/10/2020 | 13/11/2020
[8 empty] | Actual | [9 empty] | Actual
9 | Security Expenses - for Outsourced Security operatives, relation with external security agencies grant, operational intelligent grant. | LSP/S-NC/NCB/009/20 | 1 | Various | 89775000 | <100M | NCB | Plan | POST | PRIOR | 12/02/2021 | 26/02/2021 | 12/03/2021 | 23/04/2021 | 07/05/2021 | 14/05/2021 | 28/05/2021 | Plan | 25/06/2021 | 25/06/2021 |  | 06/08/2021 | 03/09/2021 | 29/10/2021 | 26/11/2021
[8 empty] | Actual | [9 empty] | Actual
10 | Special Duty expenses-provision for enterprise resource packages (ERP), Financial Manual, welfare expenses, provision for revolving loan, special essential expenditure transformation to University expenses, school of Agric Farming expenses | LSP/S-NC/NCB/010/21 | 1 | Various | 125000000 | >100M | NCB | Plan | POST | PRIOR | 19/02/2021 | 05/03/2021 | 19/04/2021 | 30/04/2021 | 14/05/2021 | 21/05/2021 | 04/06/2021 | Plan | 02/07/2021 | 02/07/2021 |  | 13/08/2021 | 10/09/2021 | 2021-05-11 | 2021-03-12
[8 empty] | Actual | [9 empty] | Actual
11 | Maintenance of Generator | LSP/S-NC-F/NS/011/21 | 1 | Various | 18320000 | <100M | NS | Plan | POST | PRIOR | 26/02/2021 | 12/03/2021 | 26/03/2021 | 07/05/2021 | 21/05/2021 | 28/05/2021 | 11/06/2021 | Plan | 09/07/2021 | 09/07/2021 |  | 20/08/2021 | 17/09/2021 | 12/11/2021 | 2021-10-12
[8 empty] | Actual | [9 empty] | Actual
12 | Motor Vehicle Repair & Maintenance - Car maintenance grant allowance, renewal of vehicles particulars | LSP/S-NC/NS/012/21 | 1 | Various | 9851880.18 | <10M | NS | Plan | POST | POST | 12/02/2021 | 26/02/2021 | 12/03/2021 | 23/04/2021 | 07/05/2021 | 14/05/2021 | NA | Plan | NA | NA |  | 06/08/2021 | 03/09/2021 | 29/10/2021 | 26/11/2021
[8 empty] | Actual | [9 empty] | Actual
13 | Conference & Seminars- Provision for Management Retreat & Council retreat | LSP/S-NC/NS/013/21 | 1 | Various | 17400000 | <100M | NS | Plan | POST | PRIOR | 19/02/2021 | 05/03/2021 | 19/04/2021 | 30/04/2021 | 14/05/2021 | 21/05/2021 | 04/06/2021 | Plan | 02/07/2021 | 02/07/2021 |  | 13/08/2021 | 10/09/2021 | 2021-05-11 | 2021-03-12
[8 empty] | Actual | [9 empty] | Actual
14 | Press & Public Relation Expenses - Rector's quarterly press briefing expenses, other public relation activities | LSP/S-NC/NS/014/21 | 1 | Various | 10380000 | <100M | NS | Plan | POST | PRIOR | 26/02/2021 | 12/03/2021 | 26/03/2021 | 07/05/2021 | 21/05/2021 | 28/05/2021 | 11/06/2021 | Plan | 09/07/2021 | 09/07/2021 |  | 20/08/2021 | 17/09/2021 | 12/11/2021 | 2021-10-12
[8 empty] | Actual | [9 empty] | Actual
15 | Consultancy & Legal Expenses- one set of Laws of the Federation & 12nos. Labour Law report | LSP/S-NC/NS/015/21 | 1 | Various | 600000 | <10M | NS | Plan | POST | POST | 05/03/2021 | 19/03/2021 | 02/04/2021 | 14/05/2021 | 28/05/2021 | 04/06/2021 | NA | Plan | NA | NA |  | 27/08/2021 | 24/09/2021 | 19/11/2021 | 17/12/2021
[8 empty] | Actual | [9 empty] | Actual
16 | Examination Administrative Expenses--Printing of ID Card for students identification | LSP/S-NC/NS/016/21 | 1 | Various | 6250000 | <10M | NS | Plan | POST | POST | 12/03/2021 | 26/03/2021 | 09/04/2021 | 21/05/2021 | 04/06/2021 | 11/06/2021 | NA | Plan | NA | NA |  | 03/09/2021 | 01/10/2021 | 26/11/2021 | 24/12/2021
[8 empty] | Actual | [9 empty] | Actual
17 | Governing Council--provision for milestone celebration of council member (birthday, direct offspring weeding, burial ceremonies of biological parents), entertainment/hospitality, maintenance of council Equipments | LSP/S-NC/NS/017/21 | 1 | Various | 12390700 | <100M | NS | Plan | POST | PRIOR | 05/02/2021 | 19/02/2021 | 05/03/2021 | 16/04/2021 | 30/04/2021 | 07/05/2021 | 21/05/2021 | Plan | 18/06/2021 | 18/06/2021 |  | 30/07/2021 | 27/08/2021 | 22/10/2021 | 19/11/2021
[8 empty] | Actual | [9 empty] | Actual
18 | Health Care & Medical Expenses- Pre-registration medical screening expenses | LSP/S-NC/NS/018/21 | 1 | Various | 4200000 | <10M | NS | Plan | POST | POST | 06/03/2020 | 20/03/2020 | 03/04/2020 | 01/05/2020 | 15/05/2020 | 22/05/2020 | NA | Plan | NA | NA |  | 07/08/2020 | 04/09/2020 | 16/10/2020 | 13/11/2020
[8 empty] | Actual | [9 empty] | Actual
19 | Erection of CCTV Camera on Ikorodu Campus | LSP/S-NC/NS/019/21 | 1 | Various | 17,854,086.90 | <100M | NS | Plan | POST | PRIOR | 12/02/2021 | 26/02/2021 | 12/03/2021 | 23/04/2021 | 07/05/2021 | 14/05/2021 | 28/05/2021 | Plan | 25/06/2021 | 25/06/2021 |  | 06/08/2021 | 03/09/2021 | 29/10/2021 | 26/11/2021
[8 empty] | Actual | [9 empty] | Actual
20 | Maintenance of office Building-plumbing works, electrical mtce, repartitioning of office space, replacement of window blind, mason work in offices, drycleaning of window blind, repair of deterioted buildings | LSP/S-NC/NCB/020/21 | 1 | Various | 65,457,000.00 | <100M | NCB | Plan | POST | PRIOR | 12/02/2021 | 26/02/2021 | 12/03/2021 | 23/04/2021 | 07/05/2021 | 14/05/2021 | 28/05/2021 | Plan | 25/06/2021 | 25/06/2021 |  | 06/08/2021 | 03/09/2021 | 29/10/2021 | 26/11/2021
[8 empty] | Actual | [9 empty] | Actual
| TOTAL COST |  |  |  | 646394704.08 |  |  | Plan | [9 empty] | Plan |  |  | #REF!

## Seminar
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: LAGOS STATE POLYTECHNIC
BUDGET YEAR: 2021
S/N | Description of Training /Workshop/Conference | Objective of Training/Workshop/Conference | Package Number | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | Conference & Seminar for Principal Officers | For training & development | LSP/S-WTC/SS/001/21 | 6 |  | Plan |  |  |  |  | 18,594,679.74
Actual
2 | Teaching Staff Seminars & Conferences | For training & development | LSP/S-WTC/SS/002/21 | 180 |  | Plan |  |  |  |  | 39,867,652.92
Actual
3 | Non-teaching staff Seminars & Conferences | For training & development | LSP/S-WTC/SS/003/21 | 50 |  | Plan |  |  |  |  | 56,144,000.00
Actual
4 | General Staff training & Development for Service delivery | for staff training & development | LSP/S-WTC/SS/004/21 |  |  | Plan |  |  |  |  | 14,732,000.00
Actual
5 | WITED Conference | for training & development | LSP/S-WTC/SS/005/21 |  |  | Plan |  |  |  |  | 394,400.00
Actual
6 | MTSS Workshop Training | for training & development | LSP/S-WTC/SS/006/21 |  |  | Plan |  |  |  |  | 464,000.00
Actual
7 | Burscon Seminar | for training & development | LSP/S-WTC/SS/007/21 |  |  | Plan |  |  |  |  | 2,900,000.00
Actual
8 | Seminar support for Union Executives | for training & development | LSP/S-WTC/SS/008/21 |  |  | Plan |  |  |  |  | 1,933,333.34
Actual
| PLAN TOTAL |  |  |  |  | Plan |  |  |  |  | 135030066
| ACTUAL TOTAL |  |  |  |  | Actual