## Non-Proc items
0
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: Works & Infrastructure
BUDGET YEAR: 2021
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TOTAL
1 | Enlightment and Campaing | MWI/NP/NM/001/2021 | 4,216,885.34 | Plan |  |  | 1054221.34 |  |  | 1054221.34 |  |  | 1054221.34 |  |  | 1054221.34 | 4,216,885.34
Actual
2 | Special Duty Expenses(Servicing of Mgt.meetings for 12months &Honourarium | MWI/NP/NM/002/2021 | 10,058,979.21 | Plan | 838248.2675 | 838248.27 | 838248.27 | 838248.27 | 838248.27 | 838248.27 | 838248.27 | 838248.27 | 838248.27 | 838248.27 | 838248.27 | 838248.27 | 10058979.2375
Actual
3 | Public Affairs Unit Expenses(for daily printing various publications of Ministry's activities | MWI/NP/NM/003/2021 | 22490054.76 | Plan |  |  | 5622513.69 |  |  | 5622513.69 |  |  | 5622513.69 |  |  | 5622513.69 | 22490054.76
Actual
4 | Legal Expenses | MWI/NP/NM/004/2021 | 4,266,433.13 | Plan |  |  | 1066608 |  |  | 1066608 |  |  | 1066608 |  |  | 1066608 | 4,266,433.13
Actual
5 | Audit Expenses | MWI/NP/NM/005/2021 | 3,613,163.63 | Plan |  |  | 903290.91 |  |  | 903290.91 |  |  | 903290.91 |  |  | 903290.91 | 3,613,163.63
Actual
6 | ICT Unit Expenses | MWI/NP/NM/006/2021 | 3,000,000.00 | Plan |  |  | 750000 |  |  | 750000 |  |  | 750000 |  |  | 750000 | 3,000,000.00
Actual
7 | Procuremunt Unit | MWI/NP/NM/007/2021 | 5,397,938.14 | Plan |  |  | 1349484.535 |  |  | 1349484.535 |  |  | 1349484.535 |  |  | 1349484.535 | 5397938.14
Actual
8 | Awards Rewards and Ceremonies(for meritorious performance of staff) | MWI/NP/NM/008/2021 | 5000000 | Plan | 416666.6667 | 416666.6667 | 416666.6667 | 416666.6667 | 416666.6667 | 416666.6667 | 416666.6667 | 416666.6667 | 416666.6667 | 416666.6667 | 416666.6667 | 416666.6667 | 5000000
Actual
9 | Planning Research & Statistics Units Expenses | MWI/NP/NM/009/2021 | 6293206.09 | Plan |  |  | 1573302 |  |  | 1573302 |  |  | 1573302 |  |  | 1573302 | 6293206.09
Actual

## trg conf wsh
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: WORKS AND INFRASTRUCTURE
BUDGET YEAR: 2021
S/N | Description of Training/Workshop/ Conference | Package No | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | Workshop&Training and Seminars & Conference for Admin Professionals for 200 Nos Officers@ N39,187.89 /Officer and 34 Nos Officers @ N115,258.50/Officer | MWI/S-WTC/SS/001/2021 | To enhance professionalism and efficient service delivery | 234 |  | Plan |  |  |  |  | 11756366.77
Actual
2 | Conference & Seminars for 30 Nos Officer @181,542.65/Officer = 5,446,279.47 and Workshop and Training for 150 Officers for Workshop @ N54,869.49 = 8,230,423.76 fees for Accounting Professionals - ICAN, ANAN NIM,CIPSMN, ICPAN ETC. | MWI/S-WTC/SS/002/2021 | To enhance professionalism and efficient service delivery | 180 |  | Plan |  |  |  |  | 16068001.61
Actual
3 | Workshop&Training for 55 Officer @9,486.93 / Officer = 1,744,770.71 and Seminars & Conference for 50 Officers @ N52,178.10 /Officer = N5,259,650.16 for Mechanical Engineers | MWI/S-WTC/SS/003/2021 | To enhance professionalism and efficient service delivery | 105 |  | Plan |  |  |  |  | 7004420.87
Actual
4 | Workshop&Training for 50 Officers @13,201.77 / Officer = N1,818,586.53 and Seminars & Conference for 50 Officers @ N117,056.33 /Officer = N5,852,816.33 for Electrical Engineers | MWI/S-WTC/SS/004/2021 | To enhance professionalism and efficient service delivery | 100 |  | Plan |  |  |  |  | 7671402.86
Actual
5 | Workshop&Training for 30 Officers @ 56,674.64 / Officer = N1,700,239.08 and Seminars & Conference for 30 Officers @ N105,261.80 /Officer =3,157,854.08 for Architect, Builder and Quantity Surveyors (ABQS) | MWI/S-WTC/SS/005/2021 | To enhance professionalism and efficient service delivery | 60 |  | Plan |  |  |  |  | 6483327.44
Actual
6 | Workshop&Training for 30 Officers @ 55,047.07 / Officer = 1,651,412.03 and Seminars & Conference for 50 Officers @ N82,983.85 /Officer =4,149,192.26 for Civil Engineers (Road Construction) | MWI/S-WTC/SS/006/2021 | To enhance professionalism and efficient service delivery | 80 |  | Plan |  |  |  |  | 5800604.29
Actual
7 | Workshop &Traning for 50 officers @ 25,256.23/ Officer = 1,262,811.38 and Seminar & Conference for 40 Officers @ 103,753.99 = 4,150,159.57 For Road Construction and Rehabilitation Department | MWI/S-WTC/SS/007/2021 | To enhance professionalism and efficient service delivery | 90 |  | Plan |  |  |  |  | 5412970.95
Actual
8 | Workshop&Training for 50 Officers @ 32,825.08 / Officer = 1,641,253.79 and Conference & Seminar for 50 Officers @ 83,079.54/Officer =4,153,976.87 | MWI/S-WTC/SS/008/2021 | To enhance professionalism and efficient service delivery | 100 |  | Plan |  |  |  |  | 4153976.87
Actual
9 | Workshop&Training for 3 Officers @ 468,422.05 / Officer = 1,405,266.14 and Conference & Seminar for 3 Officers @ 1,350,887.13/Officer =4,052,661.40 | MWI/S-WTC/SS/009/2021 | To enhance professionalism and efficient service delivery | 6 |  | Plan |  |  |  |  | 5457927.54
Actual
10 | Retreat for the Management and staff of the Ministry (Hotel Accomodation, Feeding and Incidental for 3 Night) for 70 Staff @142,857.14 /Officer = 10,000,000.00 | MWI/S-WTC/SS/010/2021 | To enhance professionalism and efficient service delivery | 70 |  | Plan |  |  |  |  | 10000000
Actual
11 | Workshop&Training for 150 Officers @ 54,869.49 / Officer = 8,230,423.76 for Human Resources and Training. | MWI/S-WTC/SS/011/2021 | To enhance professionalism and efficient service delivery | 150 |  | Plan |  |  |  |  | 8230423.76
Actual
12 | Short Term Courses for 10 officers at 17,935.82/officer | MWI/S-WTC/SS/012/2021 | To enhance professionalism and efficient service delivery | 10 |  | Plan |  |  |  |  | 179358.2
Actual

## non-cons
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY: MINISTRY OF WORKS AND INFRASTRUCTURE
BUDGET YEAR: 2021
S/N | Contract Description | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
|  | Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
1 | Maintanance of office Building (Directorate) | MWI/S-NC/NS/001/2021 | 1 | 1 | 6670402.26 | <50M | NS | Plan | post | post | 2021-02-05 | N/A | 2021-02-12 | 2021-02-26 | 2021-03-06 | N/A | N/A | Plan | 2021-03-20 | 2021-03-24 |  | 2021-04-14 | 2021-04-28 | 2021-06-16 | 2021-12-16
[8 empty] | Actual | [9 empty] | Actual
2 | Maintenance, Repairs and other Equipment | MWI/S-NC/NS/002/2021 | 1 | 1 | 85919.36 | <50M | NS | Plan | Post | Post | 2021-02-05 | N/A | 2021-02-12 | 2021-02-26 | 2021-03-06 | N/A | N/A | Plan | 2021-03-20 | 2021-03-24 |  | 2021-04-14 | 2021-04-28 | 2021-06-16 | 2021-12-16
[8 empty] | Actual | [9 empty] | Actual
3 | Motor Vehicle Repairs and Maintanance | MWI/S-NC/NS/003/2021 | 1 | 1 | 9594829.03 | <50M | NS | Plan | Post | Post | 2021-02-05 | N/A | 2021-02-12 | 2021-02-26 | 2021-03-06 | N/A | N/A | Plan | 2021-03-20 | 2021-03-24 |  | 2021-04-14 | 2021-04-28 | 2021-06-16 | 2021-12-16
[8 empty] | Actual | [9 empty] | Actual
4 | Maintanance of Office Building (Area Office) | MWI/S-NC/NS/004/2021 | 1 | 1 | 270096.22 | <50M | NS | Plan | Post | Post | 2021-02-05 | N/A | 2021-02-12 | 2021-02-26 | 2021-03-06 | N/A | N/A | Plan | 2021-03-20 | 2021-03-24 |  | 2021-04-14 | 2021-04-28 | 2021-06-16 | 2021-12-16
[8 empty] | Actual | [9 empty] | Actual
5 | Maintanance & Repair of Plants (Maintenace of 25 Generator within Secretariat and Overhauling of 5 Generators) @ 40,000 | MWI/S-NC/NS/005/2021 | 1 | 1 | 1000000 | <50M | NS | Plan | Post | Post | 2021-02-05 | N/A | 2021-02-12 | 2021-02-26 | 2021-03-06 | N/A | N/A | Plan | 2021-03-20 | 2021-03-24 |  | 2021-04-14 | 2021-04-28 | 2021-06-16 | 2021-12-16
[8 empty] | Actual | [9 empty] | Actual
6 | Maintanance of Public Address System | MWI/S-NC/NS/006/2021 | 1 | 1 | 19088.84 | <50M | NS | Plan | Post | Post | 2021-02-05 | N/A | 2021-02-12 | 2021-02-26 | 2021-03-06 | N/A | N/A | Plan | 2021-03-20 | 2021-03-24 |  | 2021-04-14 | 2021-04-28 | 2021-06-16 | 2021-12-16
[8 empty] | Actual | [9 empty] | Actual
7 | Monitoring,Enforcement & Compliance (material testing and law governinig construction of new building) | MWI/S-NC/NS/007/2021 | 1 | 1 | 2811256.84 | <50M | NS | Plan | Post | Post | 2021-02-05 | N/A | 2021-02-12 | 2021-02-26 | 2021-03-06 | N/A | N/A | Plan | 2021-03-20 | 2021-03-24 |  | 2021-04-14 | 2021-04-28 | 2021-06-16 | 2021-12-16
[8 empty] | Actual | [9 empty] | Actual
8 | Janitorial Services(Engagement of janitors within the Ministry) | MWI/S-NC/NS/008/2021 | 1 | 1 | 12000000 | <50M | NS | Plan | Post | Prior | 2021-02-05 | 2021-02-12 | 2021-02-26 | 2021-03-12 | 2021-03-19 | N/A | 2020-03-26 | Plan | 2020-04-02 | 2020-04-07 |  | 2020-04-21 | 2021-05-05 | 2021-06-30 | 2021-12-30
[8 empty] | Actual | [9 empty] | Actual
9 | fuel Dump(Servicing of 1 Fuel Dispenser. | MWI/S-NC/NS/009/2021 |  | 1 | 76541.28 | <50M | NS | Plan | Post | Post | 2021-02-05 | N/A | 2021-02-12 | 2021-02-26 | 2021-03-06 | N/A | N/A | Plan | 2021-03-20 | 2021-03-24 |  | 2021-04-14 | 2021-04-28 | 2021-06-16 | 2021-12-16
[8 empty] | Actual | [9 empty] | Actual
10 | Maintenance of Generators | MWI/S-NC/NS/010/2021 | 1 | 4 | 4000000 | <50M | NS | Plan | Post | Post | 2021-02-05 | N/A | 2021-02-12 | 2021-02-26 | 2021-03-06 | N/A | N/A | Plan | 2021-03-20 | 2021-03-24 |  | 2021-04-14 | 2021-04-28 | 2021-06-16 | 2021-12-16
[8 empty] | Actual | [9 empty] | Actual
11 | Fuel for Generators and Plants | MWI/S-NC/NS/011/2021 | 1 |  | 6000000 | <50M | NS | Plan | Post | post | 2021-02-05 | N/A | 2021-02-12 | 2021-02-26 | 2021-03-06 | N/A | N/A | Plan | 2021-03-20 | 2021-03-24 |  | 2021-04-14 | 2021-04-28 | 2021-06-16 | 2021-12-16
[8 empty] | Actual | [9 empty] | Actual

## consultancy
PROCUREMENT PLAN FOR TRAINING/ CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: Works & Infrastructure
BUDGET YEAR: 2021
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[7 empty] | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
1 | Consultancy Studies on Roads,Bridges, Drainages & Premilinary Works. | MWI/S-C/QCBS/001/2021 | QCBS | Time based | 253009046 | Prior | Plan | 2021-02-03 | 2021-02-17 | 2021-02-24 | 2021-03-23 | 30 03 20201 | 2021-04-06 | 2021-04-27 | 2021-05-04 | 2021-05-11 | 2021-05-18 | 2021-05-25 | 2021-06-01 | 2020-06-29 | 2020-07-01 |  | 2020-07-08 | 2020-07-22 | 2020-08-19 | 2020-08-26 | 2020-09-02
Actual
Plan
Actual

## goods
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: Works and Infrastructure
BUDGET YEAR: 2021
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (1-2wks) | 1-2wks) | (1-2wks) | (1-4 wks) | 48Hrs | 0 | 1wk | (1-2 wks) | (2-4wks)
1 | Procurement of Fire Fighting Equipment for fuel dump | MWI/G/NCB/001/2021 | 1 | 10 | 178026.73 | <10 | NS | Post | Prior | Plan | 2021-02-11 | N/A | 2021-02-18 | 2021-02-25 | 2021-03-05 | N/A | 2021-06-04 | 2021-06-11 |  | 2021-06-18 | 2021-06-25 | 2021-07-09 | 2021-07-16 | 2022-01-18
Actual
2 | Procurement of wheel measures,electrical tools,measuring tapes and tool boxes. | MWI/G/NCB/002/2021 | 1 | 13 | 200965.67 | <10 | NS | Post | Prior | Plan | 2021-02-11 | N/A | 2021-02-18 | 2021-02-25 | 2021-03-05 | N/A | 2021-06-04 | 2021-06-11 |  | 2021-06-18 | 2021-06-25 | 2021-07-09 | 2021-07-16 | 2022-01-18
Actual
3 | Stationery(I). adm -procurement of 10cartons of A4 Paper(SA, PS & A & HR),procurement foolscap paper for (SA, PS, A& HR), Procurement of meeting sheets for(SA, PS, H& HR)-5,371,630.32.(ii) Accts Dept- 1,455,921.63.(iii) PRS Units- 91,530.18,(iv)MECH- 1,779,191.46,(v)ABQS- 1,478,540.64(vi) RC-655,081.71,(vii) RMR- 133,727.52,(viii) PP &D- 333,239.13,(viii) Support services- 1,391,687.99. | MWI/G/NS/003/2021 | 1 | 9 | 12690550.58 | <50M | NS | Post | Prior | Plan | 2021-02-11 | 2021-02-18 | 2021-02-18 | 2021-02-25 | 2021-03-05 | 2021-04-08 | 2021-06-04 | 2021-06-11 |  | 2021-05-15 | 2021-06-25 | 2021-07-09 | 2021-07-16 | 2022-01-18
Actual
4 | Procurement of Computer Accessories, components, engineering software packages and other consumables. | MWI/G/NS/004/2021 | 1 |  | 3364791 | <10M | NS | Post | Post | Plan | 2021-02-11 | N/A | 2021-02-18 | 2021-02-25 | 2021-03-05 | N/A | 2021-06-04 | 2021-06-11 |  | 2021-06-18 | 2021-06-25 | 2021-07-09 | 2021-07-16 | 2022-01-18
Actual
5 | Drawing Office Materials (i)MECH- N168,014.89, (ii)ABQS- 61,370.97,(iii) RC- N63,629.44,(iv) RMR- N101,443.14,(v)PP&D Units- N25,018.77. | MWI/G/NS/005/2021 | 1 |  | 419477.19 | <10M | NS | Post | Post | Plan | 2021-02-11 | N/A | 2021-02-18 | 2021-02-25 | 2021-03-05 | N/A | 2021-06-04 | 2021-06-11 |  | 2021-06-18 | 2021-06-25 | 2021-07-09 | 2021-07-16 | 2022-01-18
Actual
6 | Office Furniture & Equipment | MWI/G/NS/006/2021 | 1 |  | 14224129.72 | <50M | NS | Post | prior | Plan | 2021-02-11 | N/A | 2021-02-18 | 2021-02-25 | 2021-03-05 | N/A | 2021-06-04 | 2021-06-11 |  | 2021-06-18 | 2021-06-25 | 2021-07-09 | 2021-07-16 | 2022-01-18
Actual
7 | Procurement of Uniform & Protective Outfits | MWI/G/NS/007/2021 | 2 | 1 | 7311304.44 | <10M | NS | Post | Post | Plan | 2021-02-11 | N/A | 2021-02-18 | 2021-02-25 | 2021-03-05 | N/A | 2021-06-04 | 2021-06-11 |  | 2021-04-10 | 2021-06-25 | 2021-07-09 | 2021-07-16 | 2022-01-18
Actual
8 | Printing of one no. Information Booklets | MWI/G/NS/008/2021 | 1 |  | 27476.32 | <10M | NS | Post | Post | Plan | 2021-02-11 | N/A | 2021-02-18 | 2021-02-25 | 2021-03-05 | N/A | 2021-06-04 | 2021-06-11 |  | 2021-06-18 | 2021-06-25 | 2021-07-09 | 2021-07-16 | 2022-01-18
9 | Publication and Documentation | MWI/G/NS/009/2021 | 1 |  | 1414055.77 | <10M | NS | Post | Post | Plan | 2021-02-11 | N/A | 2021-02-18 | 2021-02-25 | 2021-03-05 | N/A | 2021-06-04 | 2021-06-11 |  | 2021-06-18 | 2021-06-25 | 2021-07-09 | 2021-07-16 | 2022-01-18
10 | Fuel for generators and plants | MWI/G-F/NS/010/2021 | 1 |  | 6000000 | <10M | NS | Post | Post | Plan | 2021-02-11 | N/A | 2021-02-18 | 2021-02-25 | 2021-03-05 | N/A | 2021-06-04 | 2021-06-11 |  | 2021-06-18 | 2021-06-25 | 2021-07-09 | 2021-07-16 | 2022-01-18
11 | Special duties Expense (Procurement of jessys, Boot, Hand Gloves, Socks and Ball (ADMIN, ABQS, RC, RMR) | MWI/G/NS/011/2021 | 1 |  | 15826798.76 | <50M | NS | Post | prior | Plan | 2021-02-11 | N/A | 2021-02-18 | 2021-02-25 | 2021-03-05 | N/A | 2021-06-04 | 2021-06-11 |  | 2021-06-18 | 2021-06-25 | 2021-07-09 | 2021-07-16 | 2022-01-18
12 | ICT (Procurement of ICT basic Computers & Equipment, Consumables IT equipment | MWI/G/NS/012/2021 | 1 |  | 1000000 | <10M | NS | Post | Post | Plan | 2021-02-11 | N/A | 2021-02-18 | 2021-02-25 | 2021-03-05 | N/A | 2021-06-04 | 2021-06-11 |  | 2021-06-18 | 2021-06-25 | 2021-07-09 | 2021-07-16 | 2022-01-18
Actual

## works
PROCUREMENT PLAN FOR WORKS
Works and Infrastructure
BUDGET YEAR: 2021
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Construction of Oke Ogbe, Badagry L.G.A | MWI/W/NCB/001/2021 | 1 | 277750222.5249 | >100M | NCB | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 |  | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
2 | Construction of Community road with Bridge/Divine Avenue Okota in Oshodi-Isolo L.G.A | MWI/W/NCB/002/2021 | 1 | 180937463.2498 | >100M | NCB | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 |  | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
3 | Construction of Lateef Onigemo street Network of Roads, Ifako Gbagada in Kosofe L.G.A | MWI/W/NS/003/2021 | 1 | 26038636.5157 | <50M | NS | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 |  | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
4 | Construction of Kehinde Ogunnusi Street Ifako Gbagada in Kosofe L.G.A | MWI/W/NS/004/2021 | 1 | 13088615.8365 | <50M | NS | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
5 | Construction of Eruwen Road, Eruwen in ikorodu L.G.A | MWI/W/NCB/005/2021 | 1 | 178085659.8576 | >100M | NCB | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
6 | Ashabi Taiwo - Olafisoye Street | MWI/W/NS/006/2021 | 1 | 42844159.5797 | <50M | NS | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
7 | Construction Of Grammar School/Abacus road, Agbowa in Epe L.G.A | MWI/W/NS/007/2021 | 1 | 44555583.5853 | <50M | NS | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
8 | Apeka Community Road | MWI/W/NCB/008/2021 | 1 | 53663961.3276 | >50M | NCB | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
9 | Emmanuel Odusina Street , Oko Oba | MWI/W/NS/009/2021 | 1 | 6136796.0494 | <10M | NS | BOQ | Post | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
10 | Isiaka/Ladipo Street, Oko Oba | MWI/W/NS/010/2021 | 1 | 19347945.0494 | <50M | NS | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
11 | James okiki Street, Oko Oba | MWI/W/NS/011/2021 | 1 | 17826164.0756 | <50M | NS | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
12 | Mabayoje Street, Oko Oba | MWI/W/NS/012/2021 | 1 | 10810942.8209 | <50M | NS | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
13 | Odutola/Araromi Street, Oko Oba | MWI/W/NS/013/2021 | 1 | 12899163.2478 | <50M | NS | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
14 | Olaolu Drive | MWI/W/NS/014/2021 | 1 | 9581655.7572 | <50M | NS | BOQ | Post | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
15 | Dada Onijamo Street | MWI/W/NS/015/2021 | 1 | 14396350.6719 | <50M | NS | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
16 | Chidi Street | MWI/W/NS/016/2021 | 1 | 5747233.5931 | <10M | NS | BOQ | Post | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
17 | Cardoso Street | MWI/W/NS/017/2021 | 1 | 6141063.955 | <10M | NS | BOQ | Post | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
18 | Akpolo/Oyedeji Streets | MWI/W/NS/018/2021 | 1 | 33741411.1649 | <50M | NS | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
19 | Construction of Abaranje Road Network with Bridge | MWI/W/NCB/019/2021 | 1 | 482359700.9065 | >100M | NCB | BOQ | Prior | Plan | Prior | 2021-02-25 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
20 | Construction of Ogunlana/Bayo Oyegbemi/ Bamileke Streets | MWI/W/NCB/020/2021 | 1 | 91599076.6915 | >50M | NCB | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
21 | Yetkem Road | MWI/W/NCB/021/2021 | 1 | 128491174.5897 | >100M | NCB | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
22 | Construction of Ige,Amoke Alasela,Raji Rasak,Samson Akinola | MWI/W/NCB/022/2021 | 1 | 111513926.59 | >100M | NCB | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
23 | Construction of Tutuola,Olajide,Amdalat,Iyabo Shitta,Bey , Ebenezer,Akinboye,Sawyer | MWI/W/NCB/023/2021 | 1 | 69205566.7126 | >50M | NCB | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
24 | Irepodun-Ojokoro Street | MWI/W/NCB/024/2021 | 1 | 75574850.2489 | >50M | NCB | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
25 | Temidire Street, Agbado- Oke Odo | MWI/W/NCB/025/2021 | 1 | 133829429.8983 | >100M | NCB | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
26 | Akesan-Abaranje Link Bridge Works | MWI/W/NCB/026/2021 | 1 | 100000000 | >100M | NCB | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
27 | Construction of Ajibola, Hassan/Olaiya Suaju, Streets (Akesan Bridge Abaranje Side) | MWI/W/NCB/027/2021 | 1 | 56642225.2971 | >50M | NCB | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
28 | Construction Rabiat Ogedegbe Street Alimosho (Akesan Bridge Abaranje Side) | MWI/W/NCB/028/2021 | 1 | 62895464.0685 | >50M | NCB | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
29 | Construction of Fagbile road | MWI/W/NS/029/2021 | 1 | 44409798.7043 | <50M | NS | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
30 | Construction of Ijegun-Isheri Osun | MWI/W/NCB/030/2021 | 1 | 203144103.343 | >100M | NCB | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
31 | Ashipa Road | MWI/W/NCB/031/2021 | 1 | 101091640.9905 | >100M | NCB | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
32 | Shekoni Street | MWI/W/NS/032/2021 | 1 | 31021008.594 | <50M | NS | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
33 | Part Parent's Choice Street | MWI/W/NCB/033/2021 | 1 | 63124336.7072 | >50M | NCB | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
34 | Part Lucky Nwanneka Street | MWI/W/NS/034/2021 | 1 | 16951643.8967 | <50M | NS | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
[9 empty] | Actual |  | Prior
35 | Approaches To Lasu-Iba/Ayobo Link Bridge | MWI/W/NS/035/2021 | 1 | 33081280.3918 | <50M | NS | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
36 | Construction of Bridge Along Oko Oloyun- Ayobo Road | MWI/W/NCB/036/2021 | 1 | 335586093.9912 | >100M | NCB | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
37 | Old Ojo Road | MWI/W/ICB/037/2021 | 1 | 689778902.2153 | >500M | ICB | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
38 | Iyekantan Street/Nduka Igbokwe Street with Bridge | MWI/W/NCB/038/2021 | 1 | 82001274.8427 | >50M | NCB | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
39 | Moradeyo Street/Akinpelu/Caso/Oremeji/Baale Street | MWI/W/NCB/039/2021 | 1 | 82085937.1494 | >50M | NCB | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
40 | Comfort Street | MWI/W/NS/040/2021 | 1 | 9696531.5888 | <10M | NS | BOQ | Post | Plan | Post | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
41 | Baruwa/Nosiru/Karimu Street | MWI/W/NS/041/2021 | 1 | 46585321.5258 | <50M | NS | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
42 | Construction of Fadaini-Obale Road | MWI/W/NCB/042/2021 | 1 | 81590378.834 | <50M | NCB | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
43 | Construction of Mosadaolorun Street | MWI/W/NS/043/2021 | 1 | 26253057.959 | <50M | NS | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
44 | Construction of Akosile/Alh.Kadiri Streets | MWI/W/NS/044/2021 | 1 | 27653792.7014 | <50M | NS | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
45 | Construction of Alli Dogo Street | MWI/W/NS/045/2021 | 1 | 12335624.8 | <50M | NS | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
46 | Construction of Onigemo Street | MWI/W/NS/046/2021 | 1 | 27352100.5589 | <50M | NS | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
47 | Agbovipe- Erekiti Road with Bridge | MWI/W/NCB/047/2021 | 1 | 279955148.5908 | >100M | NCB | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
48 | Agric-Salu Road | MWI/W/NCB/048/2021 | 1 | 117718902.6083 | >100M | NCB | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
49 | Joton Bridge | MWI/W/NCB/049/2021 | 1 | 74412137.31 | >50M | NCB | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
50 | Oke Afo-Ilogbo-Yesi-Agunmo-Ijotun Road Phase II | MWI/W/NCB/050/2021 | 1 | 254801599.9595 | >100M | NCB | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
51 | Tori-Lovi Road | MWI/W/NCB/051/2021 | 1 | 157623725.3076 | >100M | NCB | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
52 | Yafin-Access Road | MWI/W/NCB/052/2021 | 1 | 52965582.4959 | >50M | NCB | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
53 | Palace- Famolu Road | MWI/W/NCB/053/2021 | 1 | 79779833.71 | >50M | NCB | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
54 | Gbaji Community Road | MWI/W/NS/054/2021 | 1 | 17884437.914 | <50M | NS | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
55 | Ganyigbo Agonvi Road | MWI/W/NCB/055/2021 | 1 | 51271271.0332 | >50M | NCB | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
56 | Farasime Yeke-Me Ring in Owode | MWI/W/NCB/056/2021 | 1 | 58492128.0306 | >50M | NCB | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
57 | Atinporomeh Link Road in Mowo, Olorunda | MWI/W/NCB/057/2021 | 1 | 112890872.0007 | >100M | NCB | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
58 | Zonal Model College Road | MWI/W/NS/058/2021 | 1 | 16801782.6561 | <50M | NS | BOQ | Prior | Plan | Post | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
59 | Muibi Falolu | MWI/W/NS/059/2021 | 1 | 7112662.9963 | <10M | NS | BOQ | Post | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
60 | Ajike Hassan | MWI/W/NS/060/2021 | 1 | 5056545.5791 | <10M | NS | BOQ | Post | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
61 | Johnson Ibiyemi | MWI/W/NS/061/2021 | 1 | 5283196.8217 | <10M | NS | BOQ | Post | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
62 | Stella Adebayo | MWI/W/NS/062/2021 | 1 | 5919469.877 | <10M | NS | BOQ | Post | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
63 | Idowu Apete | MWI/W/NS/063/2021 | 1 | 3141195.985 | <10M | NS | BOQ | Post | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
64 | Dualization of Alpha Beach (Now Engr. Murphy Adetoro) | MWI/W/NCB/064/2021 | 1 | 102641455.9663 | >100M | NCB | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
65 | Chief Augustine Anozie Street/Shallom Close (Lekki Phase I) | MWI/W/NCB/065/2021 | 1 | 15568059.5375 | <50M | NS | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
66 | Dan Ogbeide Close, Off Oyinbo Adjaho Crescent (Lekki Phase I) | MWI/W/NS/066/2021 | 1 | 4337114.7432 | <10M | NS | BOQ | Post | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
67 | Ogombo - Sangotedo Road | MWI/W/NCB/067/2021 | 1 | 142360572.5781 | >100M | NCB | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
68 | Okun Ajah- Mopo Akinlade- Mopo Ijebu-Mushiri Kogo Road | MWI/W/NCB/068/2021 | 1 | 313738537.7897 | >100M | NCB | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
69 | Saliu Obodo-Oke Ira Nla/Olokonta-Sangotedo Road | MWI/W/NCB/069/2021 | 1 | 252506093.702 | >100M | NCB | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
70 | Otulu-Ilagbo-Idata-Igbolomi PH.1 | MWI/W/NCB/070/2021 | 1 | 56697861.2706 | >50M | NCB | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
71 | Elerangbe-Dongo-Itoomu RD. | MWI/W/ICB/071/2021 | 1 | 1802496196.7975 | >1B | ICB | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
72 | Igando Oloja PH.II | MWI/W/NCB/072/2021 | 1 | 56263565.5226 | >50M | NCB | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
73 | Awoyaya-Gbetu Iwerekun-Orile With Bridge PH.II | MWI/W/NCB/073/2021 | 1 | 375411065.4045 | >100M | NCB | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
74 | Access Road Leading To Omu Resort | MWI/W/NS/074/2021 | 1 | 38694235.4236 | <50M | NS | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
75 | Akande/Yetunde Babarinsa | MWI/W/NS/075/2021 | 1 | 21453091.9364 | <50M | NS | BOQ | Prior | plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
76 | Coker/Oluwakemi | MWI/W/NS/076/2021 | 1 | 29235208.7187 | <50M | NS | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
77 | Ashabi Taiwo - Olafisoye Street | MWI/W/NS/077/2021 | 1 | 42844159.5797 | <50M | NS | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
78 | Ileogbo Street | MWI/W/NS/078/2021 | 1 | 34479641.0077 | <50M | NS | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
79 | Sola Martins | MWI/W/NCB/079/2021 | 1 | 52621725.0898 | >50M | NCB | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
80 | Construction Of Adeyemi Alao Street, Oke-Ira | MWI/W/NS/080/2021 | 1 | 6808880.3868 | <10M | NS | BOQ | Post | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
81 | Upgrading of Electrical Distribution/ Equipment within the Secretariat | MWI/W/NS/081/2021 | 1 | 22623849.04 | <50M | NS | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
82 | Resuscitation of lift in the Secretariat Complex | MWI/W/NCB/082/2021 | 1 | 206951094.49 | >100M | NCB | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
83 | Upgrading of Mechanical Workshop | MWI/W/NCB/083/2021 | 1 | 63252261.21 | >50M | NCB | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
84 | Rehabilitation of office Buildings/office Buildings | MWI/W/NCB/084/2021 | 1 | 169465313.34 | >100M | NCB | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
85 | Renovation and Maintanance of Staff Quarters in the State for 2021 | MWI/W/ICB/085/2021 | 1 | 941145656.08 | >500M | NCB | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
86 | Renovation of Area/Zonal Offices | MWI/W/NCB/086/2021 | 1 | 75000000 | >50M | NCB | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
87 | Construction of Akilo Ogba Road | MWI/W/NCB/087/2021 | 1 | 80107559.9895 | >50M | NCB | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
88 | Sholafun/Owode Streets | MWI/W/NS/088/2021 | 1 | 26797758.9673 | <50M | NS | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Actual
89 | Olisa Shobowale/Otunba Yemi Oshikoya | MWI/W/NS/089/2021 | 1 | 30796018.2798 | <50M | NS | BOQ | Prior | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
90 | Construction of Agric-Ori Okuta Road, Imota | MWI/W/NCB/090/2021 | 1 | 385002649.3043 | <500M | NCB | BOQ | Prior | Actual | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-06-25 | 2022-12-27
Plan
91 | Eyita Ojokoro Road | MWI/W/NCB/091/2021 | 1 | 293135765.7878 | <500M | NCB | BOQ | Prior | Actual | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Plan
92 | Laketu Road Lucky Fibre | MWI/W/NCB/092/2021 | 1 | 44697976.0457 | <50M | NS | BOQ | Prior | Actual | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Prior
93 | Imota by Pass road, Imota | MWI/W/NCB/093/2021 | 1 | 51056070.2338 | >50M | NCS | BOQ | Prior | Actual | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Prior
94 | Irepodun Street | MWI/W/NS/094/2021 | 1 | 24324322.0865 | <50M | NS | BOQ | Prior | Actual | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Prior
95 | Aladelola Street, Ikosi | MWI/W/NCB/095/2021 | 1 | 58777010.9225 | >50M | NCS | BOQ | Prior | Actual | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Prior
96 | Omojuwa Estate ,Mile 12 | MWI/W/NCB/096/2021 | 1 | 66395493.2934 | >50M | NCS | BOQ | Prior | Actual | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Prior
97 | Irepodun Street,Mile 12 | MWI/W/NS/097/2021 | 1 | 24324322.0865 | <50M | NS | BOQ | Prior | Actual | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Prior
98 | Princess/Isale Gangan Street | MWI/W/NS/098/2021 | 1 | 26809949.6088 | <50M | NS | BOQ | Prior | Actual | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Prior
99 | Iwaya Road | MWI/W/NCB/099/2021 | 1 | 53395387.7899 | >50M | NCB | BOQ | Prior | Prior | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
100 | Construction of Layi Oyekanmi Street | MWI/W/NS/100/2021 | 1 | 37154632.3712 | <50M | NS | BOQ | Prior | Actual | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Prior
101 | Construction of Folami/Labinjo/Olaniyan Street | MWI/W/NS/101/2021 | 1 | 38678077.1942 | <50M | NS | BOQ | Prior | Actual | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Prior
102 | Chief Adegoke/Blue Shield Road | MWI/W/NS/102/2021 | 1 | 49994618.3016 | <50M | NS | BOQ | Prior | Actual | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Prior
103 | Prince Kosoko Elemijaye | MWI/W/NCB/103/2021 | 1 | 50322304.8074 | >50M | NCB | BOQ | Prior | Actual | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Prior
104 | Baale-Raji off Raji fashola Road | MWI/W/NS/104/2021 | 1 | 31210419.2924 | <50M | NS | BOQ | Prior | Actual | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Prior
105 | Beach/Baale Road off Etegbin Road | MWI/W/NS/105/2021 | 1 | 44526074.1182 | <50M | NS | BOQ | Prior | Actual | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-27
Prior

## Ongoing works
PROCUREMENT PLAN FOR WORKS ONGOING PROJECT
Works and Infrastructure
BUDGET YEAR: 2020
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Construction of Network of Roads within Soluyi Community in Kosofe L.G.A | MWI/W/NCB/001/2021 | 1 | 111543348.17 | >100M | NCB | BOQ | Prior | Plan | Prior
Actual
2 | Construction of Additional Works in Phase I and Construction of Phase II of Network of Roads (Anipole Crescent, Sosanya Street) with Soluyi in Kosofe Local Government Area | MWI/W/NCB/002/2021 | 1 | 72977960.05 | >50M | NCB | BOQ | Prior | Plan | Prior
Actual
3 | Construction of Network of Strategic Roads in Ojokoro LCDA, Ifako - Ijaiye L.G.A - Phase 1 | MWI/W/NCB/003/2021 | 1 | 482222237.86 | <500M | NCB | BOQ | Prior | Plan | Prior
Actual
4 | Construction of Network of strategic Roads in Ojokoro LCDA, Ifako - Ijaiye L.G.A - Phase 2 | MWI/W/ICB/004/2021 | 1 | 936246132.87 | >500M | ICB | BOQ | Prior | Plan | Prior
Actual
5 | Construction of Ilaje Road with Jetty and Car Park, Bariga in Somolu L.G.A | MWI/W/NCB/005/2021 | 1 | 228929242.86 | >100M | NCB | BOQ | Prior | Plan | Prior
Actual
6 | Construction of constituency Roads within the State | MWI/W/ICB/006/2021 | 1 | 683550022.17 | >500M | ICB | BOQ | Prior | Plan | Prior
Actual
7 | Construction of Network of Roads in Ojodu LCDA in Ikeja L.G.A | MWI/W/NCB/007/2021 | 1 | 128954294.48 | >100M | NCB | BOQ | Prior | Plan | Prior
Actual
8 | Reconstruction/Dualization of Irede Road in Amuwo Odofin Local Government Area. | MWI/W/NCB/008/2021 | 1 | 214836283.61 | >100M | NCB | BOQ | Prior | Plan | Prior
Actual
9 | Construction of Abule Ado in Awuwo Odofin LGA (Phase III) | MWI/W/NS/009/2021 | 1 | 117219870.28 | >100M | NCB | BOQ | Prior | Plan | Prior
Actual
10 | Construction of Samuel Ekundayo/Toga Road in Badagry LGA | MWI/W/ICB/010/2021 | 1 | 664763447.48 | >500M | ICB | BOQ | Prior | Plan | Prior
Actual
11 | Construction of Social Science Road Unilag Estate, Magodo. | MWI/W/NS/011/2021 | 1 | 40185186.49 | <50M | NS | BOQ | Prior | Plan | Prior
Actual
12 | Emergency Repair Works on the Apapa - Oworonshoki Expressway (CH.17+500 to CH.16+000) Oshodi Bound Carriageway | MWI/W/NCB/012/2021 | 1 | 55089342.99 | >50M | NCB | BOQ | Prior | Plan | Prior
Actual
13 | Construction of Remi Oyefiade Street | MWI/W/NS/013/2021 | 1 | 21952776.63 | <50M | NS | BOQ | Prior | Plan | Prior
Actual
14 | Construction Of Adeyemi Thomas Street, Agbowa - Ikosi L.C.D.A in Epe L.G.A | MWI/W/NS/014/2021 | 1 | 25021062.01 | <50M | NS | BOQ | Post | Plan | Prior
Actual
15 | Reconstruction of Odunsi Road, Bariga | MWI/W/NCB/015/2021 | 1 | 63880529.7 | >50M | NCB | BOQ | Prior | Plan | Prior
Actual
16 | Construction of College Road, Igando in Alimosho L.G.A | MWI/W/NS/016/2021 | 1 | 19177372.32 | <50M | NS | BOQ | Post | Plan | Prior
Actual
17 | Construction of Hospital/Ibafon/Kudaisi Streets | MWI/W/NCB/017/2021 | 1 | 76949961.64 | >50M | NCB | BOQ | Post | Plan | Prior
Actual
18 | Reconstruction of Otto Wharf Road | MWI/W/NCB/018/2021 | 1 | 205675264.35 | >100M | NCB | BOQ | Prior | Plan | Prior
Actual
19 | Consruction of Bolaji Taylor/ Kayode Alabi Street | MWI/W/NS/019/2021 | 1 | 25115741.56 | <50M | NS | BOQ | Prior | Plan | Prior
Actual
20 | Construction of Afromedia - Adaloko Road, Phase III in Ojo LGA | MWI/W/NCB/020/2021 | 1 | 201689554.46 | >100M | NCB | BOQ | Prior | Plan | Prior
Actual
21 | Reconstruction of Roads (Royal Palm Drive, Acacia Drive and Mahogany Street) with Osborne Foreshore Estate Phase II, Ikoyi , Eti - Osa L.G.A | MWI/W/NCB/021/2021 | 1 | 83960248.82 | >50M | NCB | BOQ | Prior | Plan | Prior
Actual
22 | Construction of Moradeun Alabi Cresent, Magodo Phase II off CMD road and Sectional rehabilitation of Adekunle banjo road (1750m2) | MWI/W/NS/022/2021 | 1 | 25577036.82 | <50M | NS | BOQ | Prior | Plan | Prior
Actual
23 | Lagos Bus Reform Project: Development of Depot at Anthony | MWI/W/NCB/023/2021 | 1 | 58905707.47 | >50M | NCB | BOQ | Prior | Plan | Prior
Actual
24 | Lagos Bus Reform Project: Development of Depot at Yaba | MWI/W/NCB/024/2021 | 1 | 78880457.82 | >50M | NCB | BOQ | Prior | Plan | Prior
Actual
25 | Lagos Bus Reform Project: Development of Depot at Oshodi | MWI/W/NCB/025/2021 | 1 | 99004769.15 | >50M | NCB | BOQ | Prior | Plan | Prior
Actual
26 | Lagos Bus Reform Project: Development of Depot at Oshodi, Yaba and Anthony (Tools and Equipment) | MWI/W/NCB/026/2021 | 1 | 215466478.24 | >100M | NCB | BOQ | Prior | Plan | Prior
Actual
27 | Construction of Four Number Theatres at Ikeja, Epe, Badagry and Alimosho | MWI/W/NCB/027/2021 | 1 | 138391468.96 | >100M | NCB | BOQ | Prior | Plan | Prior
Actual
28 | Dualization of Bisola Durosinmi Etti Drive/ Hakeem Dickson Road, Lekki Phase 1( including Additional Works) (Reviewed) | MWI/W/NCB/028/2021 | 1 | 355463381.7 | >100M | NCB | BOQ | Prior | Plan | Prior
Actual
29 | Reconstruction of Oba Aladejobi Street/ Harnold Shodipo Crescent at Ikeja GRA Lagos | MWI/W/NCB/029/2021 | 1 | 80101842.86 | >50M | NCB | BOQ | Prior | Plan | Prior
Actual
30 | Construction of Arowojobe Estate Link Bridge and Part of Approach Road at Mende Maryland | MWI/W/NCB/030/2021 | 1 | 52915953.86 | >50M | NCB | BOQ | Prior | Plan | Prior
Actual
31 | Complection of Igbo- Nla Model College Road (Phase 2) Eredo, In Epe Local Government Area. | MWI/W/NS/031/2021 | 1 | 29425748.5 | <50M | NS | BOQ | Prior | Plan | Prior
Actual
32 | Dualisation & Improvement of Isheri Olofin - Iba -Ojo (LASU) Road,PHASE II Alimosho/ Ojo L.G.A | MWI/W/NCB/032/2021 | 1 | 301388898.66 | >100M | NCB | BOQ | Prior | Plan | Prior
Actual
33 | Construction Of 4- Legged Pedestrian Bridges at identified locations within Lagos Metropolis | MWI/W/NCB/033/2021 | 1 | 70324076.35 | >50M | NCB | BOQ | Prior | Plan | Prior
Actual
34 | Construction of Ajara Agelasho Poka/Erekiti Road In Badagry LGA | MWI/W/NCB/034/2021 | 1 | 154043214.87 | >100M | NCB | BOQ | Prior | Plan | Prior
Actual
35 | Construction of Aradagun-Iworo-Ajido (Phase I) Bridge Only (Section 1) Badagry LGA | MWI/W/NCB/035/2021 | 1 | 234413587.85 | >100M | NCB | BOQ | Prior | Plan | Prior
Actual
36 | Replacement of Failed Culvert at Aradagun - Iworo- Ajido (PHASE I) Bridge Only (Section 1) Badagry LGA | MWI/W/NS/036/2021 | 1 | 32361049.8 | <50M | NS | BOQ | Prior | Plan | Prior
Actual
37 | Construction of Balogun/ Sunny/ Alade/ Alade/Adebisi/Adebosi/ Adeyanju network of roads in Epe L.G.A | MWI/W/NCB/037/2021 | 1 | 74342595 | >50M | NCB | BOQ | Prior | Plan | Prior
Actual
38 | Construction of Access Road and Car park at Five- A- Side Centre,Ikoyi, Phase II (Access Road only) Eti-osa L.G.A | MWI/W/NS/038/2021 | 1 | 29810646.56 | <50M | NS | BOQ | Prior | Plan | Prior
Actual
39 | Construction of unity /first avenue /ivoty road, Osapa West Eti-osa L.G.A | MWI/W/NS/039/2021 | 1 | 35709815.34 | <50M | NS | BOQ | Prior | Plan | Prior
Actual
40 | Construction of Agbe Road Ifako- Ijaiye L.G.A | MWI/W/NCB/040/2021 | 1 | 65830434.85 | >50M | NCB | BOQ | Post | Plan | Prior
Actual
41 | Construction of Odogbolu street Ketu Kosofe L.G.A | MWI/W/NS/041/2021 | 1 | 32148149.19 | <50M | NS | BOQ | Prior | Plan | Prior
Actual
42 | Construction of Adisa Balogun/Igboho Streets Agboyi - Ketu Kosofe L.G.A | MWI/W/NS/042/2021 | 1 | 23441358.78 | <50M | NS | BOQ | Prior | Plan | Prior
Actual
43 | Construction of Rosanwo Street Surulere L.G.A | MWI/W/NS/043/2021 | 1 | 23106482.23 | <50M | NS | BOQ | Prior | Plan | Prior
Actual
44 | Construction of Ogunsina Ogundele way Kosofe L.G.A | MWI/W/NS/044/2021 | 1 | 35307963.48 | <50M | NS | BOQ | Prior | Plan | Prior
Actual
45 | Construction of Harvey /access road to grammar school Lagos Mainland L.G.A | MWI/W/NS/045/2021 | 1 | 34157408.52 | <50M | NS | BOQ | Prior | Plan | Prior
Actual
46 | Construction of Afromedia - Adaloko Road, Phase I in Ojo LGA | MWI/W/NCB/046/2021 | 1 | 122315410.25 | >100M | NCB | BOQ | Prior | Plan | Prior
Actual
47 | Construction of Leadforte Gate Avenue /Portion of Hon.Idowu Eletu/Ajelogo Street,Awoyaya Ibeju- Lekki L.G.A | MWI/W/NS/047/2021 | 1 | 45811112.6 | <50M | NS | BOQ | Prior | Plan | Prior
Actual
48 | Construction of Bankole/ Shodimu Streets with multi-cell culvert Kosofe L.G.A | MWI/W/NCB/048/2021 | 1 | 61349580.81 | >50M | NCB | BOQ | Prior | Plan | Prior
Actual
49 | Construction of BolajiOmupo Street Somolu L.G.A | MWI/W/NS/049/2021 | 1 | 17413580.81 | <50M | NS | BOQ | Prior | Plan | Prior
Actual
50 | Construction of Access Roads (Okusanya Network of Roads) to the Dana Plane Crash Location (Phase II) Ifako Ijaiye L.G.A | MWI/W/NS/050/2021 | 1 | 23106482.23 | <50M | NS | BOQ | Prior | Plan | Prior
Actual
51 | Construction of Link Bridge (Ikosi -Shangisha) Ikosi, ketu Kosofe L.G.A | MWI/W/NS/051/2021 | 1 | 37853025.29 | <50M | NS | BOQ | Prior | Plan | Prior
Actual
52 | Grading of odufuwa Road (Ogombo Village) Eti Osa L.G.A | MWI/W/NS/052/2021 | 1 | 30452253.44 | <50M | NS | BOQ | Prior | Plan | Prior
Actual
53 | Grading of Bisi Aromasodun Street Eti Osa L.G.A | MWI/W/NS/053/2021 | 1 | 31343025.08 | <50M | NS | BOQ | Prior | Plan | Prior
Actual
54 | Construction of Tijani/Adesegun Street Agege L.G.A | MWI/W/NS/054/2021 | 1 | 40185186.49 | <50M | NS | BOQ | Prior | Plan | Prior
Actual
55 | Construction of Oshitelu Street Agege L.G.A | MWI/W/NS/055/2021 | 1 | 16743827.7 | <50M | NS | BOQ | Prior | Plan | Prior
Actual
56 | Construction of Adedeji/ Omidiji / Omo Isreal/ Lomuwa/ Ogundare/ Oduroye Streets Alimosho L.G.A | MWI/W/NS/056/2021 | 1 | 19691314.02 | <50M | NS | BOQ | Prior | Plan | Prior
Actual
57 | Construction of Old Otta Ibari Road Alimosho L.G.A | MWI/W/NCB/057/2021 | 1 | 58029437.97 | >50M | NCB | BOQ | Prior | Plan | Prior
Actual
58 | Construction of Idowu Fashola/ Obashoro Streets Ipaja Alimosho L.G.A | MWI/W/NS/058/2021 | 1 | 41725618.64 | <50M | NS | BOQ | Prior | Plan | Post
Actual
59 | Construction of Karimu Laka & Bamishile Streets Alimosho L.G.A | MWI/W/NCB/059/2021 | 1 | 75012348.11 | >50M | NCB | BOQ | Post | Plan | Prior
Actual
60 | Construction of Jimoh Ajao/ Arowojobe Streets Alimosho L.G.A | MWI/W/NS/060/2021 | 1 | 36836420.95 | <50M | NS | BOQ | Post | Plan | Prior
Actual
61 | Construction of Alhaji Alli Street / Eweje Close ( Access to ogba Magistrate Court) Ikeja L.G.A | MWI/W/NS/061/2021 | 1 | 43746852.64 | <50M | NS | BOQ | Post | Plan | Prior
Actual
62 | Construction of Road & Car Park at Wapa Skill Acquisition Centre, Ojodu Kososfe L.G.A | MWI/W/NS/062/2021 | 1 | 40130185.86 | <50M | NS | BOQ | Post | Plan | Prior
Actual
63 | Reconstruction of Isashi Road Ojo L.G.A | MWI/W/NS/063/2021 | 1 | 167438277.03 | >100M | NCB | BOQ | Post | Plan | Prior
Actual
64 | Construction of Oyataki/ Egbatedo Street Agege L.G.A | MWI/W/NS/064/2021 | 1 | 35603365.04 | <50M | NS | BOQ | Prior | Plan | Prior
Actual
65 | Construction of Showonuola Street Agege L.G.A | MWI/W/NS/065/2021 | 1 | 28771883.33 | <50M | NS | BOQ | Post | Plan | Prior
Actual
66 | Construction of Efon Alaiye Street Alimosho L.G.A | MWI/W/NS/066/2021 | 1 | 29910463.62 | <50M | NS | BOQ | Post | Plan | Prior
Actual
67 | Reconstruction of Gaskiya College Road/Sari- Iganmu Road Apapa L.G.A | MWI/W/ICB/067/2021 | 1 | 756821021.19 | >500M | ICB | BOQ | Prior | Plan | Prior
Actual
68 | Upgrading of Roads within Apapa Central Business District, in Apapa LGA (Marine Road, Marine Road (2nd Segment), Bombay Crescent-Randle Road, Ibikunle Akintoye Street, Commercial Road and Burma Road) Phase III Apapa L.G.A | MWI/W/ICB/068/2021 | 1 | 1138580283.83 | >1B | ICB | BOQ | Prior | Plan | Prior
Actual
69 | Completion of Iyafin Access Road, Badagry L.G.A | MWI/W/NCB/069/2021 | 1 | 72989924.66 | >50M | NCB | BOQ | Prior | Plan | Prior
Actual
70 | Construction of Dele Ogunbowale Street Eti osa L.G.A | MWI/W/NS/070/2021 | 1 | 28570957.4 | <50M | NS | BOQ | Prior | Plan | Prior
Actual
71 | Construction of Ajelogo Street Ibeju Lekki L.G.A | MWI/W/NS/071/2021 | 1 | 32165585.34 | <50M | NS | BOQ | Prior | Plan | Prior
Actual
72 | Construction / Rehabilitation of Akinde/Adetiba Road Ifako Ijaiye L.G.A | MWI/W/NS/072/2021 | 1 | 26790124.33 | <50M | NS | BOQ | Prior | Plan | Prior
Actual
73 | Construction of Oju-Emuren Street Ikorodu L.G.A | MWI/W/NS/073/2021 | 1 | 14466667.14 | <50M | NS | BOQ | Prior | Plan | Prior
Actual
74 | Construction of Agunfoye Road, Igbogbo Phase I Ikorodu L.G.A | MWI/W/NS/074/2021 | 1 | 26790124.33 | <50M | NS | BOQ | Prior | Plan | Prior
Actual
75 | Reconstruction of Mushin -Isolo Road Mushin L.G.A | MWI/W/NCB/075/2021 | 1 | 180833339.2 | >100M | NCB | BOQ | Prior | plan | Prior
Actual
76 | Completion of Ariyo (Mile 10) Ira-Muwo Bridge- Phase I Ojo L.G.A | MWI/W/NCB/076/2021 | 1 | 86264200.33 | >50M | NCB | BOQ | Prior | Plan | Prior
Actual
77 | Construction of Ipaye - Mission- Isolo Road Mushin L.G.A | MWI/W/NCB/077/2021 | 1 | 106490744.19 | >100M | NCB | BOQ | Prior | Plan | Prior
Actual
78 | Construction of Bale Shekoni Street/Rev. Ezekiel Close, by Chivita Avenue, Ajao Estate Oshodi Isolo L.G.A | MWI/W/NS/078/2021 | 1 | 32148149.19 | <50M | NS | BOQ | Prior | Plan | Prior
Actual
79 | Construction of Immam Thanni Road Network, Ijeshatedo, Itire Ikate Surulere L.G.A | MWI/W/NCB/079/2021 | 1 | 59942903.18 | >50M | NCB | BOQ | Prior | Plan | Prior
Actual
80 | Construction Of 4- Legged Pedestrian Bridges at identified locations within Lagos Metropolis | MWI/W/NS/080/2021 | 1 | 46882717.57 | <50M | NS | BOQ | Post | Plan | Prior
Actual
81 | Construction of Apata Street , Oke - Ira, In Ikeja L.G.A | MWI/W/NS/081/2021 | 1 | 13930864.65 | <50M | NS | BOQ | Prior | Plan | Prior
Actual
82 | Construction of Adekunle Kuye Street Surulere L.G.A | MWI/W/NS/082/2021 | 1 | 39582408.69 | <50M | NS | BOQ | Prior | Plan | Prior
Actual
83 | Construction of Miyaki road Oworonshoki Kosofe L.G.A | MWI/W/NS/083/2021 | 1 | 26455247.77 | <50M | NS | BOQ | Prior | Plan | Prior
Actual
84 | Construction of Oje Imiavian Street, Oregun, Ikeja | MWI/W/NS/084/2021 | 1 | 44966836.81 | <50M | NS | BOQ | Prior | Plan | Prior
Actual
85 | Completion of Adekunle Deen/ Obasuah/ Ekunjimi/Omoniyi/ Raimi Ogunderu Streets Apapa L.G.A | MWI/W/NS/085/2021 | 1 | 45543211.35 | <50M | NS | BOQ | Prior | Plan | Prior
Actual
86 | Construction of Wilmer Crescent / Akpiri Street and Wilmer/ Osho Street with Bridge in Ajeromi Ifelodun LGA (Phase I) (Additional Works) | MWI/W/NS/086/2021 | 1 | 24217562.2 | <50M | NS | BOQ | Prior | Plan | Prior
Actual
87 | Construction of jamiu Eletu Road & Outfall in Ibeju-Lekki LGA | MWI/W/NS/087/2021 | 1 | 36367593.77 | <50M | NS | BOQ | Prior | Plan | Prior
Actual
88 | Construction of Johnson Umejei Close, Ajao Estate.L: 462m, W8m | MWI/W/NS/088/2021 | 1 | 15090481.17 | <50M | NS | BOQ | Prior | Plan | Prior
Actual
89 | Rehabilitation/Construction of Amuwo Odofin L.G.A Length -11248m2 | MWI/W/NS/089/2021 | 1 | 13742190.76 | <50M | NS | BOQ | Prior | Actual | Prior
Plan
90 | Construction of Access Road to Epe Dumpsite , Epe Local Govt. Area. Length-9476m2 | MWI/W/NS/90/2021 | 1 | 12290185.7 | <50M | NS | BOQ | Prior | Actual | Prior
Plan