## Non-Proc_items
	PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS

	MINISTRY/ AGENCY:		STATE TREASURY OFFICE
	BUDGET YEAR:		2021

S/N	Contract Description	Package Number	Budget Available (=N=)	Plan/Actual	JAN	FEB	MARCH	APRIL	MAY	JUNE	JULY	AUGUST	SEPT.	OCT.	NOV.	DEC.	TOTAL
1	Personnel Cost	STO/NP/NM/001/21	353,234,380.99	Plan	29,436,198.42	29,436,198.42	29,436,198.42	29,436,198.42	29,436,198.42	29,436,198.42	29,436,198.42	29,436,198.42	29,436,198.42	29,436,198.42	29,436,198.42	29,436,198.42	353,234,380.99
				Actual

2	Support Staff	STO/NP/NM/002/21	2,000,600,000.00	Plan	166,716,666.67	166,716,666.67	166,716,666.67	166,716,666.67	166,716,666.67	166,716,666.67	166,716,666.67	166,716,666.67	166,716,666.67	166,716,666.67	166,716,666.67	166,716,666.67	2,000,600,000.00
				Actual

3	Travel&Transport	STO/NP/NM/003/21	4,000,000.00	Plan	333,333.33	333,333.33	333,333.33	333,333.33	333,333.33	333,333.33	333,333.33	333,333.33	333,333.33	333,333.33	333,333.33	333,333.33	4,000,000.00
				Actual

4	Utility Services	STO/NP/NM/004/21	4,500,000.00	Plan	375,500.00	375,500.00	375,500.00	375,500.00	375,500.00	375,500.00	375,500.00	375,500.00	375,500.00	375,500.00	375,500.00	375,500.00	4,500,000.00
				Actual

5	Electricity	STO/NP/NM/005/21	1,000,000.00	Plan	83,333.33	83,333.33	83,333.33	83,333.33	83,333.33	83,333.33	83,333.33	83,333.33	83,333.33	83,333.33	83,333.33	83,333.33	1,000,000.00
				Actual

6	Renewal of ISP (Internet Service Provider)	STO/NP/NM/006/21	2,000,000.00	Plan	166,666.67	166,666.67	166,666.67	166,666.67	166,666.67	166,666.67	166,666.67	166,666.67	166,666.67	166,666.67	166,666.67	166,666.67	2,000,000.04
				Actual

7	Upkeep of archieves allowance	STO/NP/NM/007/21	500,000.00	Plan	41,666.67	41,666.67	41,666.67	41,666.67	41,666.67	41,666.67	41,666.67	41,666.67	41,666.67	41,666.67	41,666.67	41,666.67	500,000.00
				Actual

10	Bank charges	STO/NP/NM/010/21	225,000,000.00	Plan	18,750,000.00	18,750,000.00	18,750,000.00	18,750,000.00	18,750,000.00	18,750,000.00	18,750,000.00	18,750,000.00	18,750,000.00	18,750,000.00	18,750,000.00	18,750,000.00	225,000,000.00
				Actual

11	Banking Operation service expenses	STO/NP/NM/011/21	2,000,000.00	Plan	166,666.67	166,666.67	166,666.67	166,666.67	166,666.67	166,666.67	166,666.67	166,666.67	166,666.67	166,666.67	166,666.67	166,666.67	2,000,000.00
				Actual

12	Committee allowance	STO/NP/NM/012/21	10,000,000.00	Plan	833,333.33	833,333.33	833,333.33	833,333.33	833,333.33	833,333.33	833,333.33	833,333.33	833,333.33	833,333.33	833,333.33	833,333.33	10,000,000.00
				Actual

				Actual
				Plan
				Actual
15				Plan
				Actual
16				Plan
				Actual

## trg_conf_wsh
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: STATE TRAESURY OFFICE
BUDGET YEAR: 2021

S/N	Description of Training/Workshop/ Conference	Objective of Training/Workshop/Conference	No. of Participants	Duration	Plan vs Actual	Venue	Tuition Fee	Transport Fare	Allowance	Total Cost
1	Capacity Building	HR & Training	200	5 Days	Plan	Lagos	50,000,000.00	30,000,000.00	20,000,000.00	100,000,000.00
					Actual
2	Professional meetings/Conference/Seminars	HR & Training	300	4Days	Plan	Abuja	80,000,000.00	30,000,000.00	40,000,000.00	150,000,000.00
					Actual
3	Training and Staff development	Training	50	4 Days	Plan	Lagos	2,250,416.00	1,326,875.00	2,222,709.00	5,800,000.00
					Actual
4	IPSAS Training	Accountants Training	200	5 Days	Plan	Lagos	170,000,000.00	166,696,000.00	30,000,000.00	366,696,000.00
					Actual
5	Oracle		250	5 Days	Plan	Lagos	150,000,000.00	70,000,000.00	187,696,000.00	407,696,000.00
		12i training			Actual
6	Accountant Retreat	Workshop for head of departments and units	300	3 Days	Plan	Abuja	100,000,000.00	50,000,000.00	50,000,000.00	200,000,000.00
					Actual
7					Plan
					Actual
8					Plan
					Actual

## non-cons
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY: STATE TRAESURY OFFICE
BUDGET YEAR: 2021

Contract Description		BASIC DATA					Pre-or Post Qualification	Prior or Post review	BIDDING PERIOD			BID EVALUATION			CONTRACT FINALIZATION
		Package Number		Lot No.	No of Unit	Budget Available in Naira	Approval Threshold	Procurement Method	Plan Vs Actual			Bid Prep & Submission by MDA (1-4wks)	PPA No Objection Date (1-2wks)	Bid Invitation Date (1-2wks)	Bid Closing & Opening Date (2-6 wks)	Submission of Bid Evaluation Report (1-2 wks)	Minutes of Negotiation (1 wk)	PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval	Plan Vs Actual	Mr. Governor's Approval (1-4 wks)	Contract Amount in Naira	Date Contract Signature (4-6 wks)	Mobilization Advance Payment (2-4 wks)	Complete Delivery/Install (2-8 wks)	Inspection & Final Acceptance
Professional / Consultancy fees	Motor Vehicle maintenance		STO/NCS/NS/003/20			10,850,000.00	<20M	NS		POST	PRIOR	25/2/21	11/3/2021	18/3/21	1/4/21	15/4/21	29/4/21	6-5-2021	Plan	20/5/2021		19/6/2021	2-7-2021	15/07/21	22/07/2021
					Actual					Actual
Maintenance of office building		STO/NCS/NS/004/20				3,700,000.00	<10M	NS	Plan	POST	POST	3-2-2021	10-2-2021	24/2/21	4-3-2021	10-3-2021	17/3/21	24/3/21	Plan	31/3/21		28/4/21	14/5/2021	28/5/21	2-6-2021
					Actual					Actual
					Plan					Plan
					Actual					Actual
					Plan					Plan
					Actual					Actual
					Plan					Plan
					Actual					Actual
					Plan					Plan
					Actual					Actual
					Plan					Plan
					Actual					Actual
					Plan					Plan
					Actual					Actual

## consultancy
	PROCUREMENT PLAN FOR CONSULTING SERVICES
	MINISTRY/ AGENCY: STATE TREASURY OFFICE
	BUDGET YEAR: 2020

	PROJECT IDENTIFICATION			BASIC DATA			Plan vs. Actual	PREPARATION / (EOI & TOR)		SHORTLISTING			REQUEST FOR PROPOSALS		TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N)					APPROVAL		CONTRACT FINALIZATION			CONTRACT IMPLEMENTATION
S/N	Project Description	Project Package	Selectn Method	Lump sum / or / Time-Based	Estimated Amount / in N '000	Prior/ Post Review		Prep & Submission / by MDA	PPA No-Objection	MDA Advertise for EOI	Submission of EOI Report & Draft RFP to PPA	PPA No-Objection	Invitation to Submit Proposals	Submission of Proposals by Shortlisted Consultants	Opening/ Evaluation of Technical Proposals	Opening/ Evaluation of Financial Proposals	Subm of / Eval Report to PPA / (T) (F)	Negotiation Meeting	PPA No-Objection	Mr. Governor's approval.	Register Approval with PPA	Contract Amount in / N '000	Notification of Award	Contract Award	Mobilization/ / Advance / Payment	Draft / Report	Final / Report	Final / Cost
					0.00		Plan	1-4 wks	1-2 wks	1wk	2-4 weeks	1-2 wks	1-2 wks	3-6 wks	1-2 wks	1-2 wks	1wk	1-2 wks	1-2 wks	1-4 wks	48 Hrs	0.00	1 wk	2wks	2-4 wks	1-2 wks	1-2 wks	0.00
						Actual
1	Automated Multichannel Payment Solution and Retrieving	STO/S-C/QCBS/001/21	QCBS	LS	18,500,000.00	Prior	Plan	3-3-2021	24/03/21	31/03/21	14/04/21	21/04/21	28/04/21	5-5-2021	25/05/21			15/06/21	29/06/21	13/07/21	15/07/21		22/07/21	5/8/21	19/8/21	26/8/21	2/9/21
						Actual
2	Professional / Consultancy fees	STO/S-C/QCBS/001/21	QCBS	LS	15,705,512,145.00	Prior	Plan	9/3/21	16/3/21	30/3/21	6/4/21	13/4/21	21-04-21	12-May-21	18-05-21			25/05/21	2/6/21	16/6/21	18/6/21		25/6/21	5/7/21	19/7/21	28/7/21	4/8/21
						Actual
						Plan
						Actual
						Plan
						Actual
						Plan
						Actual
						Plan
						Actual

## goods
	PROCUREMENT PLAN FOR GOODS.
	MINISTRY/AGENCY: STATE TREASURY OFFICE
	BUDGET YEAR: 2021

S/N	CONTRACT IDENTIFICATION				BASIC DATA					Plan Vs Actual	BIDDING PERIOD (DATES)				BID EVALUATION (DATES)		APPROVAL		CONTRACT FINALIZATION
	Contract Description		Package Number		Lot No	No of Unit	Budget Available in Naira	Approval Threshold (=N=)	Procurement Method	Pre-or Post Qualification	Prior or Post Review		Bid Prep & Submission by MDAs	PPA No Objection Date	Bid Invitation Date	Bid Closing & Opening	Submission of Bid Evaluation Report (	PPA Issue Certificate of Compliance	Mr. Governor's Approval	Register Mr. Governor's approval with PPA	Contract Amount	Notification of Award	Contract Award	Mobilization Advance Payment	Substantial Completion/Install	Inspection & Final Acceptance
						(1-4wks)	(1-2wks)	(1-2wks)	(2-6 wks)	1-2wks)	(1-2wks)	(1-4 wks)	(48 Hours)	0.00	(1 wk)	(1-2 wks)	(2-4wks)

1	Stationery		STO/G-F/NS/001/21			various	7,550,000.00	<10M	NS	POST	POST	Plan	2/3/2021	NA	16/3/2021	30/3/2021	6/4/2021	NA	20/4/2021			27/4/2021	5-May-2021	19/5/2021		26/5/2021
						Actual

2	Uniform &Protective outfit		STO/G-F/NS/002/21			various	1,000,000.00	<10M	NS	POST	POST	Plan	9/3/2021	NA	23/3/2021	6/4/2021	13/4/2021	NA	29/4/2021			11/5/2021	25/5/2021	01/06/2021		9-6-2021
						Actual

3	Printing of security forms		STO/G/NS/003/21			various	200,000,000.00	<50M	NS	POST	PRIOR	Plan	6/4/2021	13/4/2021	20/4/2021	4/5/2021	18/5/2021	25/5/2021	1-Jun-2021			8-6-2021	22/06/2021	6-7-2021		14/07/2021
						Actual

4	Payroll preparation consumables		STO/G/NCB/004/21			various	30,000,000.00	<500M	NCB	POST	PRIOR	Plan	4/3/2021	9/3/2021	16/3/2021	30/3/2021	7/4/2021	14/4/2021	21/4/2021			29/5/2021	5/6/2021	12/6/2021		19/6/2021
						Actual

5	Motor vehicle fuel consumption		STO/G/NS/005/21			various	11,500,000.00	>50M	NS	POST	PRIOR	Plan	20/1/21	27/1/2021	3-2-2021	17/2/21	24/2/21	2-3-2021	9-3-2021			16/3/21	23/3/21	6-4-2021		10-4-2021
						Actual

6	ICT Accounting reporting tools		STO/G/NS/006/21			various	50,000,000.00	<100m	NS	POST	PRIOR	Plan	6/4/2021	13/4/2021	20/4/2021	4/5/2021	18/5/2021	25/5/2021	1-Jun-2021			8-6-2021	22/06/2021	6-Jul-2021		14/07/2021

7	Office furniture and fittings		STO/G/NS/007/21			various	50,000,000.00	<100M	NS	POST	PRIOR	Plan	4/3/2021	9/3/2021	16/3/2021	30/3/2021	7/4/2021	14/4/2021	21/4/2021			29/5/2021	5/6/2021	12/6/2021		19/6/2021
						Actual

8	Project financial management expenses		STO/G/NS/008/21			various	15,000,000	<50M	NS	POST	PRIOR	Plan	9/3/2021	16/3/2021	23/3/2021	6/4/2021	13/4/2021	20/4/2021	29/4/2021			11/5/2021	25/5/2021	01/06/2021		9-6-2021
						Actual

9	Publicity expenses		STO/G/NS/009/21			various	5,000,000.00	<100M	NS	POST	POST	Plan	23/3/2021	6/4/2021	13/4/2021	20/4/2021	29/4/2021	6/5/20	13/5/21			27/5/21	3/6/21	24/6/21		3-7-2021
						Actual

10	Planning expenses		STO/G/NS/010/21			various	5,000,000.00	<10M	NS	POST	POST	Plan	20/1/21	27-1-21	3-2-21	16-2-21	23-2-21	9-3-21	23-3-21			19-4-21	17-5-21	31-5-21		1-6-21
						Actual

11	Internal Audit Expenses		STO/G/NS/011/21			various	5,000,000.00	<10M	NS	POST	POST	Plan	20/1/21	27-1-21	3-2-21	16-2-21	23-2-21	9-3-21	23-3-21			19-4-21	17-5-21	31-5-21		1-6-21
						Actual

12	Procurement Expenses		STO/G/NS/012/21			various	5,000,000	<10M	NS	POST	POST	Plan	20/1/21	27-1-21	3-2-21	16-2-21	23-2-21	9-3-21	23-3-21			19-4-21	17-5-21	31-5-21		1-6-21
						Actual

13	Information technology expenses		STO/G/NS/013/21			various	5,000,000.00	<10M	NS	POST	POST	Plan	20/1/21	27-1-21	3-2-21	16-2-21	23-2-21	9-3-21	23-3-21			19-4-21	17-5-21	31-5-21		1-6-21
						Actual

14	Special duty expenses		STO/G/NS/014/21			various	40,000,000.00	<50M	NS	POST	PRIOR	Plan	20/1/21	27-1-21	3-2-21	16-2-21	23-2-21	9-3-21	23-3-21			19-4-21	17-5-21	31-5-21		1-6-21	1-6-21
						Actual

15	Investigation expenses		STO/G/NS/015/21			various	2,000,000.00	<10M	NS	POST	POST	Plan	20/1/21	27-1-21	3-2-21	16-2-21	23-2-21	9-3-21	23-3-21			19-4-21	17-5-21	31-5-21		1-6-21
						Actual

16	Treasury operation expenses		STO/G/NS/016/21			Various	2,000,000.00	<10M	NS	POST	POST	Plan	20/1/21	27-1-21	3-2-21	16-2-21	23-2-21	9-3-21	23-3-21			19-4-21	17-5-21	31-5-21		1-6-21
						Actual

## works
	PROCUREMENT PLAN FOR WORKS
	MINISTRY: STATE TREASURY OFFICE
	BUDGET YEAR: 2020

S/N	CONTRACT IDENTIFICATION			BASIC DATA					Plan Vs Actual	Prior or Post Review	BIDDING PERIOD (DATES)				BID EVALUATION		APPROVAL		CONTRACT FINALISATION
	Contract Description		Package Number	Lot Number	Budget Available in Naira	Approval Threshold	Procurement Method	Lump Sum or Bill of Quantity	Pre-or Post Qualification			Bid Prep & Submission by MDAs	PPA No Objection	Bid Invitation Date	Bid Closing & Opening	Submission of Bid Evaluation Report	PPA Issue Certificate of Compliance	Mr. Governor's Approval	Register Mr. Governor's approval with PPA	Contract Amount	Notification of Award	Contract Award	Mobilization Advance Payment	Substantial Completion/Install	Inspection & Final Acceptance
						PRIOR	(1-4wks)	(1-2wks)	(1-2wks)	(2-6 wks)	(1-2wks)	(1-2wks)			0.00	(1 wk)	(1-2 wks)	(2-4wks)

1	Construction of centralised store for seurity documents		STO/W/NCB/002/20		83,726,031	<100M	NCB	BOQ	POST	Plan	PRIOR	11/3/20	18/3/20	25/3/20	8/4/20	15/4/20	22/4/20				20/5/20	3/6/20	17/6/20	24/6/20	26/6/20
						Actual

3						Plan
						Actual
4						Plan
						Actual
						Plan
						Actual
						Plan
						Actual

## Cover_Page
		LAGOS STATE GOVERNMENT
		STATE TREASURY OFFICE
		PROCUREMENT PLAN
YEAR 2021