## Non-Proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: GENERAL HOSPITAL BADAGRY |  | GENERAL HOSPITAL BADAGRY
BUDGET YEAR: 2021 |  | 2021
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TOTAL
1 | PAYMENT OF ELECTRICITY BILL | PPA/NP/NM/001/20 |  | Plan | 354166 | 354166 | 354166 | 354166 | 354166 | 354166 | 354166 | 354166 | 354166 | 354166 | 354166 | 354166 | 4250000
Actual
2 |  |  |  | Plan
Actual
3 |  |  |  | Plan
Actual
4 |  |  |  | Plan
Actual
5 |  |  |  | Plan
Actual
6 |  |  |  | Plan
Actual
7 |  |  |  | Plan
Actual
8 |  |  |  | Plan
Actual
9 |  |  |  | Plan
Actual
10 |  |  |  | Plan
Actual

## trg conf wsh
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: GENERAL HOSPITAL BADAGRY
BUDGET YEAR: 2021 |  |  |  | 2020 |  | 2020
S/N | Description of Training/Workshop/ Conference | Package Number | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | ADVANCE MANAGEMENT/LEADERSHIP | PPA/S-WTC/SS/001/21 | WORKSHOP | 4PARTICIPANT |  | Plan | ASCON | 500000 | 250000 | 250000 | 1000000
Actual
2 | COWLSO | PPA/S-WTC/SS/003/21 | NOT YET KNOWN | 5PARTICIPANT |  | Plan | NOT KNOWN YET | 250000 | 200000 | 250000 | 700000
Actual
3 | [5 empty] | Plan
Actual
Plan
Actual
5 | [5 empty] | Plan
Actual
6 | [5 empty] | Plan
Actual
7 | [5 empty] | Plan
Actual
8 | [5 empty] | Plan
Actual
9 | [5 empty] | Plan
Actual
10 | [5 empty] | Plan
Actual
11 | [5 empty] | Plan
Actual
12 | [5 empty] | Plan
[6 empty] | Actual |  |  |  |  | 1810000

## non-cons
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY:
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY: |  | GENERAL HOSPITAL | [14 empty] | GENERAL HOSPITAL BADAGRY
BUDGET YEAR: |  | 2021 | [14 empty] | 2021
Contract Description | BASIC DATA | [7 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
| Package Number |  | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
MAINTENANCE OF OFFICE BUILDING | PPA/S-NS-F/001/21 |  | 1 |  | 600000 | <20M | NS | Plan | POST | POST | 2021-05-04 | 2021-06-03 | 2021-06-25 | 2021-07-13 | 2021-08-03 | 2021-08-13 | N/A | Plan | N/A | N/A |  | 2021-09-14 | N/A | 2021-10-05
[8 empty] | Actual | [9 empty] | Actual
MOTOR VEHICLE MAINTENANCE AND REPAIRS | PPA/S-NS-F/002/21 |  | 1 |  | 600000 | <20M | NS | Plan | POST | POST | 2021-06-15 | 2021-06-22 | 2021-06-29 | 2021-07-13 | 2021-07-20 | 2021-07-27 | N/A | Plan | N/A | N/A |  | 2021-10-08 | N/A | 2021-08-24
[8 empty] | Actual | [9 empty] | Actual
TRAVEL & TRASPORT | PPA/S-NS-F/003/21 |  | 1 |  | 600000 | <20M | NS | Plan | POST | POST | 2021-06-29 | 2021-06-07 | 2021-07-13 | 2021-07-27 | 2021-03-08 | 2021-10-08 | N/A | Plan | N/A | N/A |  | 2021-08-24 | N/A | 2021-07-09
[8 empty] | Actual | [9 empty] | Actual
GENERAL UTILITY | PPA/S-NS-F/004/21 |  | 1 |  | 600000 | <20M | NS | Plan | POST | POST | 2021-07-13 | 2021-07-20 | 2021-07-27 | 2021-10-08 | 2021-08-17 | 2021-08-24 | N/A | Plan | N/A | N/A |  | 2021-07-09 | N/A | 2021-09-21
[8 empty] | Actual | [9 empty] | Actual
MISCELLANOUS | PPA/S-NS-F/005/21 |  | 1 |  | 600000 | <20M | N/S | Plan | POST | POST | 2021-07-27 | 2021-03-08 | 2021-10-08 | 2021-08-24 | 2021-08-31 | 2021-07-09 | N/A | Plan | N/A | N/A |  | 2021-09-14 | N/A | 2021-09-28
[8 empty] | Actual | [9 empty] | Actual
ELECTRICITY | PPA/S-NS-F/006/21 |  | 1 |  | 2400000 | <20M | N/S | Plan | POST | POST | 2021-03-16 | 2021-04-13 | 2021-05-04 | 2021-06-01 | 2021-06-29 | 2021-07-13 | N/A | Plan | N/A | N/A |  | 2021-08-10 | N/A | 2021-09-01
[8 empty] | Actual | [9 empty] | Actual
SERVICING OF 500KVA GENERATING PLANT | PPA/S-NS-F/007/21 |  | 1 |  | 1200000 | <20M | N/S | Plan | POST | POST | 2021-01-04 | 2021-02-05 | 2021-02-12 | 2021-03-01 | 2021-03-17 | 2021-03-29 | N/A | Plan | N/A | N/A |  | 2021-04-30 | N/A | 2021-05-17
[8 empty] | Actual | [9 empty] | Actual
SERVICING OF 250KVA GENERATING PLANT | PPA/S-NS-F/008/21 |  | 1 |  | 1200000 | <20M | N/S | Plan | POST | POST | 2021-01-04 | 2021-01-21 | 2021-01-20 | 2021-02-15 | 2021-01-26 | 2021-03-08 | N/A | Plan | N/A | N/A |  | 2021-04-02 | N/A | 2021-04-20
[8 empty] | Actual | [9 empty] | Actual
OVERHAULING OF 500 KVA GENERATING PLANT | PPA/S-NS-F/009/21 |  | 1 |  | 600000 | <20M | N/S | Plan | POST | POST | 2021-03-01 | 2021-03-22 | 2021-04-12 | 2021-04-30 | 2021-05-17 | 2021-05-26 | N/A | Plan | N/A | N/A |  | 2021-06-21 | N/A | 2021-07-12
[8 empty] | Actual | [9 empty] | Actual
OVERHAULING OF 250 KVA GENERATING PLANT | PPA/S-NS-F/0010/21 |  | 1 |  | 600000 | <20M | N/S | Plan | POST | POST | 2021-03-22 | 2021-04-30 | 2021-05-10 | 2021-06-04 | 2021-06-21 | 2021-07-05 | N/A | Plan | N/A | N/A |  | 2021-08-02 | N/A | 2021-08-31
[8 empty] | Actual | [9 empty] | Actual

## consultancy
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/ AGENCY:
BUDGET YEAR:
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[5 empty] | 0 |  | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual

## goods
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY:GENERAL HOSPITAL BADAGRY
| BUDGET YEAR: YEAR 2020 | BUDGET YEAR:- 2021
S/N | CONTRACT IDENTIFICATION |  |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description |  | Package No | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[12 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | PROCUREMENT /PRINTING OF MEDICAL FORMS AND CARDS |  | PPA/G-F/NS/OO1/21 | 1 |  | 15000000 | <50M | NS | POST | PRIOR | Plan | 2021-01-04 |  | 2021-01-21 | 2021-02-12 | 2021-03-05 |  | N/A | N/A |  | 2021-03-15 | 2021-03-31 | N/A
Actual
2 | PROCUREMENT OF FORMALIN |  | PPA/G-F/NS/002/21 | 1 |  | 15000000 | <50M | NS |  | PRIOR | Plan | 2021-01-13 |  | 2021-03-02 | 2021-03-22 | 2021-04-12 |  | N/A | N/A |  | 2021-04-23 | 2021-05-04 | N/A
[9 empty] | POST |  | Actual
3 | PROCUREMENT OF FOOD ITEMS PERISHABLE & NON PERISHABL. |  |  | 1 |  | 20000000 | <50M | NS | POST | POST | Plan | 2021-03-02 |  | 2021-02-22 | 2021-03-12 | 2021-03-31 |  | N/A | N/A |  | 2021-04-12 | 2021-04-21 | N/A
Actual
4 | PROCUREMENT OF MEDICAL GAS (OXYGEN) |  | PPA/G-F/NS/004/21 | 1 |  | 10000000 | <20M | NS | POST | POST | Plan | 2021-02-17 |  | 2021-03-10 | 2021-03-30 | 2021-04-12 |  | N/A | N/A |  | 2021-04-13 | 2021-04-22 | N/A
Actual
5 | PROCUREMENT OF STATIONERIES |  | PPA/G-F/NS/004/21 | 1 |  | 600000 | <10M | NS | POST | POST | Plan | 2021-02-03 |  | 2021-03-19 | 2021-04-09 | 2021-04-30 |  | N/A | N/A |  | 2021-05-10 | 2021-05-28 | N/A
Actual
6 | MOTOR VEHICLE FUEL CONSUMPTION INCIDENCE |  | PPA/G-F/NS/005/21 | 1 |  | 649992 | <10M | N/S | POST | POST | Plan | 2021-03-16 |  | 2021-03-30 | 2021-04-23 | 2021-05-07 |  | N/A | N/A |  | 2021-05-17 | 2021-06-04 | N/A
Actual
7 | OPERATION/ SURGICAL CONSUMABLES |  | PPA/G-F/NS/006/21 | 1 |  | 40000000 | <50M | NS | POST | POST | Plan | O4/01/2021 |  | 2021-01-20 | 2021-02-18 | 2021-02-26 |  | N/A | N/A |  | 2021-03-05 | 2021-03-26 | N/A
Actual
8 | PROCUREMET ANAESTHESIA CONSUMABLES |  | PPA/G-F/NS/007/21 | 1 |  | 10000000 | <20M | NS | POST | POST | Plan | 2021-01-20 |  | 2021-10-04 | 2021-10-18 | 2021-03-20 |  | N/A | N/A |  | 2021-01-04 | 2021-04-13 | N/A
Actual
9 |  | PROCURERMENT OF LABORATORY CONSUMABLES | PPA/G-F/NS/OO8/21 | 1 |  | 55000000 | <100M | NS | POST | POST | Plan | 2021-01-13 |  | 2021-03-02 | 2021-02-17 | 2021-09-03 |  | N/A | N/A |  | 2021-03-23 | 2021-06-04 | N/A
Actual
10 |  | PROCUREMENTY OF MORTUARY COMSUMABLES | PPA/G-F/NS/09/21 | 1 |  | 20000000 | <50M | NS | POST | POST | Plan | 2021-10-02 |  | 2021-02-24 | 2021-03-16 | 2021-02-26 |  | N/A | N/A |  | 2021-03-10 | 2021-04-30 | N/A
Actual
11 |  | PROCUREMENT OD DENTAL CONSUMABLES | PPA/G-F/NS/010/21 | 1 |  | 10000000 | <20M | NS | POST | POST | Plan | 2021-10-02 |  | 2021-02-03 | 2021-02-24 | 2021-03-12 |  | N/A | N/A |  | 2021-03-26 | 2021-04-12 | N/A
Actual
12 |  | PROCUREMENT OF DELIVERY CONSUMABLES | PPA/G-F/NS/011/21 | 1 |  | 20000000 | <50M | NS | POST | POST | Plan | 2021-01-20 |  | 2021-03-02 | 2021-02-22 | 2021-03-08 |  | N/A | N/A |  | 2021-03-15 | 2021-04-01 | N/A
Actual
13 |  | PROCUREMENT OF PHYSIOTHERAPY CONSUMABLES | PPA/G-F/NS/012/21 | 1 |  | 5000000 | <10M | NS | POST | POST | Plan | 2021-10-04 |  | 2021-10-22 | 2021-11-08 | 2021-11-19 |  | N/A | N/A |  | 2021-12-06 | 2021-12-17 | N/A
[10 empty] | POST | Actual
14 |  | PROCUREMENT OF DRESSING CONSUMABLES | PPA/G-F/NS/013/21 | 1 |  | 3000000 | <10M | NS | POST | POST | Plan | 2021-02-15 |  | 2021-03-05 | 2021-03-24 | 2021-03-15 |  | N/A | N/A |  | 2021-03-26 | 2021-04-14 | N/A
Actual
15 |  | PROCUREMENT OF HOSPITAL MATTRESS, MAKINTOCH & BEDSHEETS | PPA/G-F/NS/014/21 | 1 |  | 15000000 | <20M | NS | P0ST | POST | Plan | 2021-05-05 |  | 2021-05-24 | 2021-06-14 | 2021-06-28 |  | N/A | N/A |  | 2021-07-08 | 2021-07-26 | N/A
Actual
16 |  | PROCUREMENT OF ADMISSION PACK COMSUMABLES | PPA/G-F/NS/015/21 | 1 |  | 15000000 | <20M | NS | POST | POST | Plan | 2021-06-01 |  | 2021-06-18 | 2021-07-09 | 2021-07-29 |  | N/A | N/A |  | 2021-08-16 | 2021-08-31 | N/A
Actual
17 |  | PAYMENT FOR BLOOD SCREENIG | PPA/G-F/NS/016/21 | 1 |  | 15000000 | <20M | NS | POST | POST | Plan | 2021-01-13 |  | 2021-02-08 | 2021-03-12 | 2021-03-31 |  | N/A | N/A |  | 2021-04-15 | 2021-05-17 | N/A
Actual
18 |  | PROCUREMENT OF EYE CONSUMABLES | PPA/G-F/NS/017/21 | 1 |  | 13000000 | <20M | NS | POST | POST | Plan | 2021-05-03 |  | 2021-05-28 | 2021-06-14 | 2021-06-30 |  | N/A | N/A |  | 2021-07-05 | 2021-07-23 | N/A
Actual
19 |  | PROCUREMENT OF SCAN/XRAY CONSUMABLE | PPA/G-F/NS/018/21 | 1 |  | 35000000 | <50M | NS | POST | POST | Plan | 2021-02-15 |  | 2021-03-01 | 2021-03-26 | 2021-03-09 |  | N/A | N/A |  | 2021-03-26 | 2021-04-09 | N/A
Actual
20 |  | PROCUREMENT OF ORTHOPAEDIC CONSUMABLES | PPA/G-F/NS/019/21 | 1 |  | 10000000 | <20M | NS | POST | POST | Plan | 2021-09-03 |  | 2021-09-22 | 29/20/2021 | 2021-11-12 |  | N/A | N/A |  | 2021-11-19 | 2021-12-03 | N/A
Actual
21 |  | SCHOOL OF ANAESTHESIA | PPA/G-F/NS/020/21 | 1 |  | 10000000 | <20M | NS | POST | POST | Plan | 2021-02-03 |  | 2021-02-23 | 2021-03-08 | 1900-03-24 |  | N/A | N/A |  | 2021-04-16 | 2021-04-30 | N/A
Actual
22 |  | PROCUREMENT OF CASUALTY CONSUMASBLES | PPA/G-F/NS/021/21 | 1 |  | 4000000 | <10M | NS | POST | POST | Plan | 2021-03-02 |  | 2021-03-16 | 2021-06-04 | 2021-06-22 |  | N/A | N/A |  | 2021-07-02 | 2021-07-20 | N/A
Actual
23 |  | MOTOR VEHICLE FUEL CONSUMPTION/INCIDENCE | PPA/G-F/NS/022/21 | 1 |  | 650000 | <10M | NS | POST | POST | Plan | 2021-01-13 |  | 2021-03-02 | 2021-03-24 | 2021-04-07 |  | N/A | N/A |  | 2021-04-16 | 2021-04-30 | N/A
Actual
24 |  | PROCUREMNT OF DIESEL | PPA/G-F/NS/023/21 | 1 |  | 24000000 | <50M | NS | POST | POST | Plan | 2021-02-01 |  | 19/02/202 | 2021-03-05 | 2021-03-24 |  | N/A | N/A |  | 2021-04-02 | 2021-04-23 | N/A
Actual
25 |  | FUEL FOR PLANTS | PPA/G-F/NS/024/21 | 1 |  | 24000000 | <50M | NS | POST | POST | Plan | 2021-01-04 |  | 2021-01-21 | 2021-02-08 | 2021-02-24 |  | N/A | N/A |  | 2021-03-05 | 2021-03-26 | N/A
Actual
26 |  | STATIONERY | PPA/G-F/NS/025/21 | 1 |  | 650000 | <10M | NS | POST | POST | Plan | 2021-03-01 |  | 2021-03-19 | 2021-04-23 | 2021-05-07 |  | N/A | N/A |  | 2021-05-17 | 2021-07-05 | N/A
Actual
27 |  | PURCHASE OF KITCHEN UTENSILS | PPA/G-F/NS/026/21 | 1 |  | 400000 | <10M | NS | POST | POST | Plan | 2021-05-10 |  | 2021-06-01 | 2021-06-23 | 2021-07-12 |  | N/A | N/A |  | 2021-07-05 | 2021-07-23 | N/A
|  | TOTOAL COST |  |  |  |  | VALUE |  |  |  | Actual | [8 empty] | VALUE
[7 empty] | VALUE | [12 empty] | VALUE

## works
PROCUREMENT PLAN FOR WORKS
MINISTRY:
BUDGET YEAR:
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual