## GOODS
PROCUREMENT PLAN FOR GOODS
MINISTRY/ AGENCY: LAGOS STATE RADIO SERVICE
BUDGET YEAR: 2021
CONTRACT IDENTIFICATION |  | BASIC DATA | [7 empty] | BIDDING PERIOD (DATES) |  |  |  | BIDS EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION (DATES)
Contract Description | Package Number | Lot Number | No. of Unit | Budget Avail | Approval Threshold | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDA | PPA No-Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission Bid Eval Rpt | PPA Issues Certificate of Compliance | Mr. Govenor Approval | Register Mr. Governor's approval with PPA | Contract Amount in N'000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Complete Delivery/Istall | Inspection and Final Acceptance
|  |  |  | 0 | 0 |  |  |  | Plan | 1-4 wks | 1-2 wks | 1-2 wks | 2-6 wks | 1-2 wks | 1-2 wks | (1-4 wks) | 48Hours | 0 | 1WK | 1-2 wks | 2-4 wks
Actual
Provision for Audit unit | LSRS/G/NS/001/21 |  |  | 400,000.00 | <50M | NS | POST | PRIOR | Plan | 2021-01-04 | 2021-01-11 | 18/01/2021 | 2021-02-01 | 2021-02-08 | 15/02/2021 | 22/02/2021 | 22/03/2021 |  | 24/03/2021 | 2021-03-31 | 7/04/2021 | 2021-04-21 | 2021-04-28
Actual
Procurement of Diesel and Lubricants | LSRS/G-F/NS/002/21 |  |  | 13,000,000.00 | <50M | NS | POST | POST | Plan | 2021-04-05 | 2021-04-12 | 19/04/2021 | 2021-04-26 | 2021-05-10 | 17/05/2021 | 24/05/2021 | 21/06/2021 |  | 2021-06-23 | 2021-06-30 | 7/07/2021 | 21/07/2021 | 2021-07-28
Actual
Fueling of Motor Vehicle | LSRS/G-F/NS/003/20 |  |  | 3,000,000.00 | <50M | NS | POST | POST | Plan | 2021-10-02 | 17/02/2021 | 24/02/2021 | 2021-03-03 | 17/03/2021 | 24/03/2021 | 31/03/2021 | 28/04/2021 |  | 2021-04-30 | 2021-05-07 | 2021-05-14 | 28/05/2021 | 2021-06-04
Actual
Procurement Of Stationeries | LSRS/G/NS/004/21 |  |  | 3,000,000.00 | <50M | NS | POST | POST | Plan | 2021-01-04 | 2021-01-11 | 18/01/2021 | 2021-02-01 | 2021-02-08 | 15/02/2021 | 22/02/2021 | 22/03/2021 |  | 24/03/2021 | 2021-03-31 | 7/04/2021 | 2021-04-21 | 2021-04-28
Actual
Procurement of Laptop and Computer Comsumables | LSRS/G/NS/005/21 |  |  | 3,550,000.00 | <50M | NS | POST | POST | Plan | 2021-04-05 | 2021-04-12 | 19/04/2021 | 2021-04-26 | 2021-05-10 | 17/05/2021 | 24/05/2021 | 21/06/2021 |  | 2021-06-23 | 2021-06-30 | 7/07/2021 | 21/07/2021 | 2021-07-28
Actual
Procurement of Office Equipment | LSRS/G/NS/006/21 |  |  | 3,812,000.00 | <50M | NS | POST | POST | Plan | 2021-10-02 | 17/02/2021 | 24/02/2021 | 2021-03-03 | 17/03/2021 | 24/03/2021 | 31/03/2021 | 28/04/2021 |  | 2021-04-30 | 2021-05-07 | 2021-05-14 | 28/05/2021 | 2021-06-04
Actual
Proucrement of Uniform and Protective clothings | LSRS/G/NS/07/21 |  |  | 500,000.00 | <50M | NS | POST | POST | Plan | 2021-01-04 | 2021-01-11 | 18/01/2021 | 2021-02-01 | 2021-02-08 | 15/02/2021 | 22/02/2021 | 22/03/2021 |  | 24/03/2021 | 2021-03-31 | 7/04/2021 | 2021-04-21 | 2021-04-28
Actual
Total Cost |  |  |  | 27262000 | #REF! |  |  |  | Plan
|  |  |  | #REF! | #REF! |  |  |  | Actual

## NCS
PROCUREMENT PLAN FOR NON CONSULTING SERVICES
MINISTRY/ AGENCY: LAGOS STATE RADIO SERVICE
BUDGET YEAR: 2021
CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan vs. Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BIDS EVALUATION (DATES) |  |  | APPROVAL |  | CONTRACT FINALIZATION
Contract Description | Package Number | Lot Number | Budget Avail | Approval Threshold | Procurement Method | Lumpsum or Bill of Quantities | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDA | PPA No-Objection | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | PPA Issues Certificate of Compliance | Plan vs Actual | Mr. Governor Approval | Register Mr. Governor's approval with PPA | Contract Amount in N'000 | Notification of Award | Date Contract Signature | Mobilization/ Advance Payment | Substantial Completion/Istall | Inspection and Final Acceptance
|  |  | 0 | 0 |  |  |  | Plan |  | 1-4 wks | 1-2 wks | 1-2 wks | 2-6 wks | 1-2 wks | 1-2 wks |  | 1-4wks | 48Hours | 0 | 1wk | 4-6 wks | 2-4 wks
Actual
Maintenance of Office Building | LSRS/S-NC/NS/001/21 |  | 2000000 | <50M | NS |  | POST | Plan | POST | 2021-04-01 | 2021-11-01 | 18/1/2021 | 25/1/2021 | 2021-08-02 | 15/2/2021 |  | 22/2/2021 | 22/3/2021 |  | 24/03/2021 | 2021-03-03 | 28/3/2021 | 2021-05-04 | 2021-12-04
Actual
Maintenance of Motor Vehicle | LSRS/S-NC/NS/002/21 |  | 2000000 | <50M | NS |  | POST | Plan | POST | 2021-11-01 | 18/1/2021 | 25/1/2021 | 2021-01-02 | 15/2/2021 | 22/2/2021 |  | 2021-01-03 | 29/3/2021 |  | 2021-03-04 | 2021-07-04 | 2021-05-05 | 2021-12-05 | 19/5/2021
Actual
Maintenance of Plant/Equipment | LSRS/S-NC/NS/003/21 |  | 1300000 | <50M | NS |  | POST | Plan | POST | 2021-11-01 | 18/1/2021 | 25/1/2021 | 2021-01-02 | 15/2/2021 | 22/2/2021 |  | 2021-01-03 | 29/3/2021 |  | 2021-03-04 | 2021-07-04 | 2021-05-05 | 2021-12-05 | 19/5/2021
Actual
Maintenance and Repairs of Spare parts for Specialiased Equipment | LSRS/S-NC/NS/004/21 |  | 600000 | <50M | NS |  | POST | Plan | POST | 2021-11-01 | 18/1/2021 | 25/1/2021 | 2021-01-02 | 15/2/2021 | 22/2/2021 |  | 2021-01-03 | 29/3/2021 |  | 2021-03-04 | 2021-07-04 | 2021-05-05 | 2021-12-05 | 19/5/2021
Actual
Provision for children day and ICDB | LSRS/S-NC/NS/005/21 |  | 2500000 | <50M | NS |  | POST | Plan | POST | 2021-11-01 | 18/1/2021 | 25/1/2021 | 2021-01-02 | 15/2/2021 | 22/2/2021 |  | 2021-01-03 | 29/3/2021 |  | 2021-03-04 | 2021-07-04 | 2021-05-05 | 2021-12-05 | 19/5/2021
Actual
Maintenance of Event Centres | LSRS/S-NC/NS/006/21 |  | 6200000 | <50M | NS |  | POST | Plan | POST | 2021-04-01 | 2021-11-01 | 18/1/2021 | 25/1/2021 | 2021-08-02 | 15/2/2021 |  | 22/2/2021 | 22/3/2021 |  | 24/03/2021 | 2021-03-03 | 28/3/2021 | 2021-05-04 | 2021-12-04
Actual
Maintenance and Repair of Office Equipment | LSRS/S-NC/NS/007/21 |  | 1000000 | <50M | NS |  | POST | Plan | POST | 2021-04-01 | 2021-11-01 | 18/1/2021 | 25/1/2021 | 2021-08-02 | 15/2/2021 |  | 22/2/2021 | 22/3/2021 |  | 24/03/2021 | 2021-03-03 | 28/3/2021 | 2021-05-04 | 2021-12-04
Actual
Maintenance of Marque | LSRS/S-NC/NS/008/21 |  | 2000000 | <50M | NS |  | POST | Plan | POST | 2021-04-01 | 2021-11-01 | 18/1/2021 | 25/1/2021 | 2021-08-02 | 15/2/2021 |  | 22/2/2021 | 22/3/2021 |  | 24/03/2021 | 2021-03-03 | 28/3/2021 | 2021-05-04 | 2021-12-04
Actual
Total Cost |  |  | 15600000 | #REF! |  |  |  | Plan | [10 empty] | #REF!
|  |  | #REF! | #REF! |  |  |  | Actual | [10 empty] | #REF!

## SERVICES
PROCUREMENT PLAN FOR CONSULTANCY SERVICES
MINISTRY/ AGENCY: LAGOS STATE RADIO SERVICE
BUDGET YEAR: 2021
PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) (DATES) |  | SHORTLISTING (DATES) |  |  | REQUEST FOR PROPOSALS (DATES) |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) (DATES) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION (DATES) |  |  |  |  | CONTRACT IMPLEMENTATION (DATES)
Project Description | Project Package | Selection Method | Lumpsum or Time-Based | Estimated Amount in N '000 | Prior/Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Submission of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor Approval | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Date Contract Advert | Contract Signature | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
|  |  |  | 0 |  | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-4 wks | 1-4wk | 48Hours | 0 | 1 wk | 1 wk | 2wks | 1-2 wks | 2-4 wks |  |  | 0
Actual
Engagement of External Auditors | LSRS/S-C/SS/001/21 | SS | TIME BASED | 2000000 | POST | Plan | 2021-02-04 | 9/4/2021 | 16/4/2021 | 23/4/2021 | 7/5/2021 | 14/5/2021 | 21/5/2021 | 28/5/2021 | 2021-04-06 | 2021-11-06 | 18/6/2021 | 25/6/2021 | 2/7/2021 | 30/7/2021 |  | 3/8/2021 | 2021-10-08 | 24/8/2021 | 2021-07-09 | 14/9/2021 | 28/9/2021 | 5/10/2021 | 12/10/2021
Actual
Total Cost |  |  |  | 2000000 |  | Plan | [14 empty] | #REF! | [7 empty] | #REF!
|  |  |  | #REF! |  | Actual | [14 empty] | #REF! | [7 empty] | #REF!

## NO PROCUREMENT ITEMS
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
AGENCY:LAGOS STATE RADIO SERVICE
BUDGET YEAR: 2021
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TOTAL
1 | Travels & Transport | LSRS/NP/NM/01/2021 | 3500000 | Plan | 291666.67 | 291666.67 | 291666.67 | 291666.67 | 291666.67 | 291666.67 | 291666.67 | 291666.67 | 291666.67 | 291666.67 | 291666.67 | 291666.67 | 3500000
Actual
2 | General Utility | LSRS/NP/NM/02/2021 | 8,051,000.00 | Plan | 670916.67 | 670916.67 | 670916.67 | 670916.67 | 670916.67 | 670916.67 | 670916.67 | 670916.67 | 670916.67 | 670916.67 | 670916.67 | 670916.67 | 8,051,000.00
Actual
3 | Miscellaneous | LSRS/NP/NM/03/2021 | 500000 | Plan | 41666.67 | 41666.67 | 41666.67 | 41666.67 | 41666.67 | 41666.67 | 41666.67 | 41666.67 | 41666.67 | 41666.67 | 41666.67 | 41666.67 | 500000
Actual
4 | Grants & Contributions | LSRS/NP/NM/04/2021 | 150,000.00 | Plan | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 150,000.00
Actual
5 | Servicing of Meetings | LSRS/NP/NM/05/2021 | 3,000,000.00 | Plan | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 3,000,000.00
Actual
6 | Staff Welfare | LSRS/NP/NM/06/2021 | 1,500,000.00 | Plan | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 1,500,000.00
Actual
7 | Staff Medical Refund | LSRS/NP/NM/07/2021 | 200000 | Plan | 16666.67 | 16666.67 | 16666.67 | 16666.67 | 16666.67 | 16666.67 | 16666.67 | 16666.67 | 16666.67 | 16666.67 | 16666.67 | 16666.67 | 200000
Actual
8 | Provision for Insurance of Property - LASACO | LSRS/NP/NM/08/2021 | 2000000 | Plan | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 2000000
Actual
9 | Provision for Insurance of Personnel - LASACO | LSRS/NP/NM/09/2021 | 2200000 | Plan | 183333.34 | 183333.34 | 183333.34 | 183333.34 | 183333.34 | 183333.34 | 183333.34 | 183333.34 | 183333.34 | 183333.34 | 183333.34 | 183333.34 | 2200000
Actual
10 | Bamk charges | LSRS/NP/NM/10/2021 | 600000 | Plan | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 600000
Actual
11 | VAT/WHT | LSRS/NP/NM/11/2021 | 2000000 | Plan | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 2000000
Actual
12 | Bank Charges | LSRS/NP/NM/12/2021 | 500000 | Plan | 41666.67 | 41666.67 | 41666.67 | 41666.67 | 41666.67 | 41666.67 | 41666.67 | 41666.67 | 41666.67 | 41666.67 | 41666.67 | 41666.67 | 500000
Actual
13 | Payment for Sub-Staff, Ad-hoc, Programmes Production and Freelance artiste | LSRS/NP/NM/13/2021 | 6900000 | Plan | 575000 | 575000 | 575000 | 575000 | 575000 | 575000 | 575000 | 575000 | 575000 | 575000 | 575000 | 575000 | 6900000
Actual
14 | Newspaper & Magazine | LSRS/NP/NM/14/2021 | 100000 | Plan | 8333.34 | 8333.34 | 8333.34 | 8333.34 | 8333.34 | 8333.34 | 8333.34 | 8333.34 | 8333.34 | 8333.34 | 8333.34 | 8333.34 | 100000
Actual
15 | Subscription for NAN/BON/NBC | LSRS/NP/NM/15/2021 | 2500000 | Plan | 208333.34 | 208333.34 | 208333.34 | 208333.34 | 208333.34 | 208333.34 | 208333.34 | 208333.34 | 208333.34 | 208333.34 | 208333.34 | 208333.34 | 2500000
Actual
16 | Dedicated Expenditures | LSRS/NP/NM/16/2021 | 7047546.76 | Plan | 587295.56 | 587295.56 | 587295.56 | 587295.56 | 587295.56 | 587295.56 | 587295.56 | 587295.56 | 587295.56 | 587295.56 | 587295.56 | 587295.56 | 7047546.76
Actual
17 | Wardrobe Allowance | LSRS/NP/NM/17/2021 | 41000000 | Plan | 3416666.67 | 3416666.67 | 3416666.67 | 3416666.67 | 3416666.67 | 3416666.67 | 3416666.67 | 3416666.67 | 3416666.67 | 3416666.67 | 3416666.67 | 3416666.67 | 41000000
Actual
18 | Personnel Cost | LSRS/NP/NM/18/2021 | 251298659.24 | Plan | 20941554.94 | 20941554.94 | 20941554.94 | 20941554.94 | 20941554.94 | 20941554.94 | 20941554.94 | 20941554.94 | 20941554.94 | 20941554.94 | 20941554.94 | 20941554.94 | 251298659.24
Actual
| Total |  | 335047206 | [13 empty] | 335047206

## WORKSHOP
PROCUREMENT PLAN FOR CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: LAGOS STATE RADIO SERVICE
BUDGET YEAR: 2021
S/N | Description of Workshop/Conference | Package Number | Objective of Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | Training & Staff Development |  |  |  |  | Plan | ABUJA |  |  |  | 1,500,000.00
Actual
2 | Conferences & Seminars |  |  |  |  | Plan | ABUJA |  |  |  | 500,000.00
Actual
3 | [5 empty] | Plan
Actual
4 | [5 empty] | Plan
Actual
5 | [5 empty] | Plan
Actual
| PLAN TOTAL |  |  |  |  | Plan
| ACTUAL TOTAL |  |  |  |  | Actual

## sheet
PROCUREMENT PLAN FOR WORKS
MINISTRY/ AGENCY: LAGOS STATE RADIO SERVICE | [9 empty] | NA: MEANS NOT APPLICABLE
BUDGET YEAR: 2021
CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan vs. Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BIDS EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
Contract Description | Package Number | Lot Number | Budget Avail | Approval Threshold | Procurement Method | Lumpsum or Bill of Quantities | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDA | PPA No-Objection | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | PPA Issues Certificate of Compliance | Mr. Governor Approval | Register Mr. Governor's approval with PPA | Contract Amount in N'000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Substantial Completion/Istall | Inspection and Final Acceptance
|  |  | 0 | 0 |  |  |  | Plan |  | 1-4 wks | 1-2 wks | 1-2 wks | 2-6 wks | 1-2 wks | 1-2 wks | 1-4wks | 48Hours | 0 | 1WKS | 1-2 wks | 2-4 wks
Actual
Upgrade/Structural Partitioning of Store | LSRS/W/NS/001/20 | 1 | 3,678,894.00 | <10M | NS | BOQ | POST | Plan | POST | 8/7/2020 | NA | 22/7/2020 | 5/8/2020 | 12/8/2020 | NA | 9/09/2020 | 11/09/2020 | 3,678,894.00 | 18/09/2020 | 2/10/2020 | 23/10/2020
Renovation of Lagos State Radio Service (LSRS) EKO FM Office Building | LSRS/W/NS/002/20 |  | 94,076,857.89 | <100M | NS | BOQ | POST | Actual | PRIOR | 8/7/2020 | NA | 22/7/2020 | 5/8/2020 | 12/8/2020 | NA | 9/09/2020 | 11/09/2020 | 3,678,894.00 | 18/09/2020 | 2/10/2020 | 23/10/2020
Plan
Total Cost |  |  | 97755751.89 |  |  |  |  | Plan | [9 empty] | #REF!
|  |  | #REF! | #REF! |  |  |  | Actual | [9 empty] | #REF!