## Non-Proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/AGENCY: MINISTRY OF WATERFRONT INFRASTUCTURE DEVELOPMENT
BUDGET YEAR: 2021
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TOTAL
1 | Travel & Transport | MWID/NP/NM/001/2021 | 3,900,000.00 | Plan | 325000 | 325000 | 325000 | 325000 | 325000 | 325000 | 325000 | 325000 | 325000 | 325000 | 325000 | 325000 | 3900000
Actual
2 | COWLSO PROGRAME (Special Duties Expenses) | MWID/NP/NM/002/2021 | 4500000 | Plan | SEPTEMBER: 4500000 | 4500000
|  |  |  | Actual | [13 empty] | 30000000 | 12 | 2500000
3 | SPORTS & CIVIL SERVANT WEEK CELEBRATRION (Special Duties Expenses) | MWID/NP/NM/003/2021 | 2000000 | Plan | APRIL: 2000000 | 2000000
Actual
4 | Honourarium for law enforcement Agent & Logistics | MWID/NP/NM/004/2021 | 60,000,000,.00 | Plan | [12 empty] | 60,000,000,.00
Actual
5 | General Utility Services | MWID/NP/NM/005/2021 | 2,200,000.00 | Plan | MARCH: 550000; JUNE: 550000; SEPTEMBER: 550000; DECEMBER: 550000 | 2200000
Actual
6 | Dispatch of official Letters (Special Duties Expenses) | MWID/NP/NM/006/2021 | 1,500,000.00 | Plan | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 1500000
Actual
7 | Logistics for post qualification | MWID/NP/NM/7/2021 | 2,350,000.00 | Plan | [12 empty] | 3,420,000.00
Actual
8 | Preparation of Y2022 Annual Budget for Bilateral discussion | MWID/NP/NM/8/2021 | 3,700,000.00 | Plan | [12 empty] | 3,700,000.00
Actual
9 | Public Affairs Unit. | MWID/NP/NM/9/2021 | 3200000 | Plan | [12 empty] | 3200000
Actual
10 | Payment of course fee and allowances for staff within Lagos state | MWID/NP/NM/10/2021 | 3000000 | Plan | [12 empty] | 0
Actual
11 | In house training for Drivers and junior staff Categories | MWID/NP/NM/11/2021 | 800,000.00 | Plan | [12 empty] | 0
Actual
12 | Unforeseen Circumstances | MWID/NP/NM/12/2021 | 13,000,000.00 | Plan | [12 empty] | 0
Actual
13 | Any other assignment | MWID/NP/NM/13/2021 | 30,000.000.00 | Plan | [12 empty] | 30000000
Actual
14 | Logistics for monitoring and investigation for Audit unit expense | MWID/NP/NM/14/2021 | 1500000 | Plan | [12 empty] | 0
Actual
15 | Legal unit | MWID/NP/NM,/15/2021 | 1000000 | Plan | [12 empty] | 0
Actual
16 | Cost to offset the cost of Procurement Unit, ,mandatory Proficiency Programme and Provision for statutory meeting like MTB and PPC | MWID/NP/NM/16/2021 | 3500000 | Plan | [12 empty] | 0
Actual

## trg conf wsh
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: MINISTRY OF WATERFRONT INFRASTRUCTURE DEVELOPMENT
BUDGET YEAR: 2021
S/N | Description of Training/Workshop/ Conference | Package No | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | Payment of course fee and allowances for staff within Lagos state @ N750,000,000.00 Per quarter | MWID/S-WTC/SSS/001/2021 | To enhance professionalism and efficient service delivery |  |  | Plan |  |  |  |  | 3000000
Actual
2 | Leadership Competences for ORGANIZATION Renewal in Public & Private Organization for HC | MWID/S-WTC/SSS/002/2021 | To enhance professionalism and efficient service delivery |  |  | Plan |  |  |  |  | 800000
Actual
3 | Implementing Sustainable change for HC | MWID/S-WTC/SSS/003/2021 | To enhance professionalism and efficient service delivery |  |  | Plan |  |  |  |  | 700000
Actual
4 | Strategic Management for HC & Permanent Secretary | MWID/S-WTC/SSS/004/2021 | To enhance professionalism and efficient service delivery |  |  | Plan |  |  |  |  | 600956
Actual
5 | Coren Conference for Permanent Secretary | MWID/S-WTC/SSS/005/2021 | To enhance professionalism and efficient service delivery |  |  | Plan |  |  |  |  | 600000
5.6 | [5 empty] | Actual
6 | NIM Conference for (D) A&HR | MWID/S-WTC/SSS/006/2021 | To enhance professionalism and efficient service delivery |  |  | Plan |  |  |  |  | 500000
Actual
7 | COREN Conference for D(SP) | MWID/S-WTC/SSS/007/2021 | To enhance professionalism and efficient service delivery |  |  | Plan |  |  |  |  | 500000
Actual
8 | Public Affairs Conference for D(PA) | MWID/S-WTC/SSS/008/2021 | To enhance professionalism and efficient service delivery |  |  | Plan |  |  |  |  | 500000
Actual
9 | ICAN Conference for D(Fin & Account) | MWID/S-WTC/SSS/009/2021 | To enhance professionalism and efficient service delivery |  |  | Plan |  |  |  |  | 500000
Actual
10 | NIESV Conference for D(Estate) | MWID/S-WTC/SSS/010/2021 | To enhance professionalism and efficient service delivery |  |  | Plan |  |  |  |  | 450000
Actual
11 | COREN Conference for D(Engineering) | MWID/S-WTC/SSS/011/2021 | To enhance professionalism and efficient service delivery |  |  | Plan |  |  |  |  | 450000
Actual
12 | NEC Conference for AD(Planning) | MWID/S-WTC/SSS/012/2021 | To enhance professionalism and efficient service delivery | 50 Nos |  | Plan |  |  |  |  | 450000
Actual
13 | CIPS Conference for D(Procurement) | MWID/S-WTC/SSS/013/2021 | To enhance professionalism and efficient service delivery | 3 Nos |  | Plan |  |  |  |  | 450000
Actual
14 | ANAN Conference Head (Audit) | MWID/S-WTC/SSS/014/2021 | To enhance professionalism and efficient service delivery | 75 Nos |  | Plan |  |  |  |  | 400000
Actual
15 | CIPS Conference for Procurement Officers @ N350,000 each | MWID/S-WTC/SSS/015/2021 | To enhance professionalism and efficient service delivery |  |  | Plan |  |  |  |  | 700000
Actual
16 | Refresher course for 10 (Ten) Engineers @ N350,000.00 per Officer | MWID/S-WTC/SSS/016/2021 | To enhance professionalism and efficient service delivery |  |  | Plan |  |  |  |  | 3500000
Actual
17 | Conference for Three Confidencial Secretaries @ N250,000.00 per Officer | MWID/S-WTC/SSS/017/2021 | To enhance professionalism and efficient service delivery |  |  | Plan |  |  |  |  | 750000
Actual
18 | Conference for two Quantity Surveyors @ N350,000.00 per Officer | MWID/S-WTC/SSS/018/2021 | To enhance professionalism and efficient service delivery |  |  | Plan |  |  |  |  | 700000
Actual
19 | CPN Conference for 2 (Two) ICT Officers @ N350,000.00 Per Officer | MWID/S-WTC/SSS/019/2021 | To enhance professionalism and efficient service delivery |  |  | Plan |  |  |  |  | 700000
Actual
20 | NIESV Conference for four Land Officer @ N350,000.00 per Officer | MWID/S-WTC/SSS/020/2021 | To enhance professionalism and efficient service delivery |  |  | Plan |  |  |  |  | 1400000
Actual
21 | Refresher course for 5 (Five) Geologiets @ N350,000.00 per Officer | MWID/S-WTC/SSS/021/2021 | To enhance professionalism and efficient service delivery |  |  | Plan |  |  |  |  | 1750000
Actual
22 | ANAN Conference for Five Accountants @ N350,000.00 per Officer | MWID/S-WTC/SSS/022/2021 | To enhance professionalism and efficient service delivery |  |  | Plan |  |  |  |  | 1750000
Actual
23 | Conference for two Town Planners @ N350,000.00 per Officer | MWID/S-WTC/SSS/023/2021 | To enhance professionalism and efficient service delivery |  |  | Plan |  |  |  |  | 700000
Actual
24 | NES for planning and Budgeting Officers @N300,000.00 per Officer | MWID/S-WTC/SSS/024/2021 | To enhance professionalism and efficient service delivery |  |  | Plan |  |  |  |  | 900000
Actual
25 | ANAN Conference One Auditor | MWID/S-WTC/SSS/025/2021 | To enhance professionalism and efficient service delivery |  |  | Plan |  |  |  |  | 350000
Actual
26 | NIM Conference for 9 (Nine) Administrative Officers | MWID/S-WTC/SSS/026/2021 | To enhance professionalism and efficient service delivery |  |  | Plan |  |  |  |  | 3150000
Actual
27 | NSA Conference for 3 officers of Planning Unit at N350,000 each | MWID/S-WTC/SSS/027/2021 | To enhance professionalism and efficient service delivery |  |  | Plan |  |  |  |  | 1050000
Actual
28 | Conference for 2 Public Affairs Officers @350,000 | MWID/S-WTC/SSS/028/2021 | To enhance professionalism and efficient service delivery |  |  | Plan |  |  |  |  | 7000000
Actual
29 | In house training for Drivers and junior staff categories | MWID/S-WTC/SSS/028/2021 | To enhance professionalism and efficient service delivery | [7 empty] | 800000

## non-cons
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY: MINISTRY OF WATERFRONT INFRASTRUCTURE DEVELOPMENT
BUDGET YEAR: 2021
S/N | Contract Description | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
|  | Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Approval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
1 | Maintanance of office building | MWID/S-NC/NS/001/2021 |  | 1 | 1500000 | <10M | NS | Plan | Post | Post | 2021-02-05 | N/A | 2021-02-12 | 2021-02-26 | 2021-03-05 | N/A | N/A | Plan | 2021-04-09 | 2020-04-14 |  | 2021-05-11 | 2021-06-08 | 2021-07-27 | 2022-01-27
[8 empty] | Actual | [9 empty] | Actual
2 | Refurbishment of 2 NosToyota Hilux, and 1 nos Toyota 4 runner @ | MWID/S-NC/NS/002/2021 |  | 1 | 1935000 | <10M | NS | Plan | Post | Post | 2021-02-05 | N/A | 2020-02-12 | 2020-02-26 | 2020-03-05 | N/A | N/A | Plan | 2021-04-09 | 2020-04-14 |  | 2021-05-11 | 2021-06-08 | 2021-07-27 | 2022-01-27
Actual
3 | Maintenance of Motor Vehicle Repairs and Maintanance | MWID/S-NC/NS/003/2021 |  | 1 | 2900000 | <10M | NS | Plan | Post | Post | 2021-02-05 | N/A | 2020-02-12 | 2020-02-26 | 2020-03-05 | N/A | N/A | Plan | 2021-04-09 | 2020-04-14 |  | 2021-05-11 | 2021-06-08 | 2021-07-27 | 2022-01-27
[8 empty] | Actual | [9 empty] | Actual
4 | Concession to manage the operation of Water Hycinth on Lagos waterways | MWID/S-NC/NCB/004/2021 |  | 1 | 49000000 | <50M | NCB | Plan | Post | Prior | 2021-02-05 | N/A | 2020-02-12 | 2020-02-26 | 2020-03-05 |  |  | Plan | 2021-04-09 | 2020-04-14 |  | 2021-05-11 | 2021-06-08 | 2021-07-27 | 2022-01-27
[8 empty] | Actual | [9 empty] | Actual
5 | Servicing of meetings | MWID/S-NC/NSPost/005/2021 |  | 1 | 3000000 | <10M | NS | Plan | Post | Post | 2021-02-05 | N/A | 2020-02-12 | 2020-02-26 | 2020-03-05 |  |  | Plan | 2021-04-09 | 2020-04-14 |  | 2021-05-11 | 2021-06-08 | 2021-07-27 | 2022-01-27
[8 empty] | Actual | [9 empty] | Actual
6 | Publicity and Press Coverage | MWID/S-NC/NS/006/2021 |  | 1 | 2800000 | <10M | NS | Plan | Post | Post | 2021-02-05 | N/A | 2020-02-12 | 2020-02-26 | 2020-03-05 |  |  | Plan | 2021-04-09 | 2020-04-14 |  | 2021-05-11 | 2021-06-08 | 2021-07-27 | 2022-01-27
[8 empty] | Actual | [9 empty] | Actual
7 | Enlightenment of the Ministry's activities | MWID/S-NC/NS/007/2021 |  | 1 | 3000000 | <10M | NS | Plan | Post | Post | 2021-02-05 | N/A | 2020-02-12 | 2020-02-26 | 2020-03-05 |  |  | Plan | 2021-04-09 | 2020-04-14 |  | 2021-05-11 | 2021-06-08 | 2021-07-27 | 2022-01-27
[8 empty] | Actual | [9 empty] | Actual
8 | Production of Airing of Documentary on the Ministry's activities | MWID/S-NC/NS/008/2021 |  | 1 | 2500000 | <10M | NS | Plan | Post | Prior | 2021-02-05 | N/A | 2020-02-12 | 2020-02-26 | 2020-03-05 |  |  | Plan | 2021-04-09 | 2020-04-14 |  | 2021-05-11 | 2021-06-08 | 2021-07-27 | 2022-01-27
[8 empty] | Actual | [9 empty] | Actual
9 | Enlightenment programmes on regularization of Extension in to Waterbodie | MWID/S-NC/NS/009/2021 |  | 1 | 5000000 | <10M | NS | Plan | Post | Prior | 2021-02-05 | N/A | 2020-02-12 | 2020-02-26 | 2020-03-05 |  |  | Plan | 2021-04-09 | 2020-04-14 |  | 2021-05-11 | 2021-06-08 | 2021-07-27 | 2022-01-27
[8 empty] | Actual | [9 empty] | Actual
10 | Advertisements, sending of letters, and radio jingles@N1,000,000.00 Per Quarter | MWID/S-NC/NS/10/2021 |  | 1 | 4000000 | <10M | NS | Plan | Post | Prior | 2021-02-05 | N/A | 2020-02-12 | 2020-02-26 | 2020-03-05 |  |  | Plan | 2021-04-09 | 2020-04-14 |  | 2021-05-11 | 2021-06-08 | 2021-07-27 | 2022-01-27
[8 empty] | Actual | [9 empty] | Actual
11 | Dissemination of guidelines and a documentary on ecological awareness | MWID/S-NC/NS/11/2021 |  | 1 | 5000000 | <10M | NS | Plan | Post | Post | 2021-02-05 | N/A | 2020-02-12 | 2020-02-26 | 2020-03-05 |  |  | Plan | 2021-04-09 | 2020-04-14 |  | 2021-05-11 | 2021-06-08 | 2021-07-27 | 2022-01-27
[8 empty] | Actual | [9 empty] | Actual
12 | Janitorial Services | MWID/S-NC/NCB/12/2021 |  | 1 | 1500000 | <10M | NCB | Plan | Post | Post | 2021-02-05 | N/A | 2020-02-12 | 2020-02-26 | 2020-03-05 |  |  | Plan | 2021-04-09 | 2020-04-14 |  | 2021-05-11 | 2021-06-08 | 2021-07-27 | 2022-01-27
[8 empty] | Actual | [9 empty] | Actual
13 | Retreat for Administrators /others | MWID/S-NC/NCB/13/2021 |  | 1 | 10000000 | <50M | NCB | Plan | Post | Prior | 2021-02-05 | N/A | 2020-02-12 | 2020-02-26 | 2020-03-05 |  |  | Plan | 2021-04-09 | 2020-04-14 |  | 2021-05-11 | 2021-06-08 | 2021-07-27 | 2022-01-27
[8 empty] | Actual | [9 empty] | Actual
14 | Servicing of meetings | MWID/S-NC/NCB/14/2021 |  | 1 | 3000000 | <10M | NCB | Plan | Post | Post | 2021-02-05 | N/A | 2020-02-12 | 2020-02-26 | 2020-03-05 |  |  | Plan | 2021-04-09 | 2020-04-14 |  | 2021-05-11 | 2021-06-08 | 2021-07-27 | 2022-01-27
[8 empty] | Actual | [9 empty] | Actual
15 | Asset Numbering | MWID/S-NC/NCB/15/2021 |  | 1 | 1000000 | <10M | NCB | Plan | Post | Post | 2021-02-05 | N/A | 2020-02-12 | 2020-02-26 | 2020-03-05 |  |  | Plan | 2021-04-09 | 2020-04-14 |  | 2021-05-11 | 2021-06-08 | 2021-07-27 | 2022-01-27
[8 empty] | Actual | [9 empty] | Actual

## consultancy
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/ AGENCY: Ministry of Waterfront Infrastructure Development
BUDGET YEAR: 2021
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[5 empty] | 0 |  |  | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
1 | Engagement of Consultant for identification of Dredging Site | MWID/S-C/QCBS/001/2021 | QCBS | Time based | 10000000 | Prior | Plan | 2021-02-03 | 2021-02-17 | 2021-02-24 | 2021-03-23 | 2021-03-30 | 2021-04-06 | 2021-04-27 | 2021-05-04 | 2021-05-11 | 2021-05-18 | 2021-05-25 | 2021-06-01 | 2021-06-29 | 2021-07-01 |  | 2021-07-08 | 2021-07-22 | 2021-08-19 | 2021-08-26 | 2021-09-02
Actual
2 | Statistical Survey and structured inquiry designed | MWID/S-C/QCBS/002/2021 | QCBS | Time based | 1500000 | Post | Plan | 3/02/2021 | 17/02/2021 | 24/02/2021 | 23/03/2021 | 30/03/2021 | 06/04/2021 | 27/04/2021 | 04/05/2021 | 11/05/2021 | 18/05/2021 | 25/05/2021 | 01/06/2021 | 29/06/2021 | 01/07/2021 |  | 08/07/2021 | 22/07/2021 | 19/08/2021 | 26/08/2021 | 02/09/2021
Actual
3 | Investigative & Bathymetric Survey of Waterbodies | MWID/S-C/QCBS/002/2021 | QCBS | Time based | 460000000 | Prior | Plan
[7 empty] | Actual | 24/06/2020 | 26/06/2020 | 13/07/2020 | 20/07/2021 | 27/07/2020 | 3/08/2020 | 10/08/2020 | 17/08/2020 | 24/08/2020 | 31/08/2020 | 01/09/2020 | 08/09/2020 | 09/03/2021 | 16/*03/2021

## goods
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: MINISTRY OF WATERFRONT INFRASTUCTURE DEVELOPMENT
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot No | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion /Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (1-2wks) | 1-2wks) | (1-2wks) | (1-4 wks) | 48Hrs | 0 | 1wk | (1-2 wks) | (2-4wks)
1 | Procurement of Stationery Items, and consumables for Procurement unit | MWID/G-F/NS/001/2021 |  | 1 | 2580000 | <10M | NS | Post | Post | Plan | 2021-02-11 | N/A | 2021-02-18 | 2021-02-26 | 2021-03-05 | N/A | 2021-06-05 | 2021-06-12 |  | 2021-06-19 | 26/06/202 | 2021-07-10 | 2021-07-17 | 2022-01-18
Actual
2 | Purchase of Office equipments. | MWID/G/NCB/002/2021 |  | 1 | 100000000 | <500M | NCB | Post | Prior | Plan | 2021-02-11 | 2021-02-18 | 2020-02-26 | 2020-03-25 | 2021-04-01 | 2021-04-08 | 2021-05-06 | 2021-05-10 |  | 2021-05-14 | 2021-05-21 | 2021-06-18 | 2021-07-16 | 2022-01-18
Actual
3 | Procurement of Uniform and Protective Outfit | MWID/G/NS/003/2021 |  | 1 | 7000000 | <10M | NS | Post | Post | Plan | 2021-02-11 | N/A | 2021-02-18 | 2020-03-25 | 2021-04-01 | N/A | 2021-05-06 | 2021-05-10 |  | 2021-05-14 | 2021-05-21 | 2021-06-18 | 2021-07-16 | 2022-01-18
Actual
4 | Procurement of Drawing Office Materials | MWID/G/NS/004/2021 |  | 1 | 1785916 | <10M | NS | Post | Post | Plan | 2021-02-11 | N/A | 2021-02-18 | 2021-02-25 | 2021-03-05 | N/A | 2021-06-05 | 2021-06-12 |  | 2021-06-19 | 26/06/202 | 2021-07-10 | 2021-07-17 | 2022-01-18
Actual
5 | Procurement of Tools and Equipment | MWID/G/NS/005/2021 |  | 1 | 2000100 | <10M | NS | Post | Post | Plan | 2021-02-11 | N/A | 2021-02-18 | 2021-02-25 | 2021-03-05 | N/A | 2021-06-05 | 2021-06-12 |  | 2021-06-19 | 26/06/202 | 2021-07-10 | 2021-07-17 | 2022-01-18
Actual
6 | Purchase of Computer Consumables for the Ministry (M.I.S) | MWID/G-F/NS/006/2021 |  | 1 | 1000000 | <10M | NS | Post | Post | Plan | 2021-02-11 | N/A | 2021-02-18 | 2021-02-25 | 2021-03-05 | N/A | 2021-06-05 | 2021-06-12 |  | 2021-06-19 | 26/06/202 | 2021-07-10 | 2021-07-17 | 2022-01-18
Actual
7 | Purchase of 8 nos pick up double cabin, 2 nos of (14) seater, 3.0 litres diesel engine bus and 10 nos official vehicle for various units and dept with vehicle accessories such as (jack, fire extinguisher,see caution for the new fleet | MWID/G/NCB/007/2021 |  | 1 | 225000000 | <500M | NCB | Post | Prior | Plan | 2021-02-11 | 2021-02-18 | 2021-03-25 | 2021-03-05 | 2021-03-12 | 2021-03-19 | 2021-06-05 | 2021-06-12 |  | 2021-06-19 | 26/06/202 | 2021-07-10 | 2021-07-17 | 2022-01-18
Actual
8 | Purchase of Office Furniture & Fittings | MWID/G/NCB/008/2021 |  | 1 | 50000000 | <100M | NCB | Post | Prior | Plan | 2021-02-11 | 2021-02-18 | 2021-02-25 | 2021-03-09 | 2021-03-18 | 25/03/201 | 2021-04-01 | 2021-04-08 |  | 15/*04/2021 | 2021-04-22 | 2021-04-29 | 2021-05-06 | 2021-05-13
Actual
9 | Motor Fuelling of Ministry's Vehicles | MWID/G/NCB/009/2021 |  | 1 | 4000000 | <10M | NCB | Post | Post | Plan | 2021-02-11 | N/A | 2021-02-25 | 2021-02-26 | 2021-03-05 | N/A | 2021-06-05 | 2021-06-12 |  | 2021-06-19 | 26/06/202 | 2021-07-10 | 2021-07-17 | 2022-01-18
Actual
10 | Last day in Office for officers | MWID/G/NCB/010/2021 |  | 1 | 4000000 | <10M | NCB | Post | Post | Plan | 2021-02-11 | N/A | 2021-02-25 | 2021-03-05 | 2021-03-12 | N/A | 2021-03-19 | 2021-03-26 |  | 2021-04-02 | 2021-04-09 | 23/04//2021 | 2021-07-17 | 2021-05-07
Actual
12 | Purchase of tyres for 14 Vehicle at an average of 58,000 each=58,000*5 tyres*14 vehicle*2 (bi-annual) @N8,120,000.00 | MWID/G/NCB/12/2021 |  | 1 | 8120000 | <10M | NCB | Post | Post | Plan | 2021-02-11 | N/A | 2021-02-25 | 2021-03-05 | 2021-03-12 | N/A | 2021-03-19 | 2021-03-26 |  | 2021-04-02 | 2021-04-09 | 2021-04-16 | 2021-04-23 | 2021-03-30
Actual
13 | Management Information System.. Vacum Cleaner, LAN Cable, USB, Sharp AR-163 | MWID/G/NCB/13/2021 |  | 1 | 1000000 | <10M | NCB | Post | Post | Plan | 11/02/20121 | N/A | 2021-02-25 | 2021-03-05 | 2021-03-12 | N/A | 2021-03-19 | 2021-03-26 |  | 2021-04-02 | 2021-04-09 | 2021-04-16 | 2021-04-23 | 2021-03-30
Actual
14 | Consumables for Procurement folder, spiral binding and refurbishment of bidding box | MWID/G/NCB/14/2021 |  | 1 | 1150000 | <10M | NCB | Post | Post | Plan | 11/02/20121 | N/A | 2021-02-25 | 2021-03-05 | 2021-03-12 | N/A | 2021-03-19 | 2021-03-26 |  | 2021-04-02 | 2021-04-09 | 2021-04-16 | 2021-04-23 | 2021-03-30
Actual
ON GOING
11 | 30% due to BGARCA Investment Nig.Ltd. Procurement of two (2) Towing & Survellance Boats for the Ministry | MWID/G/ST/008/2020 |  | 2 | 34668750 | <50m | ST | Post | Prior | Plan | [12 empty] | 2021-03-04 | 2021-03-30
[10 empty] | Actual | 2020-06-03 | 2020-07-16 | 2020-08-16 | 2020-08-27 | 2020-09-09 | 2020-09-11 | 2020-06-03 | N/A |  | 2020-07-11 | 2020-07-11 | 2020-12-31

## works
PROCUREMENT PLAN FOR WORKS
Minisry of Waterfront Infrastructure Development
BUDGET YEAR: 2021
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Preliminary Works on proposed (6) new Waterfront Schemes.(Amijeje, Jewasetan, Eputu, Orimedu, Atiku, Oriyanrin and kajola) | MWID/W/NCB/001/2021 |  | 160000000 | <500M | NCB | BOQ | Post | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-23
Actual
2 | Removal of 4nos Beached/Abandoned Vessels along the coastal shoreline of the state | MWID/W/NCB/002/2021 |  | 700000000 | <1B | NCB | BOQ | Post | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-23
Actual
3 | Provision of Facilities at Waterfront Schemes | MWID/W/NCB/003/2021 |  | 86168593 | <100M | NCB | BOQ | Post | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-23
Actual
4 | Reclamation works at Lekki Foreshore Scheme | MWID/W/NS/005/2021 |  | 6289655.44 | <10M | NS | BOQ | Post | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-23
Actual
5 | Upgrade of Office Building | MWID/W/NS/007/2021 |  | 30000000 | <50M |  | BOQ | Post | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-23
Actual
6 | Construction of Floating jetty , shoreline protection , waiting shelter and pontoon @ Agboyi ketu | MWID/W/NCB/008/2021 |  | 123,000,000,.00 | <500M | NCB | BOQ | Post | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-23
Actual
7 | Construction of Floating jetty, Shoreline Protection, waiting shelter and pontoon @ Adeniji Adele | MWID/W/NCB/009/2021 |  | 111000000 | <500M | NCB | BOQ | Post | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-23
Actual
8 | Construction of floating jetty, shoreline protection, waiting shelter and pontoon@ Irede Abule Osun Ojo | MWID/W/NCB/010/2021 |  | 111000000 | <500m | NCB | BOQ | Post | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 | 0 | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-24 | 2022-12-23
Actual
9 | Construction of floating jetty, Shoreline protection,waiting shelter and pontoon @ Epe | MWID/W/NCB/011/2021 |  | 141000000 | <500M | NCB | BOQ | Post | Plan | Prior | 2021-02-11 | 2021-02-25 | 2021-03-10 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-05-12 | 2021-05-14 |  | 2021-05-21 | 2021-05-28 | 2021-06-25 | 2021-12-14 | 2021-12-23
Actual
ON GOING PROJECTS
10 | Creation of Six new Waterfront Schemes (Idogun,Lepia, Alayande, Ibeshe, Akodo, Owode-Apa | MWID/W/ST/011/2020 |  | 600000000 | <1B | ST | BOQ | Post | Plan | Prior | [8 empty] | 0 |  |  |  | 2021-06-01 | 2021-06-08
[9 empty] | Actual |  | 2020-11-20 | 2020-11-26 | 2020-11-30 | 2020-12-03 | 2020-12-04 | 07/12/23020 | 2020-05-25 | N/A |  | 2020-12-07 | 2020-12-07 | 2020-12-31
11 | Outstanding liabilty for Contract award for the removal of Beached/abandoned shipwrecks from Lagos State waterfront, jet cruiser at zakin opposite Ikate village | MWID/W/ST/002/01/2019 |  | 7348525 | <10M | NCB | BOQ | Post | Plan | Post | [8 empty] | 146980000
[9 empty] | Actual |  | 2019-12-18 | 2019-12-18 | 2019-12-20 | 2019-12-20 | 2019-12-23 | 2019-12-23 | N/A | N/A |  | 2019-12-24 | 2019-12-27 | 2019-12-31
12 | Continous provision of groynes as shoreline protection from Alpha beach towards Eleko beach Phase 2 & 3 | MWID/W/ICB/002/2016 |  | 3530964489 | <5B | ICB | BOQ | Post | Plan | Prior | [8 empty] | 3000000000
[9 empty] | Actual |  | 2016-05-05 | 2016-05-12 | 2016-05-19 | 2016-06-02 | 2016-06-09 | 2016-06-16 | N/A | N/A |  | 2016-07-07 | 2016-08-04 | 2017-04-05 | 2017-11-05
13 | Channelization of Ferry route (Ijede to Badore) (6KM) | MWFID/W/ST/02/001/2017 |  | 74730625 | <100M | ST | BOQ | Post | Plan | Prior | [8 empty] | 0 |  |  |  |  | 2022-12-23
[9 empty] | Actual |  | 2017-05-02 | 2017-05-09 | 2017-05-16 | 2017-05-30 | 2017-06-06 | 2017-06-14 | N/A | N/A |  | 2017-07-04 | 2017-08-01 | 2019-01-01 | 2019-08-01
14 | Channelization of Ferry ropute (Ebute Ojo to Marina) (10KM) | MWFID/W/NCB/03/17 |  | 124162623.11 | <500M | NCB | BOQ | Post | Plan | Prior | [8 empty] | 2275000000
[9 empty] | Actual | Prior | 2017-05-02 | 2017-05-09 | 2017-05-16 | 2017-05-30 | 2017-06-06 | 2017-06-13 | N/A | N/A |  | 2017-07-04 | 2017-08-01 | 2019-01-01 | 2019-08-01
15 | Channnelization of Ferry route (Ijede to Marina) | MWFID/W/ST/02/002/2017 |  | 108986275.93 | <500M | NCB | BOQ | Post | Plan | Prior | [8 empty] | 1947000000
[9 empty] | Actual |  | 2017-05-02 | 2017-05-09 | 2017-05-16 | 2017-05-30 | 2017-06-06 | 2017-06-13 | N/A | N/A |  | 2017-07-04 | 2017-08-01 | 2019-01-01 | 2019-08-01
16 | Channelization of Ferry route (Baiyeku to Ajah) | MWFID/W/ST/02/002/2017 |  | 52757200 | <100M | NCB | BOQ | Post | Plan | Prior | [8 empty] | 0
[9 empty] | Actual |  | 2017-05-02 | 2017-05-09 | 16/5//17 | 2017-05-30 | 2017-06-06 | 2017-06-13 | N/A | N/A |  | 2017-07-04 | 2017-08-01 | 2019-01-01 | 2019-08-01
17 | Reclamation of Badagry Shoreline Protection Work, Badagry (Additional Work) | MWFID/W/DC/004/17 |  | 29640694.09 | <50M | 0% | BOQ | Post | Plan | Prior | [8 empty] | 282233291.29
[9 empty] | Actual |  | 2017-05-24 | 2017-05-31 | 2017-06-07 | 2017-06-21 | 2017-06-28 | 2017-07-05 | N/A | N/A |  | 2017-08-02 | 2017-08-30 | 2018-08-30 | 2018-09-04
18 | Land Reclamation at Oworonsoki Jetty and Construction of Infrastructure (29.6 Hectares of Land) Phase 1 | MWFID/W/DC/04/2016 |  | 15000000 | <50M | NCB | BOQ | Post | Plan | Prior | [8 empty] | 4293777355
[9 empty] | Actual |  | 2016-09-08 | 2016-09-15 | 2016-09-22 | 2016-10-06 | 2016-10-13 | 2016-10-20 | N/A | N/A |  | 2016-11-10 | 2016-12-08 | 2017-08-12 | 2017-12-15
19 | Reclamation of Badagry Shoreline Protection Work, Badagry,( Additional) | MWID/W/DC/2017 |  | 67731872 | <100M | DC | BOQ | Post | Plan | Prior | [8 empty] | 0
[9 empty] | Actual |  | 2017-05-24 | 2017-05-31 | 2017-07-06 | 2017-06-21 | 2017-06-28 | 2017-05-07 | N/A | N/A |  | 2017-08-02 | 2017-02-08 | 30/08/201
20 | Land Reclamation at Oworonsoki Jetty and Construction of Infrastructure -Phase 2 (Additional Reclamation of 20 Hectares of Land) | MWFID/W/NCB/DC/008/2017 |  | 15000000 | <50M | NCB | BOQ | Post | Plan | Prior | [8 empty] | 2213330490
[9 empty] | Actual |  | 2017-11-23 | 2017-11-30 | 2017-12-07 | 2017-12-21 | 2017-12-28 | 2018-01-04 | N/A | N/A |  | 2018-02-01 | 2018-03-01 | 2018-03-09 | 2018-10-09
21 | Shoreline Protection Works at Epe Marina, Epe Phase 2 | MWFID/W/DC/007/2017 |  | 15000000 | <50M | NCB | BOQ | Post | Plan | Prior | [8 empty] | 4151156924.25
[9 empty] | Actual |  | 2017-09-16 | 2017-09-22 | 2017-09-29 | 2017-10-13 | 2017-10-20 | 2017-10-27 | N/A | N/A |  | 2017-11-24 | 2017-12-22 | 2019-06-21 | 2019-12-16
22 | Provision of Shoreline Protection at Alaguntan/okunkobo/Olomometa in Ojo LGA(Phase 1) | MWFID/W/NCB/ST/006/2017 |  | 448846.53 | <10M | NCB | BOQ | Post | Plan | Prior | [8 empty] | 0
[9 empty] | Actual |  | 2017-12-12 | 2017-12-19 | 2017-12-26 | 2018-01-09 | 2018-01-16 | 2018-01-23 | N/A | N/A |  | 2018-02-20 | 2018-03-20 | 2019-03-20 | 2019-03-27
23 | Provision of Shoreline Protection at Alaguntan/okunkobo/Olomometa in Ojo LGA(Phase 2) | MWFID/W/NCB/ST/006/2017 |  | 168218852.46 | <500M | NCB | BOQ | Post | Plan | Prior | [8 empty] | 0
[9 empty] | Actual |  | 2017-12-12 | 2017-12-19 | 2017-12-26 | 2018-01-09 | 2018-01-16 | 2018-01-23 | N/A | N/A |  | 2018-02-20 | 2018-03-20 | 2019-03-20 | 2019-03-27
24 | Contract Award for the Holistic Solution to Lagos State Ocean Surge between Goshen Estate to Alpha Beach using Groynes (Phase 2) | MWFID/W/ICB/002/2016 |  | 16000000 | <50M | NCB | BOQ | Post | Plan | Prior | [8 empty] | 0
[9 empty] | Actual |  | 2016-05-05 | 2016-05-12 | 2016-05-19 | 2016-06-02 | 2016-06-09 | 2016-06-06 | N/A | N/A
25 | Contract Award for the Holistic Solution to Lagos State Ocean Surge between Goshen Estate to Alpha Beach using Groynes (Phase 3) | MWFID/W/ICB/002/2016 |  | 317366516.44 | <500M | ICB | BOQ | Post | Plan | Prior | [8 empty] | 3000000000
[9 empty] | Actual |  | 2016-05-05 | 2016-05-12 | 2016-05-19 | 2016-06-02 | 2016-06-09 | 2016-06-06 | N/A | N/A |  | 2016-07-07 | 2016-08-04 | 5/4//17 | 2017-11-05
26 | Outstanding liability for Contract Award for the removal of Beached/Abandoned Shipwrecks from Lagos State Waterfront, Tug boat behind Tarkwa Bay. | MWFID/W/ST/002/02/2019 |  | 13093000 | <50M | NCB | BOQ | Post | Plan | Prior | [8 empty] | 495880000
[9 empty] | Actual |  | 2019-12-18 | 2019-12-18 | 2019-12-20 | 2019-12-20 | 2019-12-23 | 2019-12-24 | N/A | N/A |  | 2019-12-23 | 2019-12-24 | 2019-12-31
27 | Outstanding liability on Construction of Concrete Jetty with waiting Shelter and Shoreline Protection at Ito Omu, Epe | MWID/W/NCB/01/007/2017 |  | 188133814.58 | <500M | NCB | BOQ | Post | Plan | Prior | [8 empty] | 313556357
[9 empty] | Actual |  | 2017-08-01 | 2017-08-08 | 2017-08-15 | 2017-08-29 | 2017-09-05 | 2017-09-12 | N/A | N/A |  | 2017-10-10 | 2017-11-07 | 2018-07-09 | 2018-09-14
28 | Outstanding liability on Construction of Concrete Jetty with waiting Shelter and Shoreline Protection at Igbogbo / Baiyeku | MWID/W/NCB/01/003/17 |  | 14020697.16 | <50M | NCB | BOQ | Post | Plan | [9 empty] | 0
[9 empty] | Actual | Prior | 2017-08-01 | 2017-08-08 | 2017-08-15 | 2017-08-29 | 2017-09-05 | 2017-09-12 | N/A | N/A |  | 2020-09-19 | 2017-09-26 | 2017-10-10
29 | Outstanding liability on Construction of Concrete jetty with waiting shelter and shoreline protection at Apa Badagry | MWID/W/NCB/03/2017 |  | 55319617.36 | <100M | NCB | BOQ | Post | Plan |  | 13/03/17 | 2017-03-20 | 2017-03-27 | 2017-04-10 | 2017-04-17 | 2017-04-24 | N/A | N/A | 0
[9 empty] | Actual |  | 2017-08-08 | 2017-08-08 | 15/08/2017 | 29/08/17 | 2017-05-09 | 2017-12-09 | N/A | N/A
30 | Outstanding liability on Construction of Concrete jetty with waiting shelter and shoreline protection at VIP Charlet, Badagry | MWID/W/NCB/02/2017 |  | 52940645.46 | <100M | NCB | BOQ | Post | OST |  | 23/03/17 | 2017-03-30 | 2017-04-06 | 2017-04-20 | 2017-04-27 | 2017-05-04 | N/A | N/A | 0
[9 empty] | Actual | Prior | 2017-08-01 | 2017-08-08 | 15/08/17 | 29/08/17 | 2017-09-05 | 2017-09-12 | N/A | N/A |  | 2017-10-10 | 2017-11-07 | 2018-07-09 | 2018-07-23
31 | Outstanding liability on Construction of concrete jetty with waiting shelter and shoreline protection at Ilashe, Ojo | MWID/W/NCB/01/008/17 |  | 179716916 | <100M | NCB | BOQ | Post | Plan | [9 empty] | 0
[9 empty] | Actual | Pripor | 2017-08-01 | 2017-08-08 | 2017-08-15 | 2017-08-29 | 2017-05-09 | 2017-12-09 | N/A | N/A |  | 2017-10-10 | 2017-10-10 | 2017-11-07
32 | Outstanding liability on Construction of concrete jetty with waiting shelter and shoreline protection at Ilado, Amuwo Odofin | MWID/W/NCB/01/006/17 |  | 64378730.47 | <100M | NCB | BOQ | Post | Plan | [9 empty] | 0
[9 empty] | Actual | Prior | 2017-08-01 | 2017-08-08 | 2017-08-15 | 2017-08-29 | 2017-09-05 | 2017-09-12 | N/A | N/A |  | 2020-10-04 | 2020-10-07 | 2017-10-10 | 2017-10-17 | 2017-10-31
33 | Outstanding liability on Construction of Concrete jetty with waiting shelter and shoreline protection at Isalu Ajido, Badagry | MWID/W/NCB/01/005/17 |  | 84203359.45 | <100M | NCB | BOQ | Post | Plan | [9 empty] | 0
[9 empty] | Actual | Prior | 2017-08-01 | 08\08\2017 | 2017-08-15 | 2017-08-29 | 2017-09-05 | 2017-09-12 | N/A | N/A |  | 2017-10-10 | 2017-10-10 | 2017-11-07 | 2017-11-18
34 | Outstanding liability on Construction of Concrete jetty with waiting shelter and shoreline protection at Offin Waterfront Ikorodu | MWID/W/NCB/01/04/17 |  | 52581087.45 | <100M | NCB | BOQ | Post | Plan |  | 27/03/17 | 2017-04-03 | 2017-03-10 | 2017-03-24 | 2017-05-01 | 2017-05-08 | N/A | N/A | 0
[9 empty] | Actual | Prior | 2017-08-01 | 2017-08-08 | 15/08/17 | 29/08/17 | 2017-09-05 | 2017-09-12 | N/A | N/A |  | 2017-10-10 | 2017-10-17 | 2017-10-31
35 | Outstanding liability onConstruction of Concrete jetty with waiting shelter and shoreline protection at Takwa Bay Island | MWFID/W/NCB/RT/05/17 |  | 164013461.65 | <500M | NCB | BOQ | Post | Plan |  | 2017-05-24 | 2017-05-31 | 2017-06-07 | 2017-06-21 | 2017-06-28 | 24/07/17 | N/A | N/A | 0
[9 empty] | Actual | Prior | 2017-10-02 | 2017-10-09 | 16/10/17 | 30/10/17 | 2017-06-11 | 13/11/17 | N/A | N/A |  | 2017-11-07 | 2017-11-12 | 2017-01-01
36 | Outstanding liability on Construction of reinforced jetty with waiting shelter and Shoreline protection at Ijegun -Egba | MWID/W/RT/002-06/20 |  | 219162987 | <500M | NCB | BOQ | Post | Plan | [9 empty] | 339150364.82
[9 empty] | Actual |  | 2020-07-22 | 2020-07-24 | 2020-08-07 | 2020-08-10 | 2020-08-14 | 2020-08-17 | N/A | N/A |  | 2020-08-17 | 2020-08-17 | 2020-10-20
37 | Outstanding liability on Construction of reinforced jetty with waiting shelter and shoreline protection at Marina Badagry | MWID/W/RT/002-7/20 |  | 219162987 | <500M | NCB | BOQ | Post | Plan | [9 empty] | 479963587.5
[9 empty] | Actual |  | 2020-07-22 | 2020-07-24 | 2020-08-07 | 2020-08-10 | 2020-08-14 | 2020-09-02 | N/A | N/A
38 | Outstanding liability onConstruction of reinforced jetty with waiting shelter and shoreline protection at Ijede | MWID/W/RT/002-01/20 |  | 219162987 | <500M | NCB | BOQ | Post | Plan | [9 empty] | 409167383.72
[9 empty] | Actual |  | 2020-07-22 | 2020-07-24 | 2020-08-07 | 2020-08-10 | 2020-08-14 | 2020-08-17 | N/A | N/A |  | 2020-08-17 | 2020-08-17 | 2020-10-20
39 | Outstanding liability onConstruction of reinforced jetty with waiting shelter and shoreline protection at Oke-iranla | MWID/W/RT/002-02/20 |  | 219162987 | <500M | NCB | BOQ | Post | Plan | [9 empty] | 368932644
[9 empty] | Actual |  | 2020-07-22 | 2020-07-24 | 2020-08-07 | 2020-08-10 | 2020-08-14 | 2020-08-17 | N/A | N/A |  | 2020-08-17 | 2020-08-17 | 2020-10-20
40 | Construction of reinforced jetty with waiting shelter and shoreline protection at Mile 2 Amuwo Odofin | MWID/W/RT/002-03/20 |  | 219162987 | <500M | NCB | BOQ | Post | Plan | [9 empty] | 178860000
[9 empty] | Actual |  | 2020-07-22 | 2020-07-24 | 2020-08-07 | 2020-08-10 | 2020-08-14 | 2020-08-17 | N/A | N/A |  | 2020-08-17 | 2020-08-17 | 2020-10-20
41 | Outstanding liability on Construction of reinforced jetty with waiting shelter and shoreline protection at Liverpool Apapa | MWID/W/RT/002-04/20 |  | 219162987 | <500M | NCB | BOQ | Post | Plan | [9 empty] | 119604375
[9 empty] | Actual |  | 2020-07-22 | 2020-07-24 | 2020-08-07 | 2020-08-10 | 2020-08-14 | 2020-08-17 | N/A | N/A |  | 2020-08-17 | 2020-08-17 | 2020-10-20
42 | Outstanding liability on Construction of reinforced jetty with waiting shelter and shoreline protection at Ebute-Ero Lagos | MWID/W/RT/002-05/20 |  | 219162987 | <500M | NCB | BOQ | Post | Plan | [9 empty] | 215365308.88
[9 empty] | Actual |  | 2020-07-22 | 2020-07-24 | 2020-08-07 | 2020-08-10 | 2020-08-14 | 2020-08-17 | N/A | N/A |  | 2020-08-17 | 2020-08-17 | 2020-10-20
43 | Channelization of Ferry Route from Ojo- Badagry | MWID/W/ST/003-1/20 |  | 225000000 | <500M | ST | BOQ | POST | Plan | [9 empty] | 4663799990
[9 empty] | Actual |  | 2020-12-01 | 2020-12-07 | 2020-12-07 | 2020-12-09 | 2020-12-10 | 2020-12-11 | N/A | N/A |  | 2020-12-11 | 2020-12-11 | 2020-12-28
44 | Provision of Holistic Shoreline Protection Phase 4, Goshen Estate | MWID/W/ICB/001/20 |  | 2544578963.04 | <5b | ICB | BEME | POST | Plan
[9 empty] | Actual |  | 2020-02-10 | 2020-02-17 | 2020-02-24 | 2020-03-02 | 2020-03-16 | 2020-03-23 | 2020-03-30 | 2020-04-06 |  | 2020-04-13 | 2020-04-20 | 2020-04-27 | 2020-05-11
45 | Channelization of Ferry Route from Ikorodu-Ilaje-Falomo | MWID/W/ST/010-2/20 |  | 200000000 | <500M | NCB | BOQ | Post | Plan | Prior | [8 empty] | 3028000000
[9 empty] | Actual |  | 2020-12-01 | 2020-12-07 | 2020-12-07 | 2020-12-09 | 2020-12-10 | 2020-12-11 | N/A | N/A |  | 2020-12-11 | 2020-12-11 | 2020-12-28