## Non-Proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/AGENCY: OFFICE OF ENVIRONMENTAL SERVICES, MINISTRY OF THE ENVIRONMENT AND WATER RESOURCES
BUDGET YEAR: 2021
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TOTAL
1 | Allowances for 20 Nos of Security personnel in the six Zero tolerance Offices | MOE&WR/OES/NP/NM/001/21 | 272000 | Plan | 22666.67 | 22666.67 | 22666.67 | 22666.67 | 22666.67 | 22666.67 | 22666.67 | 22666.67 | 22666.67 | 22666.67 | 22666.67 | 22666.67 | 272000
Actual
2 | Allowance for 80 Nos of out-Station Officers exposed to hazard in LGs and LCDAs in the State | MOE&WR/OES/NP/NM/002/21 | 1728000 | Plan | 144000 | 144000 | 144000 | 144000 | 144000 | 144000 | 144000 | 144000 | 144000 | 144000 | 144000 | 144000 | 1728000
Actual
3 | Payment of wages to 100 Nos of ESCU and Highway sanitation operatives | MOE&WR/OES/NP/NM/003/21 | 36526000 | Plan | 3043833.33 | 3043833.33 | 3043833.33 | 3043833.33 | 3043833.33 | 3043833.33 | 3043833.33 | 3043833.33 | 3043833.33 | 3043833.33 | 3043833.33 | 3043833.33 | 36526000
Actual
4 | Travel and Transport | MOE&WR/OES/NP/NM/004/21 | 21810000 | Plan | 1817500 | 1817500 | 1817500 | 1817500 | 1817500 | 1817500 | 1817500 | 1817500 | 1817500 | 1817500 | 1817500 | 1817500 | 21810000
Actual
5 | General Utility Service e.g DSTV sUbscription, recharge cards for Pnones etc | MOE&WR/OES/NP/NM/005/21 | 2244800 | Plan | 187066.66 | 187066.66 | 187066.66 | 187066.66 | 187066.66 | 187066.66 | 187066.66 | 187066.66 | 187066.66 | 187066.66 | 187066.66 | 187066.66 | 2244800
Actual
6 | Irrevocable Standing Payment order (ISPO) Special Intervention Programme | MOE&WR/OES/NP/NM/006/21 | 6400290000 | Plan | 533375500 | 533375500 | 533375500 | 533375500 | 533375500 | 533375500 | 533375500 | 533375500 | 533375500 | 533375500 | 533375500 | 533375500 | 6400290000
Actual
7 | Monthly Market Survey | MOE&WR/OES/NP/NM/007/21 | 600000 | Plan | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 600000
Actual
8 | Preparation and production of Procurement Plan | MOE&WR/OES/NP/NM/008/21 | 200000 | Plan |  | 200000 | [10 empty] | 200000
Actual
9 | Monthly wages of 10 Nos of Security operatives | MOE&WR/OES/NP/NM/009/21 | 4200000 | Plan | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 4200000
Actual
10 | Biodiversity day | MOE&WR/OES/NP/NM/010/21 | 2500000 | Plan |  |  |  |  | 2500000 | [7 empty] | 2500000
Actual
11 | Walk for Nature | MOE&WR/OES/NP/NM/011/21 | 3500000 | Plan | [9 empty] | 3500000 |  |  | 3500000
Actual
12 | World Soil Day | MOE&WR/OES/NP/NM/012/21 | 1500000 | Plan | [11 empty] | 1500000 | 1500000
Actual
13 | World Environmental Day | MOE&WR/OES/NM/013/20 | 2500000 | Plan
|  |  |  | Actual | [5 empty] | 2500000 | [6 empty] | 2500000
14 | World Toilet Day | MOE&WR/OES/NP/NM/014/21 | 1500000 | Plan | [10 empty] | 1500000 |  | 1500000
Actual
15 | One day Advocacy programme within Slaughter Slab/Abbattoirs across the State | MOE&WR/OES/NP/NM/015/21 | 2000000 | Plan | [9 empty] | 2000000 |  |  | 2000000
Actual
16 | Quarterly monitoring of envirironmental Projects across in the 5 Divisions | MOE&WR/OES/NP/NM/016/21 | 5000000 | Plan |  |  | 1250000 |  |  | 1250000 |  |  | 1250000 |  |  | 1250000 | 5000000
Actual
17 | Quarterly Market/Artisan Environmental Sanitation Exercise/Town Hall Meeting | MOE&WR/OES/NP/NM/017/21 | 4000000 | Plan |  |  | 1000000 |  |  | 1000000 |  |  | 1000000 |  |  | 1000000 | 4000000
Actual
18 | Quarterly Monitoring and Advocacy of Abbatoirs | MOE&WR/OES/NP/NM/018/21 | 2000000 | Plan |  |  | 500000 |  |  | 500000 |  |  | 500000 |  |  | 500000 | 2000000
Actual
19 | Annual Environmental Education day for all Stakeholders | MOE&WR/OES/NP/NM/019/21 | 4000000 | Plan | [5 empty] | 4000000 | [6 empty] | 4000000
Actual
20 | Monthly Meetings for Environmental Education Champions in the MDAs | MOE&WR/OES/NP/NM/020/21 | 500000 | Plan | 41666.66 | 41666.66 | 41666.66 | 41666.66 | 41666.66 | 41666.66 | 41666.66 | 41666.66 | 41666.66 | 41666.66 | 41666.66 | 41666.66 | 500000
Actual
21 | Quarterly in-house training for Environmental Education Champions in MDAs | MOE&WR/OES/NP/NM/021/21 | 400000 | Plan |  |  | 100000 |  |  | 100000 |  |  | 100000 |  |  | 100000 | 400000
Actual
22 | Environmental Education awareness in LGs and LCDAs in the State | MOE&WR/OES/NP/NM/022/21 | 2900000 | Plan | [9 empty] | 2900000 |  |  | 2900000
Actual
23 | Monitoring and documentation of waste management (Waste to Wealth) | MOE&WR/OES/NP/NM/023/21 | 1000000 | Plan |  |  |  |  | 1000000 | [7 empty] | 1000000
Actual
24 | Monthly wages for 66 Nos of Operatives against open defacation | MOE&WR/OES/NP/NM/024/21 | 24480000 | Plan | 2040000 | 2040000 | 2040000 | 2040000 | 2040000 | 2040000 | 2040000 | 2040000 | 2040000 | 2040000 | 2040000 | 2040000 | 24480000
Actual
25 | Monthly running cost for the office SSA and other offices in charge of anti open defecation in the State | MOE&WR/OES/NP/NM/025/21 | 31800000 | Plan | 2650000 | 2650000 | 2650000 | 2650000 | 2650000 | 2650000 | 2650000 | 2650000 | 2650000 | 2650000 | 2650000 | 2650000 | 31800000
Actual
26 | Monitoring and ensuring standard of Environmental and hygiene best practices in Eateries and Event Centrs within the State | MOE&WR/OES/NP/NM/026/21 | 2000000 | Plan | [8 empty] | 2000000 |  |  |  | 2000000
Actual
27 | Servicing of 10 Nos of Meetings of the Advisory Sub-Committee/Sanitation Stakeholders | MOE&WR/OES/NP/NM/027/21 | 2000000 | Plan |  |  | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 2000000
Actual
28 | Monthly meeting of water sanitation and hygienic (WASH) Committee | MOE&WR/OES/NP/NM/028/21 | 1500000 | Plan | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 1500000
Actual
29 | Staff welfare for 400 Nos of Staff | MOE&WR/OES/NP/NM/029/21 | 8900000 | Plan |  |  | 890000 | 890000 | 890000 | 890000 | 890000 | 890000 | 890000 | 890000 | 890000 | 890000 | 8900000
Actual
30 | Civil Service Week | MOE&WR/OES/NP/NM/030/21 | 700000 | Plan | [5 empty] | 700000 | [6 empty] | 700000
Actual
31 | Hos Annual Football Competition | MOE&WR/OES/NP/NM/031/2 | 500000 | Plan | [10 empty] | 500000 |  | 500000
Actual
32 | Senior Special Adviser Related Expenses | MOE&WR/OES/NP/NM/032/21 | 2500000 | Plan |  |  | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 2500000
Actual
33 | Evaluation of Bids and Proposals | MOE&WR/OES/NP/NM/033/21 | 3000000 | Plan | [7 empty] | 3000000 |  |  |  |  | 3000000
Actual
34 | Support and collaboration with Local NGO on Climate Change related Issues | MOE&WR/OES/NP/NM/034/21 | 2000000 | Plan | [9 empty] | 2000000 |  |  | 2000000
Actual
35 | Payment of dues for membership of international organisation of Climate Change related programmes | MOE&WR/OES/NP/NM/035/21 | 5000000 | Plan | [10 empty] | 5000000 |  | 5000000
Actual
36 | Management, Strategic and Unscheduled meetings | MOE&WR/OES/NP/NM/036/21 | 2200000 | Plan |  |  | 220000 | 220000 | 220000 | 220000 | 220000 | 220000 | 220000 | 220000 | 220000 | 220000 | 2200000
Actual
37 | Development of Environmental Policy and regulation for Municipal Solid waste and extended producer Responsibility (EPR) across all waste streams | MOE&WR/OES/NP/NM/037/21 | 12000000 | Plan |  |  | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 12000000
Actual
38 | Coordination of Environmental Impact Assesment process across the five (5) divisions of the State | MOE&WR/OES/NP/NM/038/21 | 15000000 | Plan |  |  |  | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 2200000 | 15000000
Actual
39 | Field work for the assessment of Public exposure to Radio frequency emission from BTS | MOE&WR/OES/NP/NM/039/21 | 5000000 | Plan |  |  |  |  | 2000000 | 2000000 | 1000000 | [5 empty] | 5000000
Actual
40 | Hiring of Boat for Impact Mitigation Exercises (IMME) for developmental projects in the State | MOE&WR/OES/NP/NM/040/21 | 2160000 | Plan |  |  |  | 2160000 | [8 empty] | 2160000
Actual
41 | Last Day in Office for 30 Nos of Staff | MOE&WR/OES/NP/NM/041/21 | 6000000 | Plan |  |  | 1500000 |  |  | 1500000 |  |  | 1500000 |  |  | 1500000 | 6000000
Actual
42 | Monthly operational cost for Zero tolerance offices | MOE&WR/OES/NP/NM/042/21 | 1200000 | Plan | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 1200000
Actual
43 | Renewal of of 30 Nos Pool and Utility Vehicle licence | MOE&WR/OES/NP/NM/043/21 | 600000 | Plan | [10 empty] | 600000 |  | 600000
Actual
44 | Monthly Staff Audit of Agencies under OES | MOE&WR/OES/NP/NM/044/21 | 1200000 | Plan | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 1200000
Actual
45 | Monitoring of degraded and hazaed prone areas and development of appropriate mitigation measures in the LGs and LCDAs of the State | MOE&WR/OES/NP/NM/045/21 | 2000000 | Plan |  |  | 1000000 |  |  | 1000000 |  |  | 1000000 |  |  | 1000000 | 2000000
Actual
46 | Awareness campaign on wetlands and biodiversity conservation in 3 divisions within the State | MOE&WR/OES/NP/NM/046/21 | 6000000 | Plan |  | 1000000 |  | 1000000 |  | 1000000 |  | 1000000 |  | 1000000 |  | 1000000 | 6000000
Actual
47 | Monitoring of landscaped and beautified sites within the State | MOE&WR/OES/NP/NM/047/20 | 2000000 | Plan |  | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 |  | 2000000
Actual
48 | Monitoring of wetlands and biodiversity within the State | MOE&WR/OES/NP/NM/048/21 | 2000000 | Plan |  | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 |  | 2000000
Actual
49 | Monitoring of 5,760 Projects across the State | MOE&WR/OES/NP/NM/049/21 | 2965200 | Plan |  |  | 296520 | 296520 | 296520 | 296520 | 296520 | 296520 | 296520 | 296520 | 296520 | 296520 | 2965200
Actual
50 | Lega Unit Related Expenses | MOE&WR/OES/NP/NM/050/21 | 4500000 | Plan | [8 empty] | 4500000 |  |  |  | 4,500.000.00
Actual
51 | Security back-up (Army, Police NSCDC) for enforcement activities | MOE&WR/OES/NP/NM/051/21 | 14400000 | Plan |  | 1440000 | 1440000 | 1440000 | 1440000 | 1440000 | 1440000 | 1440000 | 1440000 | 1440000 | 1440000 |  | 14400000
Actual
52 | Monthly payment for 112 Nos of Adhoc Staff | MOE&WR/OES/NP/NM/052/21 | 53560000 | Plan | 4463333.33 | 4463333.33 | 4463333.33 | 4463333.33 | 4463333.33 | 4463333.33 | 4463333.33 | 4463333.33 | 4463333.33 | 4463333.33 | 4463333.33 | 4463333.33 | 53560000
Actual
53 | Annual Sensitization of Bees Club Members/Membership drive in Public and Private Schools in the State | MOE&WR/OES/NP/NM/053/22 | 2600000 | Plan |  |  |  | 2600000 | [8 empty] | 2600000
Actual
54 | Annual TV Quiz Programme for 21 Winners of BEEs Club/Environmental Schools Project in the State | MOE&WR/OES/NP/NM/054/23 | 5600000 | Plan | [5 empty] | 5600000 | [6 empty] | 5600000
Actual
55 | Quarterly meeting of food Handlers across the State | MOE&WR/OES/NP/NM/055/23 | 6000000 | Plan |  |  | 1500000 |  |  | 1500000 |  |  | 1500000 |  |  | 1500000 | 6000000
Actual
56 | Monthly allowance for 15 Nos of Demolition Gang and Casual workers | MOE&WR/OES/NP/NM/056/21 | 4320000 | Plan | 360000 | 360000 | 360000 | 360000 | 360000 | 360000 | 360000 | 360000 | 360000 | 360000 | 360000 | 360000 | 4320000
Actual
| TOTAL |  | 6730856000 | [13 empty] | 6730856000

## trg conf wsh
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: Office of Environmetal Services, Ministry of the Environment and Water Resources
BUDGET YEAR: 2021
| Description of Training/Workshop/ Conference | Package Number | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | Training and Workshop for Junior staff | MOE&WR/OES/S-WTC/SS/001/21 |  | 100 | 3 | Plan |  | 15000 | 5000 | 10000 | 3000000
Actual
2 | Training and Workshop for Senior Staff | MOE&WR/OES/S-WTC/SS/002/21 |  | 40 | 3 | Plan |  | 30000 | 10000 | 10000 | 2000000
Actual
3 | Professional Conference for Junior Staff | MOE&WR/OES/S-WTC/SS/003/21 |  | 50 | 3 | Plan |  | 30000 | 20000 | 30000 | 4000000
Actual
4 | Professional Conference for Senior Staff | MOE&WR/OES/S-WTC/SS/004/21 |  | 30 | 4 | Plan |  | 60000 | 60000 | 80000 | 6000000
Actual
5 | Training on International Public Sector Accounting | MOE&WR/OES/S-WTC/SS/005/21 |  | 1 |  | Plan |  | 60000 | 60000 | 80000 | 200000
Actual
6 | Financial Audit Training | MOE&WR/OES/S-WTC/SS/006/21 |  | 3 |  | Plan |  | 60000 | 100000 | 106666.66 | 800000
Actual
7 | Institute of Internal Auditors Programme | MOE&WR/OES/S-WTC/SS/007/21 |  | 2 |  | Plan |  | 60000 | 118266.66 | 100000 | 834800
Actual
8 | Seminar for the wives of 35 Nos of of Staff at the annual meeting of Committee of Wives of Lagos State officials (COWLSO) | MOE&WR/OES/S-WTC/SS/008/21 | [5 empty] | 30000 | 20000 | 37500 | 5250000
9 | Professional Conference organised by Nigerian Statistical Association | MOE&WR/OES/S-WTC/SS/009/21 |  | 4 | 3 | Plan |  | 80000 | 100000 | 195000 | 1500000
Actual
10 | Professional Course organised by Nigerian Economic Society | MOE&WR/OES/S-WTC/SS/010/21 |  | 4 | 3 | Plan |  | 80000 | 100000 | 120000 | 1200000
Actual
11 | Effective Budget Planning System and its impact on Procurement implementation in MDAs | MOE&WR/OES/S-WTC/SS/011/21 |  | 2 |  | Plan |  | 80000 | 150000 | 170000 | 800000
Actual
12 | Annual Conference for Procurement Professional members | MOE&WR/OES/S-WTC/SS/012/21 |  |  |  | Plan |  | 60000 | 200000 | 340000 | 1200000
Actual
13 | Training on Uniformity of understanding, appreciation and reportage of the monitoring report templates for the State of the Environment in the State | MOE&WR/OES/S-WTC/SS/013/21 |  | 226 |  | Plan |  |  |  | 9734.51 | 2200000
Actual
14 | Annual Sectorial Retreat | MOE&WR/OES/S-WTC/SS/014/21 |  | 60 |  | Plan |  |  |  |  | 10150000
Actual
15 | Annual Climate Change Summit | MOE&WR/OES/S-WTC/SS/015/21 |  | 150 | [6 empty] | 105000000
16 | Excursions/Training for Teachers incharge of the Environmental Bees Club in Schools | MOE&WR/OES/S-WTC/SS/016/21 |  | 175 | [6 empty] | 5000000
| TOTAL | [9 empty] | 149134800

## non-cons
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY: office of Environmental Services, Ministry of the Environment and Water Resources
BUDGET YEAR: 2021
Contract Description | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
| Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
Maintenance of office Building | MOE&WR/OES/S-NC-F/NS/001/21 |  | Various | 2736400 | <50M | NS | Plan | Pre | Post | 01-Mar-'21 | NA | 03-Mar-'21 | 08-Mar-'21 | 11-Mar-'21 | 16-Mar-'21 | NA | Plan | 23-Mar-'21 | NA | 2736400 | 25-Mar-'21 | NA | 08-Apr-''21 | 30-Dec-''21
[7 empty] | Actual | [9 empty] | Actual
Maintenance & Repairs of Operational Vehicles | MOE&WR/OES/S-NC-F/NS/002/21 |  | 100 | 12450000 | <50M | NS | Plan | Pre | Post | 01-Mar-'21 | NA | 03-Mar-'21 | 08-Mar-'21 | 11-Mar-'21 | 16-Mar-'21 | NA | Plan | 23-Mar-'21 | NA | 12450000 | 25-Mar-'21 | NA | 08-Apr-''21 | 30-Dec-''21
[7 empty] | Actual | [9 empty] | Actual
Maintenance and Repairs of Trucks | MOE&WR/OES/S-NC-F/NS/003/21 |  | 4 | 4800000 | <50M | NS | Plan | Pre | Post | 01-Mar-'21 | NA | 03-Mar-'21 | 08-Mar-'21 | 11-Mar-'21 | 16-Mar-'21 | NA | Plan | 23-Mar-'21 | NA | 4800000 | 25-Mar-'21 | NA | 08-Apr-''21 | 30-Dec-''21
Actual
Maintenance and Repairs of 375KVA, 27KVA and Submersible Pumps | MOE&WR/OES/S-NC-F/NS/004/21 |  | 2 | 2350000 | <50M | NS | Plan | Pre | Post | 01-Mar-'21 | NA | 03-Mar-'21 | 08-Mar-'21 | 11-Mar-'21 | 16-Mar-'21 | NA | Plan | 23-Mar-'21 | NA | 2350000 | 25-Mar-'21 | NA | 08-Apr-''21 | 30-Dec-''21
[7 empty] | Actual | [9 empty] | Actual
Mtce and Repairs of office Equipment | MOE&WR/OES/S-NC-F/NS/005/21 |  | various | 3000000 | <50M | NS | Plan | Pre | Post | 01-Mar-'21 | NA | 03-Mar-'21 | 08-Mar-'21 | 11-Mar-'21 | 16-Mar-'21 | NA | Plan | 23-Mar-'21 | NA | 3000000 | 25-Mar-'21 | NA | 08-Apr-''21 | 30-Dec-''21
[7 empty] | Actual | [9 empty] | Actual
Annual Environmental Education Bees Club Anniversary in Public and Private Schools/Governor's one day out with the EBC members to give score card and render report in the State | MOE&WR/OES/S-NC/NS/006/21 |  |  | 14000000 | <50M | NS | Plan | Pre | Post | 26-Mar-''21 | 30-Mar-''21 | 31-Mar-''21 | 05-Apr-''21 | 07-Apr-''21 | NA | NA |  | 14-Apr-''21 | 16-Apr-''21 | 14000000 | 20-Apr--''21 | 27-Apr-''21 | 04-May-''21 | 05-May-''21
Actual
Hiring of heavy Equipment for Enforcement activities | MOE&WR/OES/S-NC-F/NS/007/21 |  | 12 | 65280000 | <100M | NS | Plan | Pre | Post | 09-Mar-''21 | 11-Mar-''21 | 16-Mar-''21 | 19-Mar-''21 | 23-Mar-''21 | 25-Mar-''21 | NA |  | 01-Apr-''21 | 05-Apr-''21 | 65280000 | 08-Apr-''21 | 15-Apr-''21 | 29-Apr-''21 | 30-Dec-''21
Actual
TOTAL |  |  |  | 104616400 | [15 empty] | 104616400

## consultancy
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/ AGENCY: Ministry of Environment and Water Resources, Office of Environmental Services
BUDGET YEAR: 2021
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[5 empty] | 0 |  | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks
Actual
1 | Asssessment of the Oil impacted areas and development of remediation strategies in the 5 divisions in the State | MOE&WR/OES/S-C/LCS/001/2 | LCS | LS | 28000000 | POST | Plan | 10-Mar-''21 | 12-Mar-''21 | NA | NA | NA | 15-Mar-''21 | 18-Mar-''21 | 19-Mar-''21 | 22-Apr-''21 | 24-Apr-''21 | 26-Apr-''21 | 29-Apr-''21 | 05-Apr-''21 | 07-May-''21 | 28000000 | 08-May-''21 | 13-May-''21 | 20-May-''21 | 26-Jun''21 | 229-Jun-''21
Actual
2 | Study of Carbon Footprint and vulnerability | MOE&WR/OES/S-C/LCS/002/21 | LCS | LS | 10000000 | POST | Plan | 10-Mar-''21 | 12-Mar-''21 | NA | NA | NA | 15-Mar-''21 | 18-Mar-''21 | 19-Mar-''21 | 22-Apr-''21 | 24-Apr-''21 | 26-Apr-''21 | 29-Apr-''21 | 05-Apr-''21 | 07-May-''21 | 10000000 | 08-May-''21 | 13-May-''21 | 20-May-''21 | 26-Jun''21 | 229-Jun-''21
Actual
| Study on Gender based Climate Adaptation | MOE&WR/OES/S-C/LCS/003/21 |  |  | 10000000 |  |  | 14-May-''21 | 18-May-''21 | NA | NA | NA | 20-May-''21 | 25-May-''21 | 27-May-''21 | 28-May-''21 | 31-May-''21 | 03-Jun-''21 | 07-Jun-''21 | 14-Jun-''21 | 16-Jun-''21 | 10000000 | 17-Jun-''21 | 22-Jun-''21 | 28-Jun-''21 | 23-Aug-''21 | 4-Sep-''21
4 | Study to upgrade/update the Lagos State Wetlands Study field Report 2009 and review of the draft policy on wetland Management and conservation of its biodiversity 2016 | MOE&WR/OES/S-C/LCS/004/21 | LCS | LS | 41000000 | POST | Plan | 10-Mar-''21 | 12-Mar-''21 | NA | NA | NA | 15-Mar-''21 | 18-Mar-''21 | 19-Mar-''21 | 22-Apr-''21 | 24-Apr-''21 | 26-Apr-''21 | 29-Apr-''21 | 05-Apr-''21 | 07-May-''21 | 41000000 | 08-May-''21 | 13-May-''21 | 20-May-''21 | 26-Jun''21 | 229-Jun-''21
Actual
5 | Study on Internationally declared endangered Marine Animals and Terrestrial organisms in Lagos State | MOE&WR/OES/S-C/LCS/005/21 | LCS | LS | 20000000 | POST | Plan | 14-Apr-''21 | 16-Apr-''21 | NA | NA | NA | 19-Apr-''20 | 22-Apr-''21 | 23-Apr-''21 | 26-Apr-''21 | 28-Apr-''21 | 30-Apr-''21 | 04-May-''21 | 11-May-''21 | 13-May-''21 | 20000000 | 14-May-''20 | 18-May-''21 | 21-May-''21 | 13-Aug-''21 | 20-Aug-''21
Actual
8 | Study on Public perception on the state of the environment in Lagos State | MOE&WR/OES/S-C/LCS/006/21 | LCS | LS | 10000000 | POST | Plan | 3-Jun-''21 | 07-Jun-''21 | NA | NA | NA | 09-Jun-''21 | 14-Jun-''21 | 17-Jun-''21 | 18-Jun-''21 | 21-Jun-''21 | 23-Jun-''21 | 25-Jun-''21 | 02-Jul-''21 | 05-Jul-''21 | 10000000 | 07-Jul-''21 | 09-Jul-''21 | 14-Jul-''21 | 18-Aug-''21 | 24-Aug-''21
Actual
| Ecosystem Based Adaptation study for Lagos State | MOE&WR/OES/S-C/LCS/007/21 |  |  | 15000000 |  |  | 14-Apr-''21 | 16-Apr-''21 | NA | NA | NA | 19-Apr-''20 | 22-Apr-''21 | 23-Apr-''21 | 26-Apr-''21 | 28-Apr-''21 | 30-Apr-''21 | 04-May-''21 | 11-May-''21 | 13-May-''21 | 15000000 | 14-May-''20 | 18-May-''21 | 21-May-''21 | 13-Aug-''21 | 20-Aug-''21
10 | Study on Ecological Conservation Project Development | MOE&WR/OES/S-C/LCS/008/21 | LCS | LS | 11244741 | POST | Plan | 14-Apr-''21 | 16-Apr-''21 | NA | NA | NA | 19-Apr-''20 | 22-Apr-''21 | 23-Apr-''21 | 26-Apr-''21 | 28-Apr-''21 | 30-Apr-''21 | 04-May-''21 | 11-May-''21 | 13-May-''21 | 11244741 | 14-May-''20 | 18-May-''21 | 21-May-''21 | 13-Aug-''21 | 20-Aug-''21
Actual
14 | Study to provide information to guide future policy making, programme development and for pursuing Landfill diversion technologies | MOE&WR/OES/S-C/LCS/009/21 | LCS | LS | 48100000 | POST | Plan | 11-Mar-''21 | 15-Mar-''21 | NA | NA | NA | 17-Mar-''21 | 22-Mar-''21 | 25-Mar-''21 | 26-Mar-''21 | 30-Mar-''21 | 01-Apr-''21 | 02-Apr-''21 | 09-Apr-''21 | 13-Apr-''21 | 48100000 | 14-Apr-''21 | 16-Apr-''21 | 21-Apr-''21 | 22-Jun-''21 | 29-Jul-''21
Actual
15 | Study to track performance of LAWMA Bluebox programme | MOE&WR/OES/S-C/LCS/010/21 | LCS | LS | 7000000 | POST | Plan | 11-Mar-''21 | 15-Mar-''21 | NA | NA | NA | 17-Mar-''21 | 22-Mar-''21 | 25-Mar-''21 | 26-Mar-''21 | 30-Mar-''21 | 01-Apr-''21 | 02-Apr-''21 | 09-Apr-''21 | 13-Apr-''21 | 7000000 | 14-Apr-''21 | 16-Apr-''21 | 21-Apr-''21 | 22-Jun-''21 | 29-Jul-''21
Actual
16 | Public survey for assessment of payment and quality of PSP Service | MOE&WR/OES/S-C/LCS/011/21 | LCS | LS | 12000000 | POST | Plan | 11-Mar-''21 | 15-Mar-''21 | NA | NA | NA | 17-Mar-''21 | 22-Mar-''21 | 25-Mar-''21 | 26-Mar-''21 | 30-Mar-''21 | 01-Apr-''21 | 02-Apr-''21 | 09-Apr-''21 | 13-Apr-''21 | 12000000 | 14-Apr-''21 | 16-Apr-''21 | 21-Apr-''21 | 22-Jun-''21 | 29-Jul-''21
Actual
17 | Establishment of database, data collation and processing hub and customised data processing software and ICT Network | MOE&WR/OES/S-C/LCS/012/21 | LCS | LS | 17500000 | POST | Plan | 11-Mar-''21 | 15-Mar-''21 | NA | NA | NA | 17-Mar-''21 | 22-Mar-''21 | 25-Mar-''21 | 26-Mar-''21 | 30-Mar-''21 | 01-Apr-''21 | 02-Apr-''21 | 09-Apr-''21 | 13-Apr-''21 | 17500000 | 14-Apr-''21 | 16-Apr-''21 | 21-Apr-''21 | 22-Jun-''21 | 29-Jul-''21
Actual
| Annual Environmental Education Summer workshop/International School Exchange for Public Schools In Lagos State | MOE&WR/OES/S-C/LCS/013/21 | LCS | LS | 37000000 | POST |  | 14-Apr-''21 | 16-Apr-''21 | NA | NA | NA | 19-Apr-''20 | 22-Apr-''21 | 23-Apr-''21 | 26-Apr-''21 | 28-Apr-''21 | 30-Apr-''21 | 04-May-''21 | 11-May-''21 | 13-May-''21 | 37000000 | 14-May-''20 | 18-May-''21 | 21-May-''21 | 13-Aug-''21 | 20-Aug-''21
18 | Engagement of a firm for PSP Capacity assessment and RFID Tagging of PSP Trucks and LAWMA | MOE&WR/OES/S-C/LCS/014/21 | LCS | LS | 15500000 | POST | Plan | 11-Mar-''21 | 15-Mar-''21 | NA | NA | NA | 17-Mar-''21 | 22-Mar-''21 | 25-Mar-''21 | 26-Mar-''21 | 30-Mar-''21 | 01-Apr-''21 | 02-Apr-''21 | 09-Apr-''21 | 13-Apr-''21 | 15500000 | 14-Apr-''21 | 16-Apr-''21 | 21-Apr-''21 | 22-Jun-''21 | 29-Jul-''21
Actual
| TOTAL |  |  |  | 282344741 | [16 empty] | 282344741

## goods
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: Office of Environmental Services, Ministry of the Environment and Water Resources
BUDGET YEAR: 2021
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Procurement of Stationery Items | MOE&WR/OES/G-F/NS/001/21 |  | Various | 7408800 | <50M | NS | PRE | Post | Plan | 24-Feb-''21 | NA | 26-Feb-''21 | 03-Mar-''21 | 05-Mar-''21 | NA | 12-Mar-''21 | 16-Mar''21 | 7408800 | 18-Mar-''21 | 23-Mar-''21 | NA | 30-Mar-''21 | 29-Dec-''21
Actual
2 | Procurement of 30 Nos of Desktops, 6 Nos of Laptops and Computer consumables /Assessories | MOE &WR/OES/G/NS/002/21 |  |  | 18704543 | <50M | NS | PRE | Post | Plan | 17-Mar-''21 | 19-Mar''21 | 23-Mar-''21 | 26-Mar-''21 | 30-Mar-''21 | NA | 06-Apr-''21 | 08-Apr-''21 | 18704543 | 09-Apr-''21 | 13-Apr-''21 | 16-Apr-''21 | 14-May-''21 | 18-May-''21
Actual
3 | Procurement of 3 Nos of 1 1/2 Air Conditioner | MOE &WR/OES/G/NS/003/21 |  | 3 | 750000 | <50M | NS | PRE |  | Plan | 24-Feb-''21 | NA | 26-Feb-''21 | 03-Mar-''21 | 05-Mar-''21 | NA | 12-Mar-''21 | 16-Mar''21 | 750000 | 18-Mar-''21 | 23-Mar-''21 | NA | 30-Mar-''21 | 29-Dec-''21
Actual
4 | Procurement of 20Nos International Journals and 30Nos Professional textbooks | MOE &WR/OES/G/NS/004/21 |  | Various | 300000 | <50M | NS | PRE | Post | Plan | 24-Feb-''21 | NA | 26-Feb-''21 | 03-Mar-''21 | 05-Mar-''21 | NA | 12-Mar-''21 | 16-Mar''21 | 300000 | 18-Mar-''21 | 23-Mar-''21 | NA | 30-Mar-''21 | 29-Dec-''21
Actual
5 | Procurement of Uniform and Protectives outfits | MOE &WR/OES/G/NS/005/21 |  | Various | 3475250 | <50M | NS | PRE | Post | Plan | 24-Feb-''21 | NA | 26-Feb-''21 | 03-Mar-''21 | 05-Mar-''21 | NA | 12-Mar-''21 | 16-Mar''21 | 3475250 | 18-Mar-''21 | 23-Mar-''21 | NA | 30-Mar-''21 | 29-Dec-''21
Actual
6 | Printing and Production of 4,000 copies of Lagos State Climate Change Policy | MOE &WR/OES/G/DC/006/21 |  | 4000 | 10000000 | <50M | NS | PRE | Post | Plan | 02-Mar-''21 | 04-Mar-''21 | 05-Mar-''21 | 10-Mar-''21 | 12-Mar-''21 | NA | 19-Mar-''21 | 22-Mar-''21 | 10000000 | 23-Mar-''21 | 26-Mar-''21 | 14-Jun-''21 | 31-Mar-''21 | 01-Apr-''21
Actual
7 | Printing of 50 Copies of Climate Action Plan (CAP) | MOE &WR/OES/G/DC/007/21 |  | 50 | 1000000 | <50M | NS | NS | Post | Plan | 02-Mar-''21 | 04-Mar-''21 | 05-Mar-''21 | 10-Mar-''21 | 12-Mar-''21 | NA | 19-Mar-''21 | 22-Mar-''21 | 1000000 | 23-Mar-''21 | 26-Mar-''21 | 14-Jun-''21 | 31-Mar-''21 | 01-Apr-''21
Actual
8 | Printing of 1,000 copies of Letter head papers | MOE &WR/OES/G/DC/008/21 |  | 1000 | 1000000 | <50M | NS | PRE | Post | Plan | 02-Mar-''21 | 04-Mar-''21 | 05-Mar-''21 | 10-Mar-''21 | 12-Mar-''21 | NA | 19-Mar-''21 | 22-Mar-''21 | 1000000 | 23-Mar-''21 | 26-Mar-''21 | 14-Jun-''21 | 31-Mar-''21 | 01-Apr-''21
Actual
9 | Bi-Annual Publishing of Journals on Environmental Issues | MOE &WR/OES/G/DC/009/21 |  | 2500 | 2500000 | <50M | NS | PRE | Post | Plan | 13-Apr-''21 | NA | 15-Apr-''21 | 20-Apr-''21 | 22-Apr-''21 | NA | 29-Apr-''21 | 03-May-''21 | 2500000 | 04-May-''21 | 07-May-''21 | NA | 21-May-''21 | 24-May-''21
Actual
10 | Printing of Environmental Education Manual | MOE &WR/OES/G/DC/010/21 |  | 2000 | 5000000 | <50M | NS | PRE | Post | Plan | 13-Apr-''21 | NA | 15-Apr-''21 | 20-Apr-''21 | 22-Apr-''21 | NA | 29-Apr-''21 | 03-May-''21 | 5000000 | 04-May-''21 | 07-May-''21 | NA | 21-May-''21 | 24-May-''21
Actual
11 | Preparation, Printing and Production of 2021 budget | MOE &WR/OES/G/DC/011/21 |  |  | 1100000 | <50M | NS | PRE | Post | Plan | 09-Feb-''21 | NA | 10-Feb-''21 | 12-Feb-''21 | 15-Feb-''21 | NA | 22-Feb-''21 | 24-Feb-''21 | 1100000 | 25-Feb-''21 | 26-Feb-''21 | NA | 05-Mar-''21 | 08-Mar-''21
Actual
12 | Procurement of Environmental Educational Materials | MOE &WR/OES/G/NS/012/21 |  | various | 1500000 | <50M | NS | PRE | Post | Plan | 14-Jun-''21 | NA | 16-Jun-''21 | 18-Jun-''21 | 22-Jun-''21 | NA | 29-Jun-''21 | 01-Jul-''21 | 1500000 | 02-Jul-''21 | 06-Jul-''21 | NA | 27-Jul-''21 | 28-Jul-''21
Actual
13 | Procurement of Cleaning items | MOE &WR/OES/G-F/NS/013/21 |  | various | 2000000 | <50M | NS | PRE | Post | Plan | 14-Jun-''21 | NA | 16-Jun-''21 | 18-Jun-''21 | 22-Jun-''21 | NA | 29-Jun-''21 | 01-Jul-''21 | 2000000 | 02-Jul-''21 | 06-Jul-''21 | NA | 27-Jul-''21 | 28-Jul-''21
Actual
14 | Procurement of 49,291.56 litres of petrol | MOE &WR/OES/G-F/NS/014/21 |  |  | 7922000 | <50M | NS | PRE | Post | Plan | 2021-02-22 | NA | 2021-02-24 | 2021-02-26 | 2021-03-03 | NA | 2021-03-10 | NA | 7922000 | 11-Mar-''21 | 2020-03-13 | 15-Mar-''21 | 30-Mar-''21
Actual
15 | Procurement of Operational Vehicle for the Ministry | MOE&WR/OES/G/NCB/015/21 |  |  | 123030475 | <500M | NCB | PRE | Post | Plan | 09-Mar-''21 | 11-Mar-''21 | 12-Mar-''21 | 17-Mar-''21 | 19-Mar-''21 | NA | 26-Mar-''21 | 29-Mar-''21 | 123030475 | 30-Mar-''21 | 02-Apr-''21 | 06-Apr-"21 | 20-Apr-''21 | 23-Apr-''21
Actual
15a | Procurement of 1 No of foreign fairly used 15 tons truck for ESCU Intervention Operation | MOE&WR/OES/G/NCB/016-01/21 | 1 | 12 | [5 empty] | Plan
Actual
15b | Procurement of 1 No of 18 seater bus for Environmental Monitoring | MOE&WR/OES/G/NCB/017-02/21 | 2 | 6 | [5 empty] | Plan
Actual
15c | Procurement of 6 Nos of Pick-Up - 2.0 Litres Engine 4WD | MOE&WR/OES/G/NCB/018-03/21 | 3 | 6 | [5 empty] | Plan
Actual
16 | Procurement of 8 Nos of Motor Bikes for anti open defacation | MOE&WR/OES/G/NS/019/21 |  | 7 | 3000000 | <50M | NS | PRE | Post | Plan | 14-Jun-''21 | NA | 16-Jun-''21 | 18-Jun-''21 | 22-Jun-''21 | NA | 29-Jun-''21 | 01-Jul-''21 | 3000000 | 02-Jul-''21 | 06-Jul-''21 | NA | 27-Jul-''21 | 28-Jul-''21
Actual
17 | Procurement, Istallation and Maintenance of 7 Nos of Mobile toilet at srategic locations in the State and Public Schools | MOE &WR/OES/G/NS/020/21 |  | 7 | 16050627 | <50M | NS | PRE | Post | Plan | 09-Mar-''21 | 11-Mar-''21 | 12-Mar-''21 | 17-Mar-''21 | 19-Mar-''21 | NA | 26-Mar-''21 | 29-Mar-''21 | 16050627 | 30-Mar-''21 | 02-Apr-''21 | 06-Apr-"21 | 20-Apr-''21 | 23-Apr-''21
Actual
18 | Procurement of Equipment and Kits to support EIA Process in the State | MOE &WR/OES/G/NS/021/20 |  | various | 5000000 | <50M | NS | PRE | Post | Plan | 14-Jun-''21 | NA | 16-Jun-''21 | 18-Jun-''21 | 22-Jun-''21 | NA | 29-Jun-''21 | 01-Jul-''21 | 5000000 | 02-Jul-''21 | 06-Jul-''21 | NA | 27-Jul-''21 | 28-Jul-''21
Actual
19 | Procurement of Fibre Cable (Multi-Mode), Fibre Patch band for the Ministry network access point | MOE &WR/OES/G/NS/022/20 |  | Various | 2500000 | <50M | NS | PRE | Post | Plan | 17-Mar-''21 | NA | 18-Mar-''21 | 22-Mar-''21 | 24-Mar-''21 | NA | 31-Mar-''21 | 02-Apr-''21 | 2500000 | 05-Apr-''21 | 08-Apr-''21 | NA | 15-Apr-''21 | 16-Apr-''21
Actual
20 | Procurement of Enforcement tools/Equipment | MOE &WR/OES/G/NS/023/20 |  | various | 11776000 | <50M | NS | PRE | Post | Plan | 09-Mar-''21 | 11-Mar-''21 | 12-Mar-''21 | 17-Mar-''21 | 19-Mar-''21 | NA | 26-Mar-''21 | 29-Mar-''21 | 11776000 | 30-Mar-''21 | 02-Apr-''21 | 06-Apr-"21 | 20-Apr-''21 | 23-Apr-''21
Actual
21 | Procurement of field Laboratory equipment for checking air, surface and groundwater quality for EIA study | MOE &WR/OES/G/NS/024/20 |  | 1 | 43379091 | <50M | NS | PRE | Post | Plan | 09-Mar-''21 | 11-Mar-''21 | 12-Mar-''21 | 17-Mar-''21 | 19-Mar-''21 | NA | 26-Mar-''21 | 29-Mar-''21 | 43379091 | 30-Mar-''21 | 02-Apr-''21 | 06-Apr-"21 | 20-Apr-''21 | 23-Apr-''21
Actual
22 | Procurement of Jack, Hammers, Chains, Saws etc for MEC operations | MOE &WR/OES/G/NS/025/20 |  | various | 12000000 | <50M | NS | PRE | Post | Plan | 09-Mar-''21 | 11-Mar-''21 | 12-Mar-''21 | 17-Mar-''21 | 19-Mar-''21 | NA | 26-Mar-''21 | 29-Mar-''21 | 12000000 | 30-Mar-''21 | 02-Apr-''21 | 06-Apr-"21 | 20-Apr-''21 | 23-Apr-''21
Actual
23 | Procurement of Office Furnitures | MOE &WR/OES/G/NS/026/20 |  | various | 715000 | <50M | NS | PRE | Post | Plan | 13-Apr-''21 | NA | 15-Apr-''21 | 20-Apr-''21 | 22-Apr-''21 | NA | 29-Apr-''21 | 03-May-''21 | 715000 | 04-May-''21 | 07-May-''21 | NA | 21-May-''21 | 24-May-''21
Actual
24 | Procurement of office Equipment | MOE &WR/OES/G/NS/027/20 |  | various | 2700000 | <50M | NS | PRE | Post | Plan | 13-Apr-''21 | NA | 15-Apr-''21 | 20-Apr-''21 | 22-Apr-''21 | NA | 29-Apr-''21 | 03-May-''21 | 2700000 | 04-May-''21 | 07-May-''21 | NA | 21-May-''21 | 24-May-''21
Actual
25 | Procurement of 48,874.36 litres of Diesel for 375KVA and 27 KVA Generator Plant | MOE &WR/OES/G-F/NS/028/20 |  |  | 11032000 | <50M | NS | PRE | Post | Plan | 2021-02-22 | NA | 2021-02-24 | 2021-02-26 | 2021-03-03 | NA | 2021-03-10 | NA | 11032000 | 11-Mar-''21 | 2020-03-13 | 15-Mar-''21 | 30-Mar-''21
Actual
26 | Procurement of 12 Nos of deratisation equipment for the State deratisation Project | MOE &WR/OES/G/NS/029/20 |  | 12 | 1140000 | <50M | NS | PRE | Post | Plan | 2021-02-22 | NA | 2021-02-24 | 2021-02-26 | 2021-03-03 | NA | 2021-03-10 | NA | 1140000 | 11-Mar-''21 | 2020-03-13 | 15-Mar-''21 | 30-Mar-''21
Actual
27 | Procurement of 4 Nos of Fumigation Machines | MOE &WR/OES/G/NS/030/20 |  | 4 | 3200000 | <50M | NS | PRE | Post | Plan | 2021-02-22 | NA | 2021-02-24 | 2021-02-26 | 2021-03-03 | NA | 2021-03-10 | NA | 3200000 | 11-Mar-''21 | 2020-03-13 | 15-Mar-''21 | 30-Mar-''21
Actual
28 | Procurement of 40 copies Professional textbook books and 50 copies of International Journals on Environmental Related Matters | MOE &WR/OES/G/NS/031/20 |  | 90 | 800.000.00 | <50M | NS | PRE | Post | Plan | 2021-02-22 | NA | 2021-02-24 | 2021-02-26 | 2021-03-03 | NA | 2021-03-10 | NA | 800000 | 11-Mar-''21 | 2020-03-13 | 15-Mar-''21 | 30-Mar-''21
Actual
29 | Procurement of Chemicals for disinfection of Government Establishments, Public Spaces, Bus Shelters and Public Schools | MOE &WR/OES/G/NS/032/20 |  |  | 61584750 | `<100M | NS | PRE | Post | Plan | 09-Mar-''21 | 11-Mar-''21 | 12-Mar-''21 | 17-Mar-''21 | 19-Mar-''21 | NA | 26-Mar-''21 | 29-Mar-''21 | 61584750 | 30-Mar-''21 | 02-Apr-''21 | 06-Apr-"21 | 20-Apr-''21 | 23-Apr-''21
Actual
| TOTAL |  |  |  | 359768536 |  |  |  |  | Plan | [8 empty] | 359768536
Actual

## works
PROCUREMENT PLAN FOR WORKS
MINISTRY: Office of Environmental Services, Ministry of the Environment and Water Resources
BUDGET YEAR: 2021
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
|  | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[9 empty] | Plan |  | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
Actual
1 | Construction and erection of 75 sensitization signage at 57 LGs and LCDAs strategic locations across the State against open defacation and urination | MOE&WR/OES/W/NS/ 001/21 |  | 7969525 | <50M | NS | LS | PRE | Plan | Post | 16-Feb-''21 | 2021-02-18 | 2021-02-19 | 2021-02-16 | 23-Feb-''21 | NA | 02-Mar-''21 | 04-Mar-''21 | 7969525 | 2021-03-05 | 2021-03-10 | 2021-03-15 | 2021-04-19 | 21-Apr ''21
Actual
2 | Construction of Public Toilets at Strategic Locations within the State | MOE&WR/OES/W/NCB/002/21 |  | 151278908 | <500M | NCB | BOQ | PRE | Plan | Pre | 16-Feb-''21 | 2021-02-18 | 2021-02-19 | 2021-02-16 | 23-Feb-''21 | NA | 02-Mar-''21 | 04-Mar-''21 | 151278908 | 2021-03-05 | 2021-03-10 | 2021-03-15 | 2021-07-13 | 14-Sep ''21
Actual
| Construction of Public Toilet at Obalende Motor Park | MOE&WR/OES/W/NCB/002-01/21 | 1
| Construction of Public Toilet at Orile Iganmu | MOE&WR/OES/W/NCB/002-02/21 | 2
| Construction of Public Toilet at Agege Rail Line | MOE&WR/OES/W/NS/002-03/21 | 3
| Construction of Public Toilet at Admaralty Round about, Lekki | MOE&WR/OES/W/NCB/002-04/21 | 4
| Contruction of Public Toilet at Apeleyin Motor Park, Bariga | MOE&WR/OES/W/NCB/002-05/21 | 5
3 | Rehabilitation of 5 Nos of Public toilets at Adeniyi Adele Public toilet, Mile 2 Motor Park, BRT Loading Bay, Alapere and Plank Market, Isolo | MOE&WR/OES/W/NCB/ 003/21 |  | 62000000 | <100M | NCB | BOQ | PRE | Plan | Pre | 16-Feb-''21 | 2021-02-18 | 2021-02-19 | 2021-02-16 | 23-Feb-''21 | NA | 02-Mar-''21 | 04-Mar-''21 | 62000000 | 2021-03-05 | 2021-03-10 | 2021-03-15 | 2021-06-14 | 16-Aug ''21
Actual
| Rehabilitation of Public Toilet at Adeniji Adele Public Toilet | MOE&WR/OES/W/NCB/003-01/21 | 1 | [5 empty] | Plan
Actual
| Rehabilitation of Public Toilet at Mile 2 Motor Park | MOE&WR/OES/W/NCB/003-02/21 | 2 | [5 empty] | Plan
Actual
| Rehabilitation of Public Toilet at BRT Loading Bay, Alapere | MOE&WR/OES/W/NCB/003-03/21 | 3 | [5 empty] | Plan
Actual
| Rehabilitation of Public Toilet at Plank Market, Isolo | MOE&WR/OES/W/NCB/003-04/21 | 4 | [5 empty] | Plan
Actual
4 | Construction of Recycling Bank in Alausa Secretariat Complex and Old Secretariat | MOE&WR/OES/W/NS/ 004/21 |  | 16096092 | <50M | NS | BOQ | PRE | Plan | Post | 16-Feb-''21 | 2021-02-18 | 2021-02-19 | 2021-02-16 | 23-Feb-''21 | NA | 02-Mar-''21 | 04-Mar-''21 | 16096092 | 2021-03-05 | 2021-03-10 | 2021-03-15 | 2021-06-14 | 16-Aug ''21
Actual
5 | Renovation and Facelifting of office building/administration block | MOE&WR/OES/W/NS/ 005/21 |  | 19206625 | <50M | NS | BOQ | PRE | Plan | Post | 16-Feb-''21 | 2021-02-18 | 2021-02-19 | 2021-02-16 | 23-Feb-''21 | NA | 02-Mar-''21 | 04-Mar-''21 | 19206625 | 2021-03-05 | 2021-03-10 | 2021-03-15 | 2021-06-14 | 16-Aug ''21
Actual
256551150
| TOTAL |  |  | 256551150 |  |  |  |  | Plan
Actual

## Sheet2
YEAR 2021 PROCUREMENT PLAN
PROCUREMENT PLANNING COMMITTEE
S/N | NAMES | DESIGNATION | SIGNATURE
I | Mrs. Odeneye Belinda Aderonke | Permanent Secretary
II | Mr. Bakrin Hakeem A. | D - Planning
III | Mrs. Obadan O.O | D- Legal
IV | Mr. Savage O.S | D - C & E Department
V | Dr. Hassan Sanuth A. | DD - SSD
VI | Mr. Aremu | DD- A & HR
VII | Mrs. Banire M.A | DD - EEU
VIII | Mr. Sojinu O.S | AD - EAD
IX | Mr. Bankole M.O | AD - CC&EP Department
X | Mr. Fasasi A.E | AD - MEC. Department
XI | Mr. Adeshina A.A | AD - PAR
XII | Mrs. Oyafunke O.A | AD - ICT
XIII | Mrs. Bakre F.T | Rep - F & A
XIV | Mrs. Abayomi O.O | HOU - Audit

## Sheet1
SUMMARY SHEET