## non-proc items
PROCUREMENT PLAN FOR PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY:LAGOS STATE COOPERATIVE COLLEGE
BUDGET YEAR: PROCUREMENT PLAN 2021
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TOTAL
1 | Transportation and travel allowances | LSCC/NP/NM/001/21 | 4000000 | Plan | 333333.34 | 333333.33 | 333333.33 | 333333.33 | 333333.33 | 333333.33 | 333333.33 | 333333.33 | 333333.33 | 333333.33 | 333333.33 | 333333.33 | 4000000
Actual
2 | Council member sitting allowance (Chairman N150,000 per sitting and the remaining 10 members N100,000 each per setting) | LSCC/NP/NM/002/21 | 5750000 | Plan |  | 1150000 |  | 1150000 |  | 1150000 |  | 1150000 |  | 1150000 |  |  | 5750000
Actual
3 | Extra Ordinary Board meeting | LSCC/NP/NM/003/21 | 2250000 | Plan |  | 450000 |  | 450000 |  | 450000 |  | 450000 |  | 450000 |  |  | 2250000
Actual
4 | Servicing of Council meeting | LSCC/NP/NM/004/21 | 2000000 | Plan |  | 400000 |  | 400000 |  | 400000 |  | 400000 |  | 400000 |  |  | 2000000
Actual
5 | Salary for lecturers, academic staff and other staff employ by the college | LSCC/NP/NM/005/20 | 30000000 | Plan | 7500000 |  |  | 7500000 |  |  | 7500000 |  |  | 7500000 |  |  | 30000000
Actual
6 | Expenses incurred by the Provost on special assignments by Mr Governor | LSCC/NP/NM/006/20 | 600000 | Plan | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 600000
Actual
7 | Expenses incurred by the Registrar on special assignments by Mr Governor | LSCC/NP/NM/007/21 | 600000 | Plan | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 600000
Actual
8 | Expenses incurred as a result of special duties assignment by the College | LSCC/NP/NM/008/21 | 3000000 | Plan | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 3000000
Actual
|  |  | 48200000 | Plan | 8183333.34 | 2683333.33 | 2683333.33 | 10183333.33 | 683333.33 | 2683333.33 | 8183333.33 | 2683333.33 | 683333.33 | 10183333.33 | 683333.33 | 683333.33 | 48200000
Actual

## trg conf wsh
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY:LAGOS STATE COOPERATIVE COLLEGE
BUDGET YEAR: PROCUREMENT PLAN 2021
S/N | Description of Training/Workshop/ Conference | Package Number | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | Retreat, Seminar & Workshop for Council member | LSCC/S-WTC/SS/001/21 |  |  |  | Plan |  |  |  |  | 8697350.36
Actual
2 | Conferences & Seminar | LSCC/S-WTC/SS/003/21 |  |  |  | Plan |  |  |  |  | 5999999.98
Actual
3 | Workshop &Training Expenses | LSCC/S-WTC/SS/002/21 |  |  |  | Plan |  |  |  |  | 1500000
Actual
[6 empty] | Plan |  |  |  |  | 16197350.34
Actual

## non-cons
PROCUREMENT PLAN FOR NON-CONSULTING SERVICES
MINISTRY/ AGENCY:LAGOS STATE COOPERATIVE COLLEGE
BUDGET YEAR: PROCUREMENT PLAN 2021
Contract Description | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
| Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
Accreditation | LSCC/S-NC/NS/001/21 | 01 | – | 25000000 | ≥50M | QCBS | Plan | Post | Prior | 01-'07-20 | 13-'07-20 | 22-'07-20 | 19-'08-20 | 31-'08-20 | 07-'09-20 | 16-'09-20 | Plan | 05'10-20 |  |  | 09'11-20 | 30-'11-20 | 11-'01-21
[7 empty] | Actual | [9 empty] | Actual
Routine maintenance of School building, takes care of expences incurred on special assignments and activities of the College | LSCC/S-NC/NS/002/21 | 01 | – | 2100000 | ≥50M | QCBS | Plan | Post | Post | 01-'07-20 | 13-'07-20 | 22-'07-20 | 19-'08-20 | 31-'08-20 | 07-'09-20 | 16-'09-20 | Plan | 05'10-20 |  |  | 09'11-20 | 30-'11-20 | 11-'01-21
[7 empty] | Actual | [9 empty] | Actual
Media appearance, Tv, Radio jingles, Newspaper adverts and production of flyers | LSCC/S-NC/NS/003/21 | 01 | – | 6999996 | ≥50M | QCBS | Plan | Post | Post | 16-'12-20 | 28-'12-20 | 06-'01-21 | 03-'02-21 | 15-'02-21 | 22-'02-21 | 03-'03-21 | Plan | 22-'03-20 |  |  | 26-'04-21 | 17-'05-21 | 28-'06-21
[7 empty] | Actual | [9 empty] | Actual
Maintenance of Office Building | LSCC/S-NC/NS/004/21 | 01 | – | 3000000 | ≥50M | QCBS | Plan | Post | Post | 16-'12-20 | 28-'12-20 | 06-'01-21 | 03-'02-21 | 15-'02-21 | 22-'02-21 | 03-'03-21 | Plan | 22-'03-20 |  |  | 26-'04-21 | 17-'05-21 | 28-'06-21
[7 empty] | Actual | [9 empty] | Actual
Motor Vehicle Repairs & Maint. | LSCC/S-NC/NS/005/21 | 01 | – | 5000000 | ≥50M | QCBS | Plan | Post | Post | 16-'12-20 | 28-'12-20 | 06-'01-21 | 03-'02-21 | 15-'02-21 | 22-'02-21 | 03-'03-21 | Plan | 22-'03-20 |  |  | 26-'04-21 | 17-'05-21 | 28-'06-21
[7 empty] | Actual | [9 empty] | Actual
Motor Vehicle Fuel Consumption | LSCC/S-NC/NS/006/21 | 01 | – | 5000000 | ≥50M | QCBS | Plan | Post | Post | 16-'12-20 | 28-'12-20 | 06-'01-21 | 03-'02-21 | 15-'02-21 | 22-'02-21 | 03-'03-21 | Plan | 22-'03-20 |  |  | 26-'04-21 | 17-'05-21 | 28-'06-21
[7 empty] | Actual | [9 empty] | Actual
General Utility Services | LSCC/S-NC/NS/007/21 | 01 | – | 5499999.96 | ≥50M | QCBS | Plan | Post | Post | 16-'12-20 | 28-'12-20 | 06-'01-21 | 03-'02-21 | 15-'02-21 | 22-'02-21 | 03-'03-21 | Plan | 22-'03-20 |  |  | 26-'04-21 | 17-'05-21 | 28-'06-21
[7 empty] | Actual | [9 empty] | Actual
Stationery | LSCC/S-NC/NS/008/21 | 01 | – | 3000000 | ≥50M | QCBS | Plan | Post | Post | 16-'12-20 | 28-'12-20 | 06-'01-21 | 03-'02-21 | 15-'02-21 | 22-'02-21 | 03-'03-21 | Plan | 22-'03-20 |  |  | 26-'04-21 | 17-'05-21 | 28-'06-21
[7 empty] | Actual | [9 empty] | Actual
Miscellaneous | LSCC/S-NC/NS/009/21 | 01 | – | 4500000 | ≥50M | QCBS | Plan | Post | Post | 16-'12-20 | 28-'12-20 | 06-'01-21 | 03-'02-21 | 15-'02-21 | 22-'02-21 | 03-'03-21 | Plan | 22-'03-20 |  |  | 26-'04-21 | 17-'05-21 | 28-'06-21
[7 empty] | Actual | [9 empty] | Actual
Printing of booklet/folders for short term courses | LSCC/S-NC/NS/010/21 | 01 | – | 2500000 | ≥50M | QCBS | Plan | Post | Post | 09-'09-20 | 28-'09-20 | 07-'10-20 | 04-'11-20 | 16-'11-20 | 23-'11-20 | 03-'12-20 | Plan | 21-'12-20 |  |  | 25-'01-21 | 15-'02-21 | 29-'03-21
[7 empty] | Actual | [9 empty] | Actual
Library Services | LSCC/S-NC/NS/011/21 | 01 | – | 1700000 | ≥50M | QCBS | Plan | Post | Post | 01-'07-20 | 13-'07-20 | 22-'07-20 | 19-'08-20 | 31-'08-20 | 07-'09-20 | 16-'09-20 | Plan | 05'10-20 |  |  | 09'11-20 | 30-'11-20 | 11-'01-21
[7 empty] | Actual | [9 empty] | Actual
Management Information System | LSCC/S-NC/NS/012/21 | 01 | – | 1600000 | ≥50M | QCBS | Plan | Post | Post | 09-'09-20 | 28-'09-20 | 07-'10-20 | 04-'11-20 | 16-'11-20 | 23-'11-20 | 03-'12-20 | Plan | 21-'12-20 |  |  | 25-'01-21 | 15-'02-21 | 29-'03-21
[7 empty] | Actual | [9 empty] | Actual
Generating Set Repairs | LSCC/S-NC/NS/013/21 | 01 | – | 1000000 | ≥50M | QCBS | Plan | Post | Post | 16-'12-20 | 28-'12-20 | 06-'01-21 | 03-'02-21 | 15-'02-21 | 22-'02-21 | 03-'03-21 | Plan | 22-'03-20 |  |  | 26-'04-21 | 17-'05-21 | 28-'06-21
[7 empty] | Actual | [9 empty] | Actual
|  |  | – | 66899995.96 |  |  | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual

## consultancy
PROCUREMENT PLAN FOR CONSULTANCY SERVICES
MINISTRY/ AGENCY:LAGOS STATE COOPERATIVE COLLEGE
BUDGET YEAR: PROCUREMENT PLAN 2021
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[7 empty] | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
1 | Research and Development | LSCC/S-C/CQS/001/21 | CQS | Lump sum | 7000000 | Post | Plan | 16-'11-20 | 25-'11-20 | 02-'12-20 | 23-'12-20 | 04-'01-21 | 13-'01-21 | 17-'02-21 | 01-'03-21 | 10-'03-21 | 17-'03-21 | 29-'03-21 | 07-'04-21 | 26-'04-21 | 29-'04-21 |  | 03-'05-21 | 17-'05-21 | 07-'06-21 | 16-'06-21 | 28-'06-21
Actual
2 | Creation of E-learning Platform: To facilitate distant learning, manage students and instructors, electronic library of publications, research projects and study materials. | LSCC/S-C/CQS/002/21 | CQS | Lump sum | 5000000 | Post | Plan | 09-'12-20 | 21-'12-20 | 28-'12-20 | 18-'01-21 | 27-'01-21 | 08-'02-21 | 10-'03-21 | 22-'03-21 | 31-'03-21 | 07-'04-21 | 19-'04-21 | 28-'04-21 | 17-'05-21 | 21-'05-21 |  | 24-'05-21 | 14-'06-21 | 05-'07-21 | 14-'07-21 | 26-'07-21
Actual
3 | Dedicated Internet Installation | LSCC/S-C/CQS/003/21 | CQS | Lump sum | 5000000 | Post | Plan | 16-'11-20 | 25-'11-20 | 02-'12-20 | 23-'12-20 | 04-'01-21 | 13-'01-21 | 17-'02-21 | 01-'03-21 | 10-'03-21 | 17-'03-21 | 29-'03-21 | 07-'04-21 | 26-'04-21 | 29-'04-21 |  | 03-'05-21 | 17-'05-21 | 07-'06-21 | 16-'06-21 | 28-'06-21
Actual
4 | Updating of E-Library / LMS: To create customized e-Learning and Library Management (eBook catalogue & Info) | LSCC/S-C/CQS/004/21 | CQS | Lump sum | 2500000 | Post | Plan | 09-'12-20 | 21-'12-20 | 28-'12-20 | 18-'01-21 | 27-'01-21 | 08-'02-21 | 10-'03-21 | 22-'03-21 | 31-'03-21 | 07-'04-21 | 19-'04-21 | 28-'04-21 | 17-'05-21 | 21-'05-21 |  | 24-'05-21 | 14-'06-21 | 05-'07-21 | 14-'07-21 | 26-'07-21
Actual
5 | Audit Expenses: Engagement of External Auditor | LSCC/S-C/CQS/005/21 | CQS | Lump sum | 1500000 | Post | Plan | 16-'11-20 | 25-'11-20 | 02-'12-20 | 23-'12-20 | 04-'01-21 | 13-'01-21 | 17-'02-21 | 01-'03-21 | 10-'03-21 | 17-'03-21 | 29-'03-21 | 07-'04-21 | 26-'04-21 | 29-'04-21 |  | 03-'05-21 | 17-'05-21 | 07-'06-21 | 16-'06-21 | 28-'06-21
Actual
[5 empty] | 21000000 |  | Plan
Actual

## goods
PROCUREMENT PLAN FOR GOODS
MINISTRY/ AGENCY: LAGOS STATE COOPERATIVE COLLEGE
BUDGET YEAR: PROCUREMENT PLAN 2021
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Purchase of 2nos. Hiace Panel van @ 19617255.32 | LSCC/G/NS/001/21 | 01 | – | 39234510.64 | ≥50M | NS | Pre | Prior | Plan | 14-12-2020 | 23-12-2020 | 04-01-2021 | 01-02-2021 | 10-02-2021 | 22-02-2021 | 15-03-2021 | 17-03-2021 |  | 24-03-2021 | 05-04-2021 | 26-04-2021
Actual
2 | Purchase of Rio 1.4L EX Saloon Auto Transmission | LSCC/G/NS/002/21 | 01 | – | 11500000 | ≥50M | NS | Post | Prior | Plan | 14-12-2020 | 23-12-2020 | 04-01-2021 | 01-02-2021 | 10-02-2021 | 22-02-2021 | 15-03-2021 | 17-03-2021 |  | 24-03-2021 | 05-04-2021 | 26-04-2021
Actual
3 | Purchase of nos. 20 Panasonic Airconditioner @ N250000 | LSCC/G/NS/003/21 | 01 | – | 5000000 | ≥50M | NS | Post | Post | Plan | 22-02-2021 | 03-03-2021 | 15-03-2021 | 12-04-2021 | 21-04-2021 | 03-05-2021 | 24-05-2021 | 26-05-2021 |  | 02-06-2021 | 14-06-2021 | 05-07-2021
Actual
4 | PurchasGenerating Set (fuel consumption) | LSCC/G/NS/004/21 | 01 | – | 5000000 | ≥50M | NS | Post | Post | Plan | 22-02-2021 | 03-03-2021 | 15-03-2021 | 12-04-2021 | 21-04-2021 | 03-05-2021 | 24-05-2021 | 26-05-2021 |  | 02-06-2021 | 14-06-2021 | 05-07-2021
Actual
5 | Purchase of books to College physical Library | LSCC/G/NS/005/21 | 01 | – | 2500000 | ≥50M | NS | Post | Post | Plan | 22-02-2021 | 03-03-2021 | 15-03-2021 | 12-04-2021 | 21-04-2021 | 03-05-2021 | 24-05-2021 | 26-05-2021 |  | 02-06-2021 | 14-06-2021 | 05-07-2021
Actual
6 | 60 Single Seater lecture chair with writing platform @N35,000 per one, | LSCC/G/NS/006/21 | 01 | – | 2100000 | ≥50M | NS | Post | Post | Plan | 15-02-2021 | 24-02-2021 | 08-03-2021 | 05-04-2021 | 14-04-2021 | 26-04-2021 | 17-05-2021 | 19-05-2021 |  | 26-05-2021 | 07-06-2021 | 28-06-2021
Actual
7 | Planning Unit Expenses | LSCC/G/NS/007/21 | 01 | – | 1800000 | ≥50M | NS | Post | Post | Plan | 18-11-2020 | 30-11-2020 | 09-12-2020 | 06-01-2021 | 18-01-2021 | 27-01-2021 | 15-02-2021 | 17-02-2021 |  | 24-02-2021 | 03-03-2021 | 29-03-2021
Actual
8 | Purchase of40 Standing fans @N40,000 per one | LSCC/G/NS/008/21 | 01 | – | 1600000 | ≥50M | NCB | Post | Post | Plan | 22-02-2021 | 03-03-2021 | 15-03-2021 | 12-04-2021 | 21-04-2021 | 03-05-2021 | 24-05-2021 | 26-05-2021 |  | 02-06-2021 | 14-06-2021 | 05-07-2021
Actual
9 | Procurement Unit | LSCC/G/NS/009/21 | 01 | – | 1300000 | ≥50M | NCB | Post | Post | Plan | 18-11-2020 | 30-11-2020 | 09-12-2020 | 06-01-2021 | 18-01-2021 | 27-01-2021 | 15-02-2021 | 17-02-2021 |  | 24-02-2021 | 03-03-2021 | 29-03-2021
Actual
10 | Purchase of 16 Office Chairs @N80,000 per one | LSCC/G/NS/010/21 | 01 | – | 1280000 | ≥50M | NS | Post | Post | Plan | 22-02-2021 | 03-03-2021 | 15-03-2021 | 12-04-2021 | 21-04-2021 | 03-05-2021 | 24-05-2021 | 26-05-2021 |  | 02-06-2021 | 14-06-2021 | 05-07-2021
Actual
11 | ICT Unit Expenses | LSCC/G/NS/011/21 | 01 | – | 1000000 | ≥50M | NS | Post | Post | Plan | 18-11-2020 | 30-11-2020 | 09-12-2020 | 06-01-2021 | 18-01-2021 | 27-01-2021 | 15-02-2021 | 17-02-2021 |  | 24-02-2021 | 03-03-2021 | 29-03-2021
Actual
12 | Audit Expenses | LSCC/G/NS/012/21 | 01 | – | 1000000 | ≥50M | NS | Post | Post | Plan | 18-11-2020 | 30-11-2020 | 09-12-2020 | 06-01-2021 | 18-01-2021 | 27-01-2021 | 15-02-2021 | 17-02-2021 |  | 24-02-2021 | 03-03-2021 | 29-03-2021
Actual
13 | Public Affair Unit | LSCC/G/NS/013/21 | 01 | – | 1000000 | ≥50M | NCB | Post | Post | Plan | 18-11-2020 | 30-11-2020 | 09-12-2020 | 06-01-2021 | 18-01-2021 | 27-01-2021 | 15-02-2021 | 17-02-2021 |  | 24-02-2021 | 03-03-2021 | 29-03-2021
Actual
14 | Purchase of8 Office Tables @N120,000 per one | LSCC/G/NS/014/21 | 01 | – | 960000 | ≥50M | NCB | Post | Post | Plan | 14-12-2020 | 23-12-2020 | 04-01-2021 | 01-02-2021 | 10-02-2021 | 22-02-2021 | 15-03-2021 | 17-03-2021 |  | 24-03-2021 | 05-04-2021 | 26-04-2021
Actual
15 | Purchase of 10 Office Shelves @N95,000 per one | LSCC/G/NS/015/21 | 01 | – | 950000 | ≥50M | NS | Post | Post | Plan | 22-02-2021 | 03-03-2021 | 15-03-2021 | 12-04-2021 | 21-04-2021 | 03-05-2021 | 24-05-2021 | 26-05-2021 |  | 02-06-2021 | 14-06-2021 | 05-07-2021
Actual
16 | Purchase of 10 CWAY Water Dispenser @N80,000 per one | LSCC/G/NS/016/21 | 01 | – | 800000 | ≥50M |  |  |  | Plan | 15-02-2021 | 24-02-2021 | 08-03-2021 | 05-04-2021 | 14-04-2021 | 26-04-2021 | 17-05-2021 | 19-05-2021 |  | 26-05-2021 | 07-06-2021 | 28-06-2021
Actual
17 | Purchase of Uniform and Protective outfit | LSCC/G/NS/017/21 | 01 | – | 600000 | ≥50M | NS | Post | Post | Plan | 14-12-2020 | 23-12-2020 | 04-01-2021 | 01-02-2021 | 10-02-2021 | 22-02-2021 | 15-03-2021 | 17-03-2021 |  | 24-03-2021 | 05-04-2021 | 26-04-2021
Actual
18 | Purchase of Six 32 inch LED TV @N90,000 | LSCC/G/NS/018/21 | 01 | – | 540000 | ≥50M | NCB | Post | Post | Plan | 22-02-2021 | 03-03-2021 | 15-03-2021 | 12-04-2021 | 21-04-2021 | 03-05-2021 | 24-05-2021 | 26-05-2021 |  | 02-06-2021 | 14-06-2021 | 05-07-2021
Actual
19 | Intercom connectivity for 18 rooms @ N500,000 | LSCC/G/NS/019/21 | 01 | – | 500000 | ≥50M |  |  |  | Plan | 15-02-2021 | 24-02-2021 | 08-03-2021 | 05-04-2021 | 14-04-2021 | 26-04-2021 | 17-05-2021 | 19-05-2021 |  | 26-05-2021 | 07-06-2021 | 28-06-2021
Actual
20 | Legal Unit Expenses | LSCC/G/NS/020/21 | 01 | – | 500000 | ≥50M | NS | Post | Post | Plan | 18-11-2020 | 30-11-2020 | 09-12-2020 | 06-01-2021 | 18-01-2021 | 27-01-2021 | 15-02-2021 | 17-02-2021 |  | 24-02-2021 | 03-03-2021 | 29-03-2021
Actual
21 | Purchase of 1 Scanfrost Semi Professional Burgundy @N455,000 | LSCC/G/NS/021/21 | 01 | – | 455000 | ≥50M |  |  |  | Plan | 14-12-2020 | 23-12-2020 | 04-01-2021 | 01-02-2021 | 10-02-2021 | 22-02-2021 | 15-03-2021 | 17-03-2021 |  | 24-03-2021 | 05-04-2021 | 26-04-2021
Actual
22 | Purchase of 40 Plastic Chairs @N10,000 per one for the College Canteen | LSCC/G/NS/022/21 | 01 | – | 400000 | ≥50M | NCB | Post | Post | Plan | 22-02-2021 | 03-03-2021 | 15-03-2021 | 12-04-2021 | 21-04-2021 | 03-05-2021 | 24-05-2021 | 26-05-2021 |  | 02-06-2021 | 14-06-2021 | 05-07-2021
Actual
23 | Purchase of 1 Big Deep Freezer @N400,000 | LSCC/G/NS/023/21 | 01 | – | 400000 | ≥50M |  |  |  | Plan | 15-02-2021 | 24-02-2021 | 08-03-2021 | 05-04-2021 | 14-04-2021 | 26-04-2021 | 17-05-2021 | 19-05-2021 |  | 26-05-2021 | 07-06-2021 | 28-06-2021
Actual
24 | 8 nos of magnetic board @N45,000 per one | LSCC/G/NS/024/21 | 01 | – | 360000 | ≥50M | NS | Post | Post | Plan | 18-11-2020 | 30-11-2020 | 09-12-2020 | 06-01-2021 | 18-01-2021 | 27-01-2021 | 15-02-2021 | 17-02-2021 |  | 24-02-2021 | 03-03-2021 | 29-03-2021
Actual
25 | Purchase of One 6.7KVA Generator @N350,000. | LSCC/G/NS/025/21 | 01 | – | 350000 | ≥50M | NS | Post | Post | Plan | 14-12-2020 | 23-12-2020 | 04-01-2021 | 01-02-2021 | 10-02-2021 | 22-02-2021 | 15-03-2021 | 17-03-2021 |  | 24-03-2021 | 05-04-2021 | 26-04-2021
Actual
26 | Purchase of 8 Bruhm 32inch freewall bracket @N40,000 | LSCC/G/NS/026/21 | 01 | – | 320000 | ≥50M | NS | Post | Post | Plan | 22-02-2021 | 03-03-2021 | 15-03-2021 | 12-04-2021 | 21-04-2021 | 03-05-2021 | 24-05-2021 | 26-05-2021 |  | 02-06-2021 | 14-06-2021 | 05-07-2021
Actual
27 | Purchase of Chiller @N300,000 | LSCC/G/NS/027/21 | 01 | – | 300000 | ≥50M |  |  |  | Plan | 15-02-2021 | 24-02-2021 | 08-03-2021 | 05-04-2021 | 14-04-2021 | 26-04-2021 | 17-05-2021 | 19-05-2021 |  | 26-05-2021 | 07-06-2021 | 28-06-2021
Actual
28 | Purchase of 10 Plastic Tables @N30,000 per on | LSCC/G/NS/028/21 | 01 | – | 300000 | ≥50M | NS | Post | Post | Plan | 18-11-2020 | 30-11-2020 | 09-12-2020 | 06-01-2021 | 18-01-2021 | 27-01-2021 | 15-02-2021 | 17-02-2021 |  | 24-02-2021 | 03-03-2021 | 29-03-2021
Actual
29 | Purchase of Kitchen Utensils @N250,000 both for College Canteen | LSCC/G/NS/029/21 | 01 | – | 250000 | ≥50M |  |  |  | Plan | 14-12-2020 | 23-12-2020 | 04-01-2021 | 01-02-2021 | 10-02-2021 | 22-02-2021 | 15-03-2021 | 17-03-2021 |  | 24-03-2021 | 05-04-2021 | 26-04-2021
Actual
30 | Purchase of 2 Hospital Bed @N120,000 per one | LSCC/G/NS/030/21 | 01 | – | 240000 | ≥50M | NS | Post | Post | Plan | 22-02-2021 | 03-03-2021 | 15-03-2021 | 12-04-2021 | 21-04-2021 | 03-05-2021 | 24-05-2021 | 26-05-2021 |  | 02-06-2021 | 14-06-2021 | 05-07-2021
Actual
31 | Purchase of 2 Refrigerators @N120,000 per one | LSCC/G/NS/031/21 | 01 | – | 240000 | ≥50M |  |  |  | Plan | 15-02-2021 | 24-02-2021 | 08-03-2021 | 05-04-2021 | 14-04-2021 | 26-04-2021 | 17-05-2021 | 19-05-2021 |  | 26-05-2021 | 07-06-2021 | 28-06-2021
Actual
32 | Purchase of One 40 inch LED TV @N200,000 | LSCC/G/NS/032/21 | 01 | – | 200000 | ≥50M | NS | Post | Post | Plan | 18-11-2020 | 30-11-2020 | 09-12-2020 | 06-01-2021 | 18-01-2021 | 27-01-2021 | 15-02-2021 | 17-02-2021 |  | 24-02-2021 | 03-03-2021 | 29-03-2021
Actual
33 | Purchase of 1 Metalic Ladder @ N120,000 | LSCC/G/NS/033/21 |  |  | 120000 | ≥50M |  |  |  | Plan | 14-12-2020 | 23-12-2020 | 04-01-2021 | 01-02-2021 | 10-02-2021 | 22-02-2021 | 15-03-2021 | 17-03-2021 |  | 24-03-2021 | 05-04-2021 | 26-04-2021
Actual
34 | Purchase of 6 Bed Cover @N20,000 per one. | LSCC/G/NS/034/21 | 01 | – | 120000 | ≥50M | NS | Post | Post | Plan | 22-02-2021 | 03-03-2021 | 15-03-2021 | 12-04-2021 | 21-04-2021 | 03-05-2021 | 24-05-2021 | 26-05-2021 |  | 02-06-2021 | 14-06-2021 | 05-07-2021
Actual
35 | 10pics of projector pointer @N10,000 per one | LSCC/G/NS/035/21 | 01 | – | 100000 | ≥50M | NS | Post | Post | Plan | 15-02-2021 | 24-02-2021 | 08-03-2021 | 05-04-2021 | 14-04-2021 | 26-04-2021 | 17-05-2021 | 19-05-2021 |  | 26-05-2021 | 07-06-2021 | 28-06-2021
Actual
36 | Purchase of 2 Vitafoam 3.5 by 6 matress @N50,000 per one | LSCC/G/NS/036/21 | 01 | – | 100000 | ≥50M | NS | Post | Post | Plan | 18-11-2020 | 30-11-2020 | 09-12-2020 | 06-01-2021 | 18-01-2021 | 27-01-2021 | 15-02-2021 | 17-02-2021 |  | 24-02-2021 | 03-03-2021 | 29-03-2021
Actual
37 | 2 DSTV installation @ N35,000 per one | LSCC/G/NS/037/21 | 01 | – | 70000 | ≥50M |  |  |  | Plan | 14-12-2020 | 23-12-2020 | 04-01-2021 | 01-02-2021 | 10-02-2021 | 22-02-2021 | 15-03-2021 | 17-03-2021 |  | 24-03-2021 | 05-04-2021 | 26-04-2021
Actual
38 | 50kg Gas Cylinder refill @N60,000 per one | LSCC/G/NS/038/21 | 01 | – | 60000 | ≥50M |  |  |  | Plan | 22-02-2021 | 03-03-2021 | 15-03-2021 | 12-04-2021 | 21-04-2021 | 03-05-2021 | 24-05-2021 | 26-05-2021 |  | 02-06-2021 | 14-06-2021 | 05-07-2021
Actual
39 | Purchase of 1 First AID Box @N50,000 | LSCC/G/NS/039/21 | 01 | – | 50000 | ≥50M | NS | Post | Post | Plan | 15-02-2021 | 24-02-2021 | 08-03-2021 | 05-04-2021 | 14-04-2021 | 26-04-2021 | 17-05-2021 | 19-05-2021 |  | 26-05-2021 | 07-06-2021 | 28-06-2021
Actual
[5 empty] | 83599510.64 |  |  |  |  | Plan
Actual

## works
PROCUREMENT PLAN FOR WORKS
MINISTRY/ AGENCY:LAGOS STATE COOPERATIVE COLLEGE
BUDGET YEAR: PROCUREMENT PLAN 2021
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Being 30% final payment for the renovation work in the college | MYSD/W/NS/001/21 | 01 | 16280989.65 | ≥50m | NS | Bill of Quantity | Post | Plan | Prior | ON GOING | [6 empty] | ON GOING
Actual
2 | Being 30% final payment for the renovation work at the extention building at the college | MYSD/W/NS/002/21 | 01 | 2984499.7 | ≥50m | NS | Bill of Quantity | Post | Plan |  | ON GOING | [6 empty] | ON GOING
Actual
3 | Partitioning for Registrar and 2 Deputy Provost Office | MYSD/W/NS/003/21 | 01 | 3395000 | ≥50m | NS | Bill of Quantity | Post | Plan | Post | 10-'03-21 | 22-'03-21 | 31-'03-21 | 28-'04-21 | 10-'05-21 | 19-'05-21 |  |  |  | 26-'05-21 | 07-'06-21 | 28-'06-21
Actual
4 | Partitioning of Office in the College Training Hall | MYSD/W/NS/004/21 | 01 | 3000000 | ≥50m | NS | Bill of Quantity | Post | Plan | Post | 10-'03-21 | 22-'03-21 | 31-'03-21 | 28-'04-21 | 10-'05-21 | 19-'05-21 |  |  |  | 26-'05-21 | 07-'06-21 | 28-'06-21
Actual
|  |  |  | 25660489.35 |  |  |  | Post | Plan
Actual