## Non-Proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: LAGOS STATE SPORTS TRUST FUND
BUDGET YEAR: 2022
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER
1 | TRAVEL AND TRANSPORT | LSSTF/NP/NM/001/21 | 300,000.00 | Plan | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000
Actual
2 | GENERAL UTILITY SERVICE | LSSTF/NP/NM/001/21 | 2,200,000.00 | Plan | 183333.33 | 183333.33 | 183333.33 | 183333.33 | 183333.33 | 183333.33 | 183333.33 | 183333.33 | 183333.33 | 183333.33 | 183333.33 | 183333.33
Actual
3 | MISCELLANEOUS | LSSTF/NP/NM/003/22 |  | Plan
Actual
4 | COMMITTEE ALLOWANCES | LSSTF/NP/NM/004/22 | 5,400,000.00 | Plan | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000
Actual
5 | SPECIAL DUTIES EXPENSES | LSSTF/NP/NM/005/22 | 8,912,011.00 | Plan | 742667.58 | 742667.58 | 742667.58 | 742667.58 | 742667.58 | 742667.58 | 742667.58 | 742667.58 | 742667.58 | 742667.58 | 742667.58 | 742667.58
Actual
6 | SPORTS MARKETING & SPONSORSHIP | LSSTF/NP/NM/006/22 | 10,000,000.00 | Plan | 833333.33 | 833333.33 | 833333.33 | 833333.33 | 833333.33 | 833333.33 | 833333.33 | 833333.33 | 833333.33 | 833333.33 | 833333.33 | 833333.33
Actual
7 | LEGAL UNIT EXPENSES FOR DRAWING AGREEMENT AND SIGNING OF MOUs | LSSTF/NP/NM/007/22 | 310,000.00 | Plan | 25833.33 | 25833.33 | 25833.33 | 25833.33 | 25833.33 | 25833.33 | 25833.33 | 25833.33 | 25833.33 | 25833.33 | 25833.33 | 25833.33
Actual
8 | BANKING EXPENSES | LSSTF/NP/NM/008/22 | 700,000.00 | Plan | 58333.33 | 58333.33 | 58333.33 | 58333.33 | 58333.33 | 58333.33 | 58333.33 | 58333.33 | 58333.33 | 58333.33 | 58333.33 | 58333.33
Actual

## trg conf wsh
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: LAGOS STATE SPORTS TRUST FUND
BUDGET YEAR: 2022
S/N | Description of Training/Workshop/ Conference | Package Number | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | TRAINING AND WORKSHOP FOR THE EXECUTIVE SECRETARY | LSSTF/S-WTC/SS/001/22 | Personnel Development / Capacity Building | 257 |  | Plan | Lagos | 30000000 | 20000000 | 58600000 | 108600000
Actual
2 | CONFERENCE AND SEMINARS FOR STAFF AND BOARD MEMBERS | LSSTF/S-WTC/SS/002/22 |  |  |  | Plan
Actual
3 | TRAINING OF STATE ATHLETES AND COACHES | LSSC/S-WTC/SS/003/22 |  |  |  | Plan
Actual

## non-cons
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY: LAGOS STATE SPORTS TRUST FUND
BUDGET YEAR: 2022
Contract Description | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
| Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
Branding Sports equipment | LSSTF/S-NC/NS/001/22 |  |  | 1000000 | <10,000,000.00 | NS | Plan | POST | POST | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 16th Mar.2021 | 23rd Mar,2021 | 30th Mar,2021 | Plan | 27th Aprl,2021 | 29th Aprl,2021 | NA | 27th May,2021 | 10th June,2021 | 24th June,2021 | 8th July,2021
[7 empty] | Actual | [9 empty] | Actual
Contingency (Logistics and security) | LSSTF/S-NC/NS/002/22 |  |  | 350000 | <10,000,000.00 | NS | Plan | POST | POST | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 16th Mar.2021 | 23rd Mar,2021 | 30th Mar,2021 | Plan | 27th Aprl,2021 | 29th Aprl,2021 | NA | 27th May,2021 | 10th June,2021 | 24th June,2021 | 8th July,2021
[7 empty] | Actual | [9 empty] | Actual
MAINTENANCE OF OFFICE BUIDING | LSSTF/S-NC/NS/003/22 |  |  | 350000 | <10,000,000.00 | NS | Plan | POST | PRIOR
Actual
MOTOR VEHICLE REPAIRS AND MAINTENANCE | LSSTF/S-NC/NS/004/22 |  |  | 300000 | <10,000,000.00 | NS | Plan | POST | POST
Actual

## consultancy
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/ AGENCY: LAGOS STATE SPORT TRUST FUND
BUDGET YEAR: 2022
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[5 empty] | 0 |  | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
1 | PRESS AND PUBLICITY | LSSTF/S-C/QCBS/001/22 | QCBS | Lump sum | 1335500 | post | Plan | 20th Jan,2022 | 3rd feb,2022 | 10th Feb,2022 | 24th Feb, 2022 | 2nd March,2022 | 16th March,2022 | 6th April,2022 | 13th April,2022 | 20th April,2022 | 27th April,2022 | 4th May,2022 | 11th May,2022 | 25th May,2022 | 26th May,2022 | NA | 2nd June,2022 | 16th June,2022 | 30th June,2022 | 7th July,2022 | 14th June,2022 | NA
Actual
2 | CONSULTANCY(Out sourcing of public relations) | LSSTF/S-C/QCBS/001/22 | QCBS | Lump sum | 1200000 | post | Plan | 20th Jan,2022 | 3rd feb,2022 | 10th Feb,2022 | 24th Feb, 2022 | 2nd March,2022 | 16th March,2022 | 6th April,2022 | 13th April,2022 | 20th April,2022 | 27th April,2022 | 4th May,2022 | 11th May,2022 | 25th May,2022 | 26th May,2022 | NA | 2nd June,2022 | 16th June,2022 | 30th June,2022
Actual
3 | EXTERNAL AUDITOR | LSSTF/S-C/QCBS/001/22 | QCBS | Lump sum | 2500000 | post | Plan | 20th Jan,2022 | 3rd feb,2022 | 10th Feb,2022 | 24th Feb, 2022 | 2nd March,2022 | 16th March,2022 | 6th April,2022 | 13th April,2022 | 20th April,2022 | 27th April,2022 | 4th May,2022 | 11th May,2022 | 25th May,2022 | 26th May,2022 | NA | 2nd June,2022 | 16th June,2022 | 30th June,2022
Actual
Plan
Actual
Plan
Actual
Plan
Actual

## goods
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: LAGOS STATE SPORTS TRUST FUND
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | MOTOR VEHICLE FUEL CONSUMPTIONS | LSSTF/G/NS/001/22 | NA |  | 1750000 | <10M | NS | POST | POST | Plan | 20th Jan,2022 | 3rd feb,2022 | 10th Feb,2022 | 24th feb,2022 | 2nd Mar,2022 | 9th Mar.2022 | 6th Aprl,2022 | 8th Aprl,2022 | NA | 15th Aprl,2022 | 22nd Aprl,2022 | 6th May,2022 | 24th May,2022 | 8th June,2022
Actual
2 | STATIONERY | LSSTF/G/NS/002/22 | NA |  | 800000 | <10M | NS | POST | POST | Plan | 20th Jan,2022 | 3rd feb,2022 | 10th Feb,2022 | 24th feb,2022 | 2nd Mar,2022 | 9th Mar.2022 | 6th Aprl,2022 | 8th Aprl,2022 | NA | 15th Aprl,2022 | 22nd Aprl,2022 | 6th May,2022 | 24th May,2022 | 8th June,2022
Actual
3 | UNIFORMS AND PROTECTIVE | LSSTF/G/NS/003/22 | NA |  | 750000 | <10M | NS | POST | POST | Plan | 20th Jan,2022 | 3rd feb,2022 | 10th Feb,2022 | 24th feb,2022 | 2nd Mar,2022 | 9th Mar.2022 | 6th Aprl,2022 | 8th Aprl,2022 | NA | 15th Aprl,2022 | 22nd Aprl,2022 | 6th May,2022 | 24th May,2022 | 8th June,2022
Actual
4 | MANAGEMENT AND INFORMATION SYSTEM | LSSTF/G/NS/004/22 | NA |  | 630000 | <10M | NS | POST | POST | Plan | 20th Jan,2022 | 3rd feb,2022 | 10th Feb,2022 | 24th feb,2022 | 2nd Mar,2022 | 9th Mar.2022 | 6th Aprl,2022 | 8th Aprl,2022 | NA | 15th Aprl,2022 | 22nd Aprl,2022 | 6th May,2022 | 24th May,2022 | 8th June,2022
Actual
5 | SUPPLY AND INSTALLATION OF 65KVA DEDICATED GENERATOR FOR THE OLYMPIC SIZE SWIMMING POOL | LSSTF/G/NS/005/22 | NA |  | 20851676.61 | <50M | NS | PRE | PRIOR | Plan | 20th Jan,2022 | 3rd feb,2022 | 10th Feb,2022 | 24th feb,2022 | 2nd Mar,2022 | 9th Mar.2022 | 6th Aprl,2022 | 8th Aprl,2022 | NA | 15th Aprl,2022 | 22nd Aprl,2022 | 6th May,2022 | 24th May,2022 | 8th June,2022
Actual

## works
PROCUREMENT PLAN FOR WORKS
MINISTRY: LAGOS STATE SPORTS TRUST FUND
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | PROCUREMENT OF SPORTS EQUIPMENT TO 644 PUBLIC SECONDARY SCHOOL VIA 6 EDUCATION DISTRICT | LSSTF/W/NCB/001/22 | NA | 100000000 | >500m | NCB | Bill of Quatity | Pre | Plan | prior | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 16th Mar.2021 | 23rd Mar,2021 | 25th March,2021 | 26th March,2021 | NA | 30th Mar,2021 | 7th April,2021 | 14th April,2021 | 28th April,2021 | 5th May,2021
Actual
2 | PROCUREMENT OF SPORTS EQUIPMENT TO LG/LCDA | LSSTF/W/NCB/002/22 | NA | 100000000 | >500m | NCB | Bill of Quatity | pre | Plan | prior | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 16th Mar.2021 | 23rd Mar,2021 | 25th March,2021 | 26th March,2021 | NA | 30th Mar,2021 | 7th April,2021 | 14th April,2021 | 28th April,2021 | 5th May,2021
Actual
3 | REDEVELOPMENT OF ROWE SPORTS CENTRE YABA (SWIMMING FACILITY, SPORTS MEDICINE HALL,SHOOTING RANGE, WEIGHT LIFTING HALL AND JUDO HALL) | LSSTF/W/NCB/003/22 | NA | 250000000 | >500m | NCB | Bill of Quatity | pre | Plan | prior | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 16th Mar.2021 | 23rd Mar,2021 | 25th March,2021 | 26th March,2021 | NA | 30th Mar,2021 | 7th April,2021 | 14th April,2021 | 28th April,2021 | 5th May,2021
Actual
4 | DEVELOPMENT OF SPORTS CENTRES IN THE FIVE DIVISION OF THE STATE (IBILE) | LSSTF/W/NCB/004/22 | NA | 460000000 | >500m | NCB | Bill of Quatity | pre | Plan | prior | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 16th Mar.2021 | 23rd Mar,2021 | 25th March,2021 | 26th March,2021 | NA | 30th Mar,2021 | 7th April,2021 | 14th April,2021 | 28th April,2021 | 5th May,2021
Actual
5 | BALANCE PAYMENT FOR RECONSTRUCTION OF OLYMPIC SIZE SWIMMING POOL | LSSTF/W/NS/005/22 | NA | 43315954.9 | >50m | NS | Bill of Quatity | pre | Plan | prior | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 16th Mar.2021 | 23rd Mar,2021 | 25th March,2021 | 26th March,2021 | NA | 30th Mar,2021 | 7th April,2021 | 14th April,2021 | 28th April,2021 | 5th May,2021
Actual
6 | BALANCE OF PAYMENT FOR ON RENOVATION OF INDOORS SPORTS HALL (MOBOLAJI JOHNSON INDOORS SPORTS HALL) PHASE I | LSSTF/W/NS/006/22 | NA | 35989463.04 | >50m | NS | Bill of Quatity | pre | Plan | prior | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 16th Mar.2021 | 23rd Mar,2021 | 25th March,2021 | 26th March,2021 | NA | 30th Mar,2021 | 7th April,2021 | 14th April,2021 | 28th April,2021 | 5th May,2021
Actual
7 | BALANCE OF PAYMENT FOR ON RENOVATION OF INDOORS SPORTS HALL (MOBOLAJI JOHNSON INDOORS SPORTS HALL) PHASE II | LSSTF/W/NS/007/22 | NA | 55143444.75 | >100m | NS | Lumpsum | pre | Plan | prior | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 16th Mar.2021 | 23rd Mar,2021 | 25th March,2021 | 26th March,2021 | NA | 30th Mar,2021 | 7th April,2021 | 14th April,2021 | 28th April,2021 | 5th May,2021
Actual
8 | BALANCE OF PAYMENT ON REHABILITATION OF FIVE OUTDOORCOURTS AND CONSTRUCTION OF FIVE SPORTS OUTDOOR COURTS AND CONSTRUCTION OF ADDITIONAL TOILETS & SHOWERS | LSSTF/W/NS/008/22 | NA | 34699260.67 | >50m | NS | Bill of Quatity | pre | Plan | prior | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 16th Mar.2021 | 23rd Mar,2021 | 25th March,2021 | 26th March,2021 | NA | 30th Mar,2021 | 7th April,2021 | 14th April,2021 | 28th April,2021 | 5th May,2021
Actual
9 | DEVELOPMENT OF SPORTS CENTRES IN THE FIVE DIVISION OF THE STATE (IBILE) | LSSTF/W/NS/009/22 | NA | 260000000 | >500m | NS | Bill of Quatity | post | Plan | Post | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 16th Mar.2021 | 23rd Mar,2021 | 25th March,2021 | 26th March,2021 | NA | 30th Mar,2021 | 7th April,2021 | 14th April,2021 | 28th April,2021 | 5th May,2021
Actual