## goods
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: MINISTRY OF WEALTH CREATION AND EMPLOYMENT
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Wealth Creation Expenses:Procurement of Equipment Support for Vulnerable Persons such as people living with disabilities, deportees (Wealth Creation) Capitale.t.c. | MWC&E/G/ICB/001/22 | 1 | Various | 846274480 | >1B | ICB | PRE | PRIOR | Plan | 2022-03-02 | 2022-03-09 | 2022-03-16 | 2022-03-23 | 2022-03-30 | 2022-04-06 | 2022-04-13 | 2022-04-16 |  | 2022-04-23 | 2022-04-30 | 2022-05-07
Actual
2 | Procurement of Stationery | MWC&E/G-F/NS/002/22 | 1 | Various | 4040000 | <10M | NS | POST | POST | Plan | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-05 | 2022-03-12 | 2022-03-19 | 2022-03-26 | 2022-03-31 |  | 2022-04-07 | 2022-04-14 | 2022-04-21
Actual
3 | Procurement /Upgrading of Equipments for Job Centres | MWC&E/G/NS/003/22 | 1 | Various | 30000000 | <100M | NCB | PRE | PRIOR | Plan | 2022-02-17 | 2022-02-24 | 2022-03-02 | 2022-03-09 | 2022-03-16 | 2022-03-23 | 2022-03-30 | 2022-04-02 |  | 2022-04-09 | 2022-04-16 | 2022-04-23
Actual
4 | Procurement of Special duties expenses material (Gds). | MWC&E/G/NS/004/22 | 1 | Various | 18128168.2 | <50M | NS | POST | POST | Plan | 2022-03-05 | 2022-03-12 | 2022-03-19 | 2022-03-26 | 2022-04-02 | 2022-04-09 | 2022-04-16 | 2022-04-21 |  | 2022-04-28 | 2022-05-05 | 2022-05-12
Actual
5 | Procurement of Management Information System consumables | MWC&E/G/NS/005/22 | 1 | Various | 2000000 | <10M | NS | POST | POST | Plan | 2022-02-19 | 2022-02-26 | 2022-03-04 | 2022-03-11 | 2022-03-18 | 2022-03-25 | 2022-04-01 | 2022-04-08 |  | 2022-04-15 | 2022-04-22 | 2022-04-29
Actual
6 | Procurement of Consumable for Maintenance of Job centres | MWC&E/G/NS/006/22 | 1 | Various | 5000000 | <10M | NS | POST | POST | Plan | 2022-03-11 | 2022-03-18 | 2022-03-25 | 2022-04-01 | 2022-04-08 | 2022-04-15 | 2022-04-22 | 2022-04-27 |  | 2022-05-04 | 2022-05-11 | 2022-05-18
Actual
7 | Procurement of Uniform & Protective Outfits | MWC&E/G/NS/007/22 | 1 | Various | 1000000 | <10M | NS | POST | POST | Plan | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-22 |  | 2022-04-29 | 2022-05-06 | 2022-05-13
Actual
8 | Procurement of Sports Materials | MWC&E/G/NS/008/22 | 1 | Various | 1000000 | <10M | NS | POST | POST | Plan | 2022-02-26 | 2022-03-04 | 2022-03-11 | 2022-03-18 | 2022-03-25 | 2022-04-01 | 2022-04-08 | 2022-04-01 |  | 2022-04-13 | 2022-04-20 | 2022-04-27
Actual
9 | Procurement of Planning Unit consumable | MWC&E/G/NS/09/22 | 1 | Various | 2000000 | <10M | NS | POST | POST | Plan | 2022-03-02 | 2022-03-09 | 2022-03-16 | 2022-03-23 | 2022-03-30 | 2022-04-06 | 2022-04-13 | 2022-04-15 |  | 2022-04-22 | 2022-04-29 | 2022-05-06
Actual
10 | Procurement of ICT Unit consumables | MWC&E/G/NS/010/22 | 1 | Various | 2000000 | <10M | NS | POST | POST | Plan | 2022-07-04 | 2022-04-14 | 2022-04-21 | 2022-04-28 | 2022-05-05 | 2022-12-05 | 2022-05-19 | 2022-05-22 |  | 2022-05-29 | 2022-05-06 | 2022-12-06
Actual
11 | Procurement of Legal Unit consumables | MWC&E/G/NS/011/22 | 1 | Various | 2000000 | <10M | NS | POST | POST | Plan | 2022-04-03 | 2022-11-03 | 2022-03-18 | 2022-03-25 | 2022-01-04 | 2022-08-04 | 2022-04-15 | 2022-04-17 |  | 2022-04-24 | 2022-01-05 | 2022-08-05
Actual
12 | Procurement of Audit Unit consumables | MWC&E/G/NS/012/22 | 1 | Various | 2000000 | <10M | NS | POST | POST | Plan | 2022-02-03 | 2022-09-03 | 2022-03-16 | 2022-03-23 | 2022-03-30 | 2022-06-04 | 2022-04-13 | 2022-04-16 |  | 2022-04-23 | 2022-04-30 | 2022-07-05
Actual
13 | Procurement of Press/Public Affairs Unit consumables | MWC&E/G/NS/013/22 | 1 | Various | 7000000 | <10M | NS | POST | POST | Plan | 2022-03-03 | 2022-10-03 | 2022-03-17 | 2022-03-24 | 2022-03-31 | 2022-07-04 | 2022-04-14 | 2022-04-17 |  | 2022-04-24 | 2022-01-05 | 2022-08-05
14 | Procurement of Procurement Unit consumables | MWC&E/G/NS/014/22 | 1 | Various | 2000000 | <10M | NS | POST | POST | Plan | 2022-07-03 | 3/114/2022 | 2022-03-20 | 2022-03-27 | 2022-03-04 | 2022-10-04 | 2022-04-17 | 2022-04-22 |  | 2022-04-29 | 2022-06-05 | 2022-05-13
Actual
15 | Procurement of Equipments and Furnitures | MWC&E/G/NS/O15/22 | 1 | Various | 50000000 | <100M | NS | POST | PRIOR | Plan | 2022-01-04 | 2022-08-04 | 2022-04-15 | 2022-04-22 | 2022-04-29 | 2022-06-05 | 2022-05-13 | 2022-05-18 |  | 2022-05-25 | 2022-01-06 | 2022-08-06
Actual
16 | State Cash Transfer Expenses | MWC&E/G/NS/O16/22 | 1 | Various | 126255505 | <500M | NS | POST | PRIOR | Plan | 2022-01-04 | 2022-08-04 | 2022-04-15 | 2022-04-22 | 2022-04-29 | 2022-06-05 | 2022-05-13 | 2022-05-18 |  | 2022-05-25 | 2022-01-06 | 2022-08-06
Actual

## non-cons
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY:
| MINISTRY/ AGENCY: MINISTRY OF WEALTH CREATION & EMPLOYMENT YEAR 2022 | [15 empty] | BUDGET YEAR: 2022
| Contract Description | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
|  | Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
| Printing | MWC&E/S-NC/NS/OO1/22 | 1 | Various | 1000000 | <10M | NS | Plan | POST | POST | 2022-04-07 | 2022-04-14 | 2022-04-21 | 2022-04-28 | 2022-05-05 | 2022-05-12 | 2022-05-19 | Plan | 2022-05-26 | 2022-05-30 |  | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-23
[8 empty] | Actual | [9 empty] | Actual
2 | Special Duties:Payment for Janitorial services | MWC&E/S-NC/NS/OO2/22 | 1 | Various | 4949725.8 | <10M | NS | Plan | POST | POST | 2022-01-04 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | Plan | 2022-02-21 | 2022-02-25 |  | 2022-03-03 | 2022-03-10 | 2022-03-17 | 2022-03-24
[8 empty] | Actual | [9 empty] | Actual
3 | Production of I.D cards for Tradesmen & Artisans | MWC&E/S-NC/003/22 | 1 | 6000 | 2000000 | <10M | NS | Plan | POST | POST | 2022-02-17 | 2022-02-24 | 2022-03-02 | 2022-03-09 | 2022-03-16 | 2022-03-23 | 2022-03-30 | Plan | 2022-04-06 | 2022-04-08 |  | 2022-04-19 | 2022-04-23 | 2022-04-30 | 2022-05-09
[8 empty] | Actual | [9 empty] | Actual
4 | Partitioning and Rehabilitation of Offices | MWC&E/S-NC/004/22 |  | Various | 31641082 | <50M | NS | Plan |  |  | 2022-04-07 | 2022-04-14 | 2022-04-21 | 2022-04-28 | 2022-05-05 | 2022-05-12 | 2022-05-19 | Plan | 2022-05-26 | 2022-05-30 |  | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-23
[8 empty] | Actual | [9 empty] | Actual
5 | Uniform and Protective | MWC&E/S-NC/005/22 |  | Various | 1000000 | <10M | NS | Plan |  |  | 2022-02-17 | 2022-02-24 | 2022-03-02 | 2022-03-09 | 2022-03-16 | 2022-03-23 | 2022-03-30 | Plan | 2022-04-06 | 2022-04-08 |  | 2022-04-19 | 2022-04-23 | 2022-04-30 | 2022-05-09
[8 empty] | Actual | [9 empty] | Actual
6 | Renovation of Service Charter desk office | MWC&E/S-NC/006/22 |  | Various | 15000000 | <50M | NS | Plan |  |  | 2022-01-04 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | Plan | 2022-02-21 | 2022-02-25 |  | 2022-03-03 | 2022-03-10 | 2022-03-17 | 2022-03-24
[8 empty] | Actual | [9 empty] | Actual
[8 empty] | Plan | [9 empty] | Plan
[8 empty] | Actual | [9 empty] | Actual

## trg conf wsh (2)
PROCUREMENT PLAN FOR WORKSHOP/TRAINING
MINISTRY/ AGENCY: MINISTRY OF WEALTH CREATION AND EMPLOYMENT
BUDGET YEAR: Y2022
S/N | Description of Training/Workshop/ Conference | Package Number | Objective of Training/Workshop/Conference | No. of Participants | Duration (days) | Plan vs Actual | Venue | Tuition Fee N | Transport Fare N | Allowance N | Total Cost N
1 | CIPM | MWC&E/S-WTC/0O1/22 | Capacity Building | 10 | 4 | Plan | Abj/Nov | 78,500.00X10=785,000.00 | 55000 | Allowances
Actual
2 | NBA | MWC&E/S-WTC/0O2/22 | Capacity Building | 1 | 5 | Plan | Abj/Sep | 120000 | 55000 | Allowances
Actual
3 | NIM | MWCE/S-WTC/003/22 | Capacity Building | 3 | 4 | Plan | Abj/Sep | 65,000.00x3=195,000.00 | 55000 | Allowances
Actual
4 | NSA | MWC&E/S-WTC/0O4/22 | Capacity Building | 1 | 4 | Plan | Abj/Sep | 60000 | 55000 | Allowances
Actual
5 | NES | MWC&E/S-WTC/005/22 | Capacity Building | 8 | 4 | Plan | Abj/Sep | 40,000.00x8=320,000.00 | 55000 | Allowances
Actual
6 | CIPSMN | MWC&E/S-WTC/006/22 | Capacity Building | 2 | 4 | Plan | Abj/Aug | 60,000.00x2=120,000.00 | 55000 | Allowances
Actual
7 | NIPR | MWC&E/S-WTC/0O7/22 | Capacity Building | 2 | 4 | Plan | Enugu/Nov | 65,000.00x2=130,000.00 | 55000 | Allowances
Actual
8 | CASSON | MWC&E/S-WTC/008/22 | Capacity Building | 4 | 4 | Plan | Jos/Sep | 40,000.00x4=160,000.00 | 55000 | Allowances
Actual
9 | CST&RI | MWC&E/S-WTC/009/22 | Capacity Building | 2 | 4 | Plan | Abj/Nov | 60,000.00x2=120,000.00 | 55000 | Allowances
Actual
10 | COREN | MWC&E/S-WTC/010/22 | Capacity Building | 1 | 4 | Plan | Abj/Aug | 40000 | 55000 | Allowances
Actual
11 | ICAN | MWC&E/S-WTC/011/22 | Capacity Building | 2 | 5 | Plan | Abj/Sep | 180,000.00x2=360,000.00 | 55,000x2=110,000.00 | 222,000x2=444,000,000.00
Actual
12 | ANAN | MWC&E/S-WTC/012/22 | Capacity Building | 8 | 5 | Plan | Abj/Sep | 45,000.00x8=360,000.00 | 55,000x8=440,000.00 | 1763000
Actual
13 | IPAN | MWC&E/S-WTC/013/22 | Capacity Building | 2 | 4 | Plan | Abu/Sep | 60,000.00x2=120,000.00 | 55000 | Allowances
Actual
B | Conference &Seminer | 22000000 | [5 empty] | WORKSHOP&TRAINING |  |  | 10000000

## Non-Proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: MINISTRY OF WEALTH CREATION AND EMPLOYMENT
BUDGET YEAR: Y2022
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/ Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER
1 | Travel & Transport | MWC&E/NP/NM/001/22 | 4,410,000 | Plan | 367500 | 367500 | 367500 | 367500 | 367500 | 367500 | 367500 | 367500 | 367500 | 367500 | 367500 | 367500
Actual
2 | General Utility Services | MWC&E/NP/NM/002/22 | 4,540,000 | Plan | 378333 | 378333 | 378333 | 378333 | 378333 | 378333 | 378333 | 378333 | 378333 | 378333 | 378333 | 378333
Actual
3 | Miscellaneous | MWC&E/NP/NM/003/22 | 5560000 | Plan | 463333 | 463333 | 463333 | 463333 | 463333 | 463333 | 463333 | 463333 | 463333 | 463333 | 463333 | 463333
Actual
4 | Servicing of Meetings | MWC&E/NP/NM/004/22 | 3000000 | Plan | 300000 |  | 300000 |  | 300000 |  | 300000 |  | 300000 |  | 300000
Actual
5 | Special duties expenses:Welfare Package for Retirng Staff | MWC&E/NP/NM/006/22 | 3000000 | Plan | [5 empty] | 2000000 | [5 empty] | 1000000
Actual
6 | Maintenance of office building (Running cost) | MWC&E/NP/NM/012/22 | 3770000 | Plan | 314166 | 314167 | 314166 | 314167 | 314166 | 314167 | 314166 | 314167 | 314166 | 314167 | 314166 | 314167
Actual
7 | M/V Maintenance and Repair (Running cost) | MWC&E/NP/NM/013/22 | 6640000 | Plan | 553333 | 553333 | 553333 | 553333 | 553333 | 553333 | 553333 | 553333 | 553333 | 553333 | 553333 | 553333
Actual
8 | M/V Fuel Consumption (Running cost) | MWC&E/NP/NM/014/22 | 7040000 | Plan | 586666 | 586667 | 586666 | 586667 | 586666 | 586667 | 586666 | 586667 | 586666 | 586667 | 586666 | 586667
Actual
9 | Monitoring and Evaluation Expenses | MWC&E/NP/NM/015/22 | 3000000 | Plan |  |  | 1500 | [6 empty] | 1500
Actual
10 | Upkeep/Maintenance of Incubation Centres (Running cost at incubator centres). | MWC&E/NP/NM/016/22 | 250000 | Plan | 20833 | 20833 | 20833 | 20833 | 20833 | 20833 | 20833 | 20833 | 20833 | 20833 | 20833 | 20833
Actual
11 | Visitation/Meetings with Stakeholders | MWC&E/NP/NM/017/22 | 2000000 | Plan | 500000 |  |  | 500000 |  |  | 500000 |  |  | 500000
Actual
Sundry Expenses
12 |  | MWC&E/NP/NM/018/22 | 3000000 | Plan
Actual

## consultancy (2)
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/ AGENCY: MINISTRY OF WEALTH CREATION & EMPLOYMENT
BUDGET YEAR: Y2022
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award |  | Draft Report | Final Report | Final Cost
[7 empty] | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
1 | Management Consultancy Services | MWC&E/S-C/CQS/001/22 | CQS | Lump sum | 1000000 | Post | Plan | 4/4/2022 | 11/4/2022 | 19/4/2022 | 25/4/2022 | 29/4/2022 | 6/5/2022 | 13/5/2022 | 20/5/2022 | 27/5/2022 | 2/6/2022 | 10/6/2022 | 17/6/2022 | 24/6/2022 | 29/6/2022 |  | 6/7/2022 | 13/7/2022 | 20/7/2022 | 27/7/2022 | 3/8/2022
Actual
2 | Stakeholders Summit | MWC&E/S-C/CQS/002/22 | CQS | Lump sum | 15000000 | Prior | Plan | 7/3/2022 | 14/3/2022 | 21/3/2022 | 28/3/2022 | 4/4/2022 | 11/4/2022 | 19/4/2022 | 25/4/2022 | 2/5/2022 | 9/5/2022 | 16/5/2022 | 23/5/2022 | 30/5/2022 | 3/6/2022 |  | 10/6/2022 |  | 24/6/2022 | 1/7/2022 | 8/7/2022
Actual
3 | Retreat | MWC&E/S-C/CQS/003/22 | CQS | Lump sum | 25000000 | Prior | Plan | 4/8/2022 | 11/8/2022 | 18/8/2022 | 26/8/2022 | 1/9/2022 | 8/9/2022 | 15/9/2022 | 22/9/2022 | 29/9/2022 | 6//10/2022 | 13/10/2022 | 20/10/2022 | 27/10/2022 | 31/10/2022 |  | 7/11/2022 | 14/11/2022 | 21/11/2022 | 28/11/2022 | 5/12/2022
Actual
4 | Special duties expenses:Wellness services | MWC&E/S-C/CQS/004/22 | CQS | Lump sum | 6000000 | Post | Plan | 2022-03-03 | 2022-10-03 | 2022-03-17 | 2022-03-21 | 28/3/2022 | 2022-04-04 | 2022-11-04 | 2022-04-19 | 2022-04-25 | 2022-02-05 | 2022-09-05 | 2022-05-16 | 2022-05-23 | 2022-03-06 |  | 2022-10-06 | 2022-06-17 | 2022-06-24 | 2022-01-07 | 2022-08-08
Actual
5 | Annual Statistical document/ Data collection on Employment | MWC&E/S-C/LCS/005/22 | LCS | Lump sum | 1000000 | Post | Plan | 2022-02-04 | 2022-09-04 | 2022-04-16 | 2022-04-25 | 2022-04-30 | 2022-09-05 | 2022-05-16 | 2022-05-20 | 2022-05-27 | 2022-06-06 | 13/6/2022 | 2022-06-20 | 2022-06-27
Actual
6 | Entrepreneurship and Employability Skill development for Youth | MWC&E/S-C/CQS/006/22 | CQS | Lump sum | 96000000 | Prior | Plan | 2022-04-02 | 2022-11-02 | 2022-02-18 | 2022-02-25 | 2022-04-03 | 2022-11-03 | 2022-03-18 | 2022-03-25 | 2022-01-04 | 2022-08-04 | 2022-04-14 | 2022-04-22 | 2022-04-29 | 2022-06-05 |  | 2022-05-13 | 2022-05-20 | 2022-05-27 | 2022-03-06 | 2022-10-06
Actual
7 | Celebration of Artisans Week/Celebration of global Entrepreneurship Week | MWC&E/S-C/LCS/007/22 | LCS | Lump sum | 21500000 | Prior | Plan | 3/2/2022 | 10/2/2022 | 17/2/2022 | 24/2/2022 | 2/3/2022 | 9/3/2022 | 16/3/2022 | 23/3/2022 | 30/3/2022 | 6/4/2022 | 13/4/2022 | 20/4/2022 | 27/4/2022 | 29/4/2022 |  | 6/5/2022 | 13/5/2022 | 20/5/2022 | 27/5/2022 | 3/6/2022
Actual
8 | Mentorship/Apprenticeship and Mindset Re-Orientation | MWC&E/S-C/CQS/008/22 | CQS | Lump sum | 20000000 | Prior | Plan | 5/3/20/22 | 12/3/2022 | 19/3/2022 | 26/3/2022 | 2/4/2022 | 9/4/2022 | 16/4/2022 | 23/4/2022 | 30/4/2022 | 9/5/2022 | 16/5/2022 | 23/5/2022 | 30/5/2022 | 2/6/2022 |  | 9/6/2022 | 16/6/2022 | 23/6/2022 | 30/6/2022 | 7/7/2022
Actual
9 | Corporate Lagos Expenses | MWC&E/S-C/CQS/009/22 | CQS | Lump sum | 13000000 | Prior | Plan | 7/4/2022 | 14/4/2022 | 21/4/2022 | 28/4/2022 | 5/5/2022 | 12/5/2022 | 19/5/2022 | 26/5/2022 | 2/6/2022 | 9/6/2022 | 16/6/2022 | 23/6/2022 | 30/6/2022 | 4/7/2022 |  | 11/7/2022 | 18/7/2022 | 25/7/2022 | 29/7/2022 | 8/8/2022
Actual
10 | Organisation of Job fair | MWC&E/S-C/LCS/010/22 | LCS | Lump sum | 14000000 | Prior | Plan | 6/5/2022 | 13/5/2022 | 20/5/2022 | 27/5/2022 | 3/6/2022 | 10/6/2022 | 17/6/2022 | 24/6/2022 | 1/7/2022 | 8/7/2022 | 15/7/2022 | 22/7/2022 | 29/7/2022 | 3/8/2022 |  | 10/8/2022 | 17/8/2022 | 24/8/2022 | 31/8/2022 | 1/9/2022
Actual
11 | Virtual Market/ Database Portal | MWCE/S-C/QCBS/011/22 | QCBS | Lump sum | 100233623 | Prior | Plan | 2/4/2022 | 9/4/2022 | 16/4/2022 | 23/4/2022 | 30/4/2022 | 7/5/2022 | 14/5/2022 | 21/5/2022 | 28/5/2022 | 6/6/2022 | 13/6/2022 | 20/6/2022 | 27/6/2022 | 30/6/2022 |  | 7/7/2022 | 14/7/2022 | 21/7/2022 | 28/7/2022 | 4/8/2022
Actual
12 | Graduate Intership Programme | MWC&E/S-C/QCBS/012/22 | QCBS | Lump sum | 650000000 | Prior | Plan | 2/4/2022 | 9/4/2022 | 16/4/2022 | 23/4/2022 | 30/4/2022 | 7/5/2022 | 14/5/2022 | 21/5/2022 | 28/5/2022 | 6/6/2022 | 13/6/2022 | 20/6/2022 | 27/6/2022 | 1/7/2022 |  | 8/7/2022 | 15/7/2022 | 22/7/2022 | 29/7/2022 | 5/8/2022
Actual
13 | Non-Oil Export Promotion Programme (Business Support Clinic for Entrepreneurs/start-ups in Lagos State)-(Cap) | MWC&E/S-C/QCBS/013/22 | QCBS | Lump sum | 22050000 | Prior | Plan | 4/5/2022 | 11/5/2022 | 18/5/2022 | 25/5/2022 | 1/6/2022 | 8/6/2022 | 15/6/2022 | 22/6/2022 |  | 6/7/2022 | 13/7/2022 | 20/7/2022 | 27/7/2022 | 29/7/2022 |  | 8/8/2022 | 15/8/2022 | 22/8/2022 | 29/8/2022 | 5/9/2022
Actual
14 | Construction/Equipment:Creation of Industrial Hub(Cap) | MWC&E/S-C/QCBS/014/22 | QCBS | Lump sum | 1641321561 | Prior | Plan | 4/5/2022 | 11/5/2022 | 18/5/2022 | 25/5/2022 | 1/6/2022 | 8/6/2022 | 15/6/2022 | 22/6/2022 |  | 6/7/2022 | 13/7/2022 | 20/7/2022 | 27/7/2022 | 29/7/2022 |  | 8/8/2022 | 15/8/2022 | 22/8/2022 | 29/8/2022 | 5/9/2022
Actual
15 | Employability Skill development for Youth | MWC&E/S-C/QCBS/015/22 | QCBS | Lump sum | 173000000 | Prior | Plan | 2/4/2022 | 9/4/2022 | 16/4/2022 | 23/4/2022 | 30/4/2022 | 7/5/2022 | 14/5/2022 | 21/5/2022 | 28/5/2022 | 6/6/2022 | 13/6/2022 | 20/6/2022 | 27/6/2022 | 1/7/2022 |  | 8/7/2022 | 15/7/2022 | 22/7/2022 | 29/7/2022 | 5/8/2022
Actual
1

## works
PROCUREMENT PLAN FOR WORKS
MINISTRY: MWC&E
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Partioning and Renovation of Office Building (Capital) | MWC&E/W/NS/001/21 | LS | 31641082 | <100M | NS | BOQ | POST | Plan | PRIOR | 2022-01-28 | 2022-02-04 | 2022-02-11 | 2022-02-25 | 2022-03-03 | 2022-03-10 | 2022-03-17 | 2022-03-21 | 0 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-19 | 2022-04-25
Actual
2 | Construction /equipment of Industrial/ incubation Hubs (Building) Capital | MWC&E/W/ICB/002/21 | LS | 1641321561 | <2B | ICB | BOQ | PRE | Plan | PRIOR | 2022-03-02 | 2022-10-02 | 2022-02-17 | 2022-02-24 | 2022-02-03 | 2022-09-03 | 2022-03-16 | 2022-03-18 | 0 | 44280 | 2022-04-01 | 2022-04-08 | 2022-04-15 | 2022-04-22
Actual
15000000
31641082
30000000

## Consultant 3
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/ AGENCY: MINISTRY OF WEALTH CREATION & EMPLOYMENT
BUDGET YEAR: Y2022
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[7 empty] | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
1 | Management Consultancy Services | MWC&E/S/CQS/01/2022 | CQS | Lump sum | 1000000 | Post | Plan
Actual
2 | Stakeholders Summit | MWC&E/S/CQS/02/2022 | CQS | Lump sum | 15000000 | Post | Plan
Actual
3 | Organisation of Retreat | MWC&E/S/CQS/03/2022 | CQS | Lump sum | 25000000 | Post | Plan
Actual
4 | Special duties expenses: Services | MWC&E/S/CQS/04/2022 | CQS | Lump sum | 3935000 | Post | Plan
Actual
5 | Annual Statistical document/ Data collection on Employment | MWC&E/S/LCS/05/2022 | LCS | Lump sum | 3064006 | Post | Plan
Actual
6 | Entrepreneurship and Employability Skill development for Youth | MWC&E/S/CQS/06/2022 | CQS | Lump sum | 1000000 | Post | Plan
Actual
7 | Celebration of Artisans Week/Celebration of global Entrepreneurship Week | MWC&E/S/LCS/07/2022 | LCS | Lump sum | 20340000 | Post | Plan
8 | Mentorship/Apprenticeship and Mindset Re-Orientation | MWC&E/S/CQS/08/2022 | CQS | Lump sum | 20000000 | Post | Actual
9 | Corporate Lagos Expenses | MWC&E/S/CQS/09/2022 | CQS | Lump sum | 21500000 | Post
10 | Organisation of Job fair | MWC&E/S/LCS/10/2022 | LCS | Lump sum | 20000000 | Post
11 | Virtual Market/ Database Portal | MWC&E/S/CQS/11/2022 | CQS | Lump sum | 300000000 | Prior
12 | Graduate Intership Programme | MWC&E/S/QCBS/12/2022 | QCBS | Lump sum | 1200000000 | Prior
13 | Non-Oil Export Promotion Programme (Business Support Clinic for Entrepreneurs/start-ups in Lagos State). | MWC&E/S/CQS/13/2022 | CQS | Lump sum | 35000000 | Post
2000000
1

## consultancy
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/AGENCY: MINISTRY OF WEALTH CREATION AND EMPLOYMENT
BUDGET YEAR: Y2022
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[7 empty] | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
1 | Management Consultancy Services | MWC&E/S/CQS/01/2020 | CQS | Lump sum | 2000000 | Post | Plan | 4/2/2020
Actual
2 | Stakeholders Summit | MWC&E/S/CQS/02/2020 | CQS | Lump sum | 10000000 | Post | Plan
Actual
3 | Organisation of Retreat | MWC&E/S/CQS/03/2020 | CQS | Lump sum | 10000000 | Post | Plan
Actual
4 | Special duties expenses: Services | MWC&E/S/CQS/04/2020 | CQS | Lump sum | 3935000 | Post | Plan
Actual
5 | Annual Statistical document/ Data collection on Employment | MWC&E/S/LCS/05/2020 | LCS | Lump sum | 600000 | Post | Plan
Actual
6 | Entrepreneurship and Employability Skill development for Youth | MWC&E/S/CQS/06/2020 | CQS | Lump sum | 88540000 | Post | Plan
Actual
7 | Celebration of Artisans Week/Celebration of global Entrepreneurship Week | MWC&E/S/LCS/07/2020 | LCS | Lump sum | 20340000 | Post | Plan
8 | Mentorship/Apprenticeship and Mindset Re-Orientation | MWC&E/S/CQS/08/2020 | CQS | Lump sum | 9255000 | Post | Actual
9 | Corporate Lagos Expenses | MWC&E/S/CQS/09/2020 | CQS | Lump sum | 5000000 | Post | plan
10 | Organisation of Job fair | MWC&E/S/LCS/10/2020 | LCS | Lump sum | 20000000 | Post
11 | Virtual Market/ Database Portal | MWC&E/S/CQS/11/2020 | CQS | Lump sum | 197496683 | Prior
12 | Graduate Intership Programme | MWC&E/S/QCBS/12/2020 | QCBS | Lump sum | 1060000000 | Prior
13 | Non-Oil Export Promotion Programme (Business Support Clinic for Entrepreneurs/start-ups in Lagos State). | MWC&E/S/CQS/13/2020 | CQS | Lump sum | 22050000 | Post
1